## Shuklaganj (2)
PROGRESS REPORT FOR 05 MLD SHUKLAGANJ SITE
Sr. No. | Description of Items | Amount | % | Proposed BOQ Amount | Milestone-1 (From 15th March.'21 to 1st Sep'21) |  | Milestone-2 (From 2nd Sep'21 to 27th Dec'21 ) |  | Milestone-3 (From 28th Dec'21 to 25th March'22 ) |  | Achieved for 3rd Milestone |  | Milestone-4 (From 26th March'22 to 2nd May'22 ) |  | Achieved for 4th Milestone |  | Milestone-5 (From 3rd May'22 to 2nd July'22 ) |  | Achieved for 5th Milestone |  | Milestone-6 (From 3rd July'22 to 8th Sep'22 ) |  | Achieved for 6th Milestone |  | Milestone-7 (From 9th Sep'22 to 12th Nov'22 ) |  | Achieved for 7th Milestone |  | Milestone-8 (From 13th Nov'22 to 14th Dec.'22 ) |  | Achieved for 8th Milestone |  | Total Scope | Achieved | Percentage | Cumulative |  | Upto Oct'22 | Upto Sept'22 | For Oct'22 | Upto 4th Milestone |  | Achieved For 5th Milestone |  | Need for 5th Milestone
[5 empty] | % | Amount | % | Amount | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount
[6 empty] | 26618774.9056 |  | 26618774.6155 |  | 26618774.996 |  |  |  | 26618774.57 |  |  |  | 26618775.485 |  |  |  | 26618775.2252 |  |  |  | 26618774.9961 |  |  |  | 26618775.2063
I | Design & Drawing of STP | 10647510 | [30 empty] | 10647510 | 10647510 | 100%
1 | On approval of BEP |  | 50% | 5323755 | 100% | 5323755 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 5323755 | 100% | 100% | 0% | 100% | 5323755 | 0% | 0 |  | 0
2 | On approval of design & drawings for Civil & Sewerage works |  | 50% | 5323755 | 90% | 4791379.5 |  | 0 |  | 0 |  | 0 | 10% | 532375.5 | 10% | 532375.5 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 5323755 | 100% | 100% | 0% | 100% | 5323755 | 0% | 0 |  | 0
[36 empty] | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
II | CONSTRUCTION | [34 empty] | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
A | SHUKLAGANJ STP (5 MLD) | 106475100 | [33 empty] | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
i) | SBR Basin Area | 23956898 | [30 empty] | 23956898 | 18685657.44 | 78% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 479137.96 | 100% | 479137.96 | 0% |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 479137.96 | 100% | 100% | 0% | 100% | 479137.96 | 0% | 0 |  | 0
2 | Excavation wall footing |  | 8% | 1916551.84 | 60% | 1149931.104 | 40% | 766620.736 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 1916551.84 | 100% | 100% | 0% | 100% | 1916551.84 | 0% | 0 |  | 0
3 | PCC wall footing |  | 10% | 2395689.8 |  | 0 | 53% | 1268992.594 | 47% | 1126697.206 | 47% | 1125974.206 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 2394966.8 | 100% | 100% | 0% | 100% | 2395689.8 | 0% | 0 |  | 0
4 | RCC Foundation/Raft of wall |  | 12% | 2874827.76 |  | 0 |  | 0 | 100% | 2874827.76 | 100% | 2874827.76 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 2874827.76 | 100% | 100% | 0% | 100% | 2874827.76 | 0% | 0 |  | 0
5 | Wall 50% of total upto base slab |  | 10% | 2395689.8 |  | 0 |  | 0 | 100% | 2395689.8 | 100% | 2395689.8 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 2395689.8 | 100% | 100% | 0% | 100% | 2395689.8 | 0% | 0 |  | 0
6 | Walls (balance 50% of upto base slab) |  | 10% | 2395689.8 |  | 0 |  | 0 | 50% | 1197844.9 | 50% | 1197844.9 | 50% | 1197844.9 | 50% | 1197844.9 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 2395689.8 | 100% | 100% | 0% | 100% | 2395689.8 | 0% | 0 |  | 0
7 | PCC Base Slab |  | 15% | 3593534.7 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3593534.7 | 100% | 3593534.7 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 3593534.7 | 100% | 100% | 0% | 100% | 3593534.7 | 0% | 0 |  | 0
8 | RCC Foundation base slab |  | 11% | 2635258.78 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2635258.78 | 100% | 2635258.78 |  | 0 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 100% | 2635258.78 | 100% | 66% | 34% | 66.1% | 1741906.0536 | 0% | 0 | 0% | 0
9 | Wall 50% of total lift work |  | 10% | 2395689.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 479137.96 |  | 0 | 60% | 1437413.88 |  | 0 | 20% | 479137.96 |  | 0 |  | 0 | [5 empty] | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Walls (balance 50% of Total Lift work) |  | 7% | 1676982.86 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32% | 536634.5152 |  | 0 | 68% | 1140348.3448 |  | 0 |  | 0 | [5 empty] | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
13 | Hydro Testing /Finishing works |  | 5% | 1197844.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1197844.9 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
ii | Chlorination Tank Area | 2395690 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 2395690 | 2275905.5 | 95% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 47913.8 | 100% | 100% | 0% | 100% | 47913.8 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 311439.7 |  | 0 |  |  | 100% | 311439.7 | 100% | 311439.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 311439.7 | 100% | 100% | 0% | 100% | 311439.7 | 0% | 0 |  | 0
3 | PCC |  | 15% | 359353.5 |  | 0 |  | 0 | 100% | 359353.5 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 100% | 0% | 100% | 359353.5 | 0% | 0 |  | 0
4 | RCC Foundation/Raft |  | 25% | 598922.5 |  | 0 |  | 0 | 100% | 598922.5 | 100% | 598922.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 598922.5 | 100% | 100% | 0% | 100% | 598922.5 | 0% | 0 |  | 0
5 | Wall 50% of total lift work |  | 15% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 359353.5 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 100% | 0% | 80% | 287482.8 | 20% | 71870.7 |  | 0
6 | Walls (balance 50% of Total Lift work) |  | 20% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 | 26% | 124575.88 | 26% | 124575.88 | 74% | 354562.12 | 74% | 354562.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 479138 | 100% | 100% | 0% | 0% | 0 | 100% | 479138 |  | 0
7 | Baffle Walls work |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 | 100% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 119784.5 | 100% | 100% | 0% | 0% | 0 | 100% | 119784.5 | 0% | 0
8 | Hydro Testing /Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iii | Chlorination Room Area | 2395690 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2395690 | 2036336.5 | 85% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 47913.8 | 100% | 100% | 0% | 100% | 47913.8 | 0% | 0 |  | 0
2 | Excavation |  | 8% | 191655.2 |  | 0 |  | 0 | 100% | 191655.2 | 100% | 191655.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 191655.2 | 100% | 100% | 0% | 100% | 191655.2 | 0% | 0 |  | 0
3 | PCC |  | 10% | 239569 |  | 0 |  | 0 | 100% | 239569 | 100% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 239569 | 100% | 100% | 0% | 100% | 239569 | 0% | 0 |  | 0
4 | RCC Foundation/Column footing |  | 25% | 598922.5 |  | 0 |  | 0 | 100% | 598922.5 | 100% | 598922.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 598922.5 | 100% | 100% | 0% | 100% | 598922.5 | 0% | 0 |  | 0
5 | Column & Beam |  | 15% | 359353.5 |  | 0 |  | 0 | 50% | 179676.75 | 50% | 179676.75 | 50% | 179676.75 | 50% | 179676.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 100% | 0% | 80% | 287482.8 | 20% | 71870.7 | 0% | 0
6 | Ground floor Slab |  | 10% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 239569 | 100% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 239569 | 100% | 100% | 0% | 0% | 0 | 100% | 239569 | 0% | 0
7 | Roof Slab |  | 15% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 359353.5 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 0% | 100% | 0% | 0 | 100% | 359353.5 |  | 0
8 | Brickwork |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Plaster |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Testing/Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iv | Guard Room Area | 1676983 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1676983 | 1257737.25 | 75% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 33539.66 | 100% | 33539.66 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 33539.66 | 100% | 100% | 0% | 100% | 33539.66 | 0% | 0 |  | 0
2 | Excavation |  | 8% | 134158.64 | 100% | 134158.64 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 134158.64 | 100% | 100% | 0% | 100% | 134158.64 | 0% | 0 |  | 0
3 | PCC |  | 10% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
4 | RCC Foundation/column footing |  | 10% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
5 | Column & Beam |  | 15% | 251547.45 | 100% | 251547.45 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 251547.45 | 100% | 100% | 0% | 100% | 251547.45 | 0% | 0 |  | 0
6 | RCC Ground floor Slab |  | 15% | 251547.45 |  | 0 |  | 0 | 100% | 251547.45 | 100% | 251547.45 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 251547.45 | 100% | 100% | 0% | 100% | 251547.45 | 0% | 0 |  | 0
7 | RCC Roof Slab |  | 5% | 83849.15 |  | 0 |  | 0 | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 83849.15 | 100% | 100% | 0% | 100% | 83849.15 | 0% | 0 |  | 0
8 | Brick work |  | 10% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
9 | Plumbing, fixtures |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Sanitary works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
11 | Electrification work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
12 | Plaster |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 83849.15
13 | Finishing works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iv | Admin Bldg Area (G+1) | 5270517 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5270517 | 2055501.63 | 39% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 105410.34 | 100% | 105410.34 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 105410.34 | 100% | 100% | 0% | 100% | 105410.34 | 0% | 0 |  | 0
2 | Excavation |  | 5% | 263525.85 |  | 0 | 100% | 263525.85 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 263525.85 | 100% | 100% | 0% | 100% | 263525.85 | 0% | 0 |  | 0
3 | PCC |  | 7% | 368936.19 |  | 0 |  | 0 | 100% | 368936.19 | 100% | 368936.19 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 368936.19 | 100% | 100% | 0% | 100% | 368936.19 | 0% | 0 |  | 0
4 | Column footings/Foundation |  | 10% | 527051.7 |  | 0 |  | 0 | 100% | 527051.7 | 100% | 527051.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 527051.7 | 100% | 100% | 0% | 100% | 527051.7 | 0% | 0 |  | 0
5 | Column & Beam up to Floor Base slab |  | 15% | 790577.55 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 790577.55 | 100% | 790577.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 790577.55 | 100% | 100% | 0% | 100% | 790577.55 | 0% | 0 |  | 0
6 | Floor base Slab |  | 15% | 790577.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 790577.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 790577.55
7 | Column & Beam upto Roof Slab |  | 8% | 421641.36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 421641.36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | 1st Floor Roof Slab |  | 13% | 685167.21 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 685167.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Brickwork |  | 8% | 421641.36 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 421641.36 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Electrification, plumbing, fixtures , sanitary works |  | 7% | 368936.19 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368936.19 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
11 | Plaster |  | 5% | 263525.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 263525.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
12 | finishing works |  | 5% | 263525.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 263525.85 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
v | Air Blower Room Area | 4791380 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4791380 | 2635259 | 55% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 95827.6 | 100% | 95827.6 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 95827.6 | 100% | 100% | 0% | 100% | 95827.6 | 0% | 0 |  | 0
2 | Excavation |  | 8% | 383310.4 |  | 0 | 100% | 383310.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 383310.4 | 100% | 100% | 0% | 100% | 383310.4 | 0% | 0 |  | 0
3 | PCC |  | 15% | 718707 |  | 0 |  | 0 | 100% | 718707 | 100% | 718707 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 718707 | 100% | 100% | 0% | 100% | 718707 | 0% | 0 |  | 0
4 | RCC Foundation/column footing |  | 15% | 718707 |  | 0 |  | 0 | 100% | 718707 | 100% | 718707 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 718707 | 100% | 100% | 0% | 100% | 718707 | 0% | 0 |  | 0
5 | Column & Beam |  | 15% | 718707 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 718707 | 100% | 718707 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 718707 | 100% | 100% | 0% | 100% | 718707 | 0% | 0 |  | 0
6 | RCC Roof Slab |  | 20% | 958276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 958276
7 | Cable Trench Work |  | 10% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | Brick work |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 239569 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Plaster |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 239569 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Testing/Finishing work |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 239569 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
vi | Staff Quarter Area (G+1) | 1676983 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1676983 | 1299661.825 | 77.5% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 33539.66 | 100% | 33539.66 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 33539.66 | 100% | 100% | 0% | 100% | 33539.66 | 0% | 0 |  | 0
2 | Excavation |  | 8% | 134158.64 | 100% | 134158.64 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 134158.64 | 100% | 100% | 0% | 100% | 134158.64 | 0% | 0 |  | 0
3 | PCC |  | 10% | 167698.3 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
4 | RCC Foundation/column footing |  | 10% | 167698.3 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
5 | Column & Beam upto ground floor slab |  | 15% | 251547.45 |  | 0 |  | 0 | 100% | 251547.45 | 100% | 251547.45 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 251547.45 | 100% | 100% | 0% | 100% | 251547.45 | 0% | 0 |  | 0
6 | RCC Ground floor Slab (Base floor slab) |  | 10% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 167698.3 | 100% | 100% | 0% | 100% | 167698.3 | 0% | 0 |  | 0
7 | Column upto roof slab & RCC 1st floor Slab |  | 20% | 335396.6 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 335396.6 | 100% | 335396.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 335396.6 | 100% | 100% | 0% | 100% | 335396.6 | 0% | 0 |  | 0
8 | Brick work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 | 50% | 41924.575 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 50% | 41924.575 | 50% | 50% | 0% | 50% | 41924.575 | 0% | 0 | 50% | 41924.575
9 | Plumbing, fixtures , sanitary works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Electrification work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
11 | Plaster |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 83849.15
12 | Finishing works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
vii | Inlet Chamber Area | 1437414 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1437414 | 790577.7 | 55% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 28748.28 |  | 0 |  | 0 | 100% | 28748.28 | 100% | 28748.28 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 28748.28 | 100% | 100% | 0% | 100% | 28748.28 | 0% | 0 |  | 0
2 | Excavation & PCC |  | 13% | 186863.82 |  | 0 |  |  | 100% | 186863.82 | 100% | 186863.82 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 186863.82 | 100% | 100% | 0% | 100% | 186863.82 | 0% | 0 |  | 0
3 | RCC Foundation/Column footing |  | 15% | 215612.1 |  | 0 |  |  | 100% | 215612.1 | 100% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 215612.1 | 100% | 100% | 0% | 100% | 215612.1 | 0% | 0 |  | 0
4 | Column & Beam |  | 25% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 359353.5 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 40% | 60% | 25.45% | 91455.4658 | 74.55% | 267898.0343 | 0% | 0
5 | RCC Slab |  | 20% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 287482.8
6 | RCC Wall |  | 20% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
7 | Hydro Testing /Finishing works |  | 5% | 71870.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 71870.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
viii | Manual & Mechanica Fine Bar Screen Chamber AreaArea | 1437414 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1437414 | 977441.52 | 68% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 28748.28 |  | 0 |  | 0 | 100% | 28748.28 | 100% | 28748.28 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 28748.28 | 100% | 100% | 0% | 100% | 28748.28 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 186863.82 |  | 0 |  |  | 100% | 186863.82 | 100% | 186863.82 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 186863.82 | 100% | 100% | 0% | 100% | 186863.82 | 0% | 0 |  | 0
3 | PCC |  | 15% | 215612.1 |  | 0 |  |  | 100% | 215612.1 | 100% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 215612.1 | 100% | 100% | 0% | 100% | 215612.1 | 0% | 0 |  | 0
4 | RCC Foundation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 | 100% | 287482.8 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 287482.8 | 100% | 100% | 0% | 100% | 287482.8 | 0% | 0 |  | 0
5 | Column & Beam |  | 15% | 215612.1 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 | 100% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 215612.1 | 100% | 40% | 60% | 25.45% | 54873.2795 | 74.55% | 160738.8206 | 0% | 0
6 | RCC Slab |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 287482.8
7 | RCC Wall |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 53903.025 | 60% | 43122.42 | 25% | 17967.675 |  | 0 |  | 0 |  | 0 |  |  |  | 60% | 43122.42 | 60% | 60% | 0% | 60% | 43122.42 | 0% | 0 |  | 0
8 | Walkway/Platform |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 71870.7 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Hydro Testing /Finishing works |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 71870.7 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
ix | Grit Chamber Area | 3114397 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3114397 | 2024358.05 | 65% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 62287.94 |  | 0 |  | 0 | 100% | 62287.94 | 100% | 62287.94 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 62287.94 | 100% | 100% | 0% | 100% | 62287.94 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 404871.61 |  | 0 |  |  | 100% | 404871.61 | 100% | 404871.61 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 404871.61 | 100% | 100% | 0% | 100% | 404871.61 | 0% | 0 |  | 0
3 | PCC |  | 15% | 467159.55 |  | 0 |  |  | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 467159.55 | 100% | 100% | 0% | 100% | 467159.55 | 0% | 0 |  | 0
4 | RCC Foundation |  | 20% | 622879.4 |  | 0 |  |  | 100% | 622879.4 | 100% | 622879.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 622879.4 | 100% | 100% | 0% | 100% | 622879.4 | 0% | 0 |  | 0
5 | Column & Beam |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 | 50% | 233579.775 | 50% | 233579.775 | 50% | 233579.775 | 50% | 233579.775 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 467159.55 | 100% | 40% | 60% | 25.42% | 118751.9576 | 74.58% | 348407.5924 | 0% | 0
6 | RCC Slab |  | 20% | 622879.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 622879.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 622879.4
7 | RCC Wall |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 116789.8875 | 0% | 0 | 25% | 38929.9625 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | Walkway/Platform |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Hydro Testing /Finishing works |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
x | Parshall Flume Channel Area | 3114397 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 3114397 | 1868638.2 | 60% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 62287.94 |  | 0 |  | 0 | 100% | 62287.94 | 100% | 62287.94 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 62287.94 | 100% | 100% | 0% | 100% | 62287.94 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 404871.61 |  | 0 |  |  | 100% | 404871.61 | 100% | 404871.61 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 404871.61 | 100% | 100% | 0% | 60% | 242922.966 | 40% | 161948.644 |  | 0
3 | PCC |  | 15% | 467159.55 |  | 0 |  |  | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 467159.55 | 100% | 100% | 0% | 0% | 0 | 100% | 467159.55 |  | 0
4 | RCC Foundation |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 | 50% | 233579.775 | 50% | 233579.775 | 50% | 233579.775 | 50% | 233579.775 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 467159.55 | 100% | 100% | 0% | 0% | 0 | 100% | 467159.55 |  | 0
5 | Column & Beam |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 467159.55 | 100% | 40% | 60% | 0% | 0 | 100% | 467159.55 | 0% | 0
6 | RCC Slab |  | 20% | 622879.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 622879.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 622879.4
7 | RCC Wall |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | Walkway/Platform |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Piping & fitting Work |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Hydro Testing /Finishing works |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 155719.85 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xi | Sludge Dewatering System Area (Centrifuge Pump House, Sludge sump & Poly dosing tank) | 4312242 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4312242 | 301856.94 | 7% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 86244.84 |  | 0 |  | 0 | 100% | 86244.84 | 100% | 86244.84 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 86244.84 | 100% | 100% | 0% | 100% | 86244.84 | 0% | 0 |  | 0
2 | Excavation |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 | 100% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 215612.1 | 100% | 100% | 0% | 0% | 0 | 100% | 215612.1 | 0% | 0
3 | PCC |  | 8% | 344979.36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 344979.36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 344979.36
4 | RCC Foundation |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 323418.15 |  | 0 | 25% | 107806.05 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Column & Beam Upto First Floor |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
6 | First Floor Slab |  | 15% | 646836.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 646836.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
7 | Column & Beam First Floor to Roof Slab |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | Roof Slab |  | 15% | 646836.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 646836.3 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Brickwork |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Plaster |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
11 | Piping & fiittings Work |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
12 | Hydro Testing /Finishing works |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xii | Sludge Thickener Area | 3353966 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3353966 | 3186267.7 | 95% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 67079.32 | 100% | 67079.32 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 67079.32 | 100% | 100% | 0% | 100% | 67079.32 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 436015.58 | 100% | 436015.58 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 436015.58 | 100% | 100% | 0% | 100% | 436015.58 | 0% | 0 |  | 0
3 | PCC |  | 15% | 503094.9 | 100% | 503094.9 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 503094.9 | 100% | 100% | 0% | 100% | 503094.9 | 0% | 0 |  | 0
4 | RCC Foundation Wall/base slab |  | 25% | 838491.5 |  | 0 | 100% | 838491.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 838491.5 | 100% | 100% | 0% | 100% | 838491.5 | 0% | 0 |  | 0
5 | Wall 50% of total lift work |  | 20% | 670793.2 |  | 0 |  |  | 100% | 670793.2 | 100% | 670793.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 670793.2 | 100% | 100% | 0% | 100% | 670793.2 | 0% | 0 |  | 0
6 | Walls (balance 50% of Total Lift work) |  | 20% | 670793.2 |  | 0 |  |  | 50% | 335396.6 | 50% | 335396.6 | 50% | 335396.6 | 50% | 335396.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 670793.2 | 100% | 98% | 2% | 88% | 590298.016 | 12% | 80495.184 | 0% | 0
7 | Hydro Testing /Finishing works |  | 5% | 167698.3 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 167698.3
xiii | Supernatant Sump Area | 2395690 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2395690 | 2275905.5 | 95% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 47913.8 | 100% | 100% | 0% | 100% | 47913.8 | 0% | 0 |  | 0
2 | Excavation |  | 13% | 311439.7 |  | 0 | 100% | 311439.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 311439.7 | 100% | 100% | 0% | 100% | 311439.7 | 0% | 0 |  | 0
3 | PCC |  | 15% | 359353.5 |  | 0 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 359353.5 | 100% | 100% | 0% | 100% | 359353.5 | 0% | 0 |  | 0
4 | RCC Foundation wall/base slab |  | 25% | 598922.5 |  | 0 | 100% | 598922.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 598922.5 | 100% | 100% | 0% | 100% | 598922.5 | 0% | 0 |  | 0
5 | Wall 50% of total lift work |  | 20% | 479138 |  | 0 | 100% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 479138 | 100% | 100% | 0% | 100% | 479138 | 0% | 0 |  | 0
6 | Walls (balance 50% of Total Lift work) |  | 20% | 479138 |  | 0 |  | 0 | 100% | 479138 | 100% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 479138 | 100% | 100% | 0% | 100% | 479138 | 0% | 0 |  | 0
7 | Hydro Testing /Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 59892.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 59892.25 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 119784.5
xiv | Sludge Storage Platform Area | 1916552 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1916552 | 95827.6 | 5% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 5% | 95827.6 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 95827.6 | 100% | 95827.6 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 95827.6 | 100% | 100% | 0% | 100% | 95827.6 | 0% | 0 |  | 0
2 | Excavation |  | 20% | 383310.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 191655.2 |  | 0 | 50% | 191655.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
3 | PCC |  | 30% | 574965.6 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 574965.6 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | Foundation Work |  | 40% | 766620.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 766620.8 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Finishing work |  | 5% | 95827.6 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 95827.6 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xv | Transformer Yard Area | 1437414 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1437414 | 71870.7 | 5% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 71870.7 | 100% | 71870.7 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 71870.7 | 100% | 100% | 0% | 100% | 71870.7 | 0% | 0 |  | 0
2 | Excavation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
3 | PCC |  | 30% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | Foundation Work |  | 45% | 646836.3 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 323418.15 |  | 0 | 50% | 323418.15 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xvi | DG Shed Area | 1437414 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1437414 | 71870.7 | 5% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 71870.7 | 100% | 71870.7 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 71870.7 | 100% | 100% | 0% | 100% | 71870.7 | 0% | 0 |  | 0
2 | Excavation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
3 | PCC |  | 30% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | Foundation Work |  | 45% | 646836.3 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 646836.3 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xvii | EXTERNAL DEVELOPMENT | 17997165 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21351131 | 6820925.535 | 31.95% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| Boundary Wall with Gate |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
2 | Excavation |  | 15% | 2699574.75 | 50% | 1349787.375 | 5% | 134978.7375 | 35% | 944851.1625 | 6% | 161974.485 | 10% | 269957.475 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 61% | 1646740.5975 | 61% | 61% | 0% | 61% | 1646740.5975 | 0% | 0 |  | 0
3 | PCC |  | 20% | 3599433 | 50% | 1799716.5 |  | 0 | 28% | 1007841.24 | 2% | 71988.66 | 7% | 251960.31 |  | 0 | 10% | 359943.3 |  | 0 | 5% | 179971.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 52% | 1871705.16 | 52% | 52% | 0% | 52% | 1871705.16 | 0% | 0 |  | 0
4 | RCC Column footing |  | 20% | 3599433 | 50% | 1799716.5 |  | 0 | 20% | 719886.6 | 2% | 71988.66 | 4% | 151041.32 |  | 0 | 14% | 496856.62 |  | 0 | 12% | 431931.96 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 52% | 1871705.16 | 52% | 52% | 0% | 52% | 1871705.16 | 0% | 0 |  | 0
5 | RCC Column & Beam |  | 15% | 2699574.75 | 26% | 701889.435 | 10% | 269957.475 | 19% | 512919.2025 | 7% | 188970.2325 | 4% | 107982.99 |  | 0 | 15% | 404936.2125 |  | 0 | 26% | 701889.435 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 43% | 1160817.1425 | 43% | 43% | 0% | 43% | 1160817.1425 | 0% | 0 |  | 0
6 | Brickwork |  | 15% | 2699574.75 |  | 0 | 10% | 269957.475 |  | 0 |  | 0 | 4% | 107982.99 |  | 0 | 5% | 134978.7375 |  | 0 | 65% | 1754723.5875 |  | 0 | 16% | 431931.96 |  | 0 |  | 0 |  | 0 |  |  |  | 10% | 269957.475 | 10% | 10% | 0% | 10% | 269957.475 | 0% | 0 |  | 0
7 | Plaster |  | 10% | 1799716.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5% | 89985.825 |  | 0 | 15% | 269957.475 |  | 0 | 80% | 1439773.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
8 | Finishing Work |  | 5% | 899858.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 21.5% | 193469.5237 |  | 0 | 78.5% | 706388.7263 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| Earthfilling, Internal Roads ,Landscaping |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Earthfilling, Internal Roads ,Landscaping | 3353966 | 100% | 3353966 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 29% | 972650.14 |  | 0 | 71% | 2381315.86 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
B | MPS-20 MLD |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| Civil Work |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
i | Construction of Raw Sewage Sump | 8582759 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8582759 | 6608724.43 | 77% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 171655.18 | 100% | 171655.18 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 171655.18 | 100% | 100% | 0% | 100% | 171655.18 | 0% | 0 |  | 0
2 | Excavation |  | 10% | 858275.9 | 40% | 343310.36 | 60% | 514965.54 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 858275.9 | 100% | 100% | 0% | 100% | 858275.9 | 0% | 0 |  | 0
3 | PCC |  | 15% | 1287413.85 |  | 0 | 100% | 1287413.85 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1287413.85 | 100% | 100% | 0% | 100% | 1287413.85 | 0% | 0 |  | 0
4 | RCC Foundation/Raft |  | 20% | 1716551.8 |  | 0 | 100% | 1716551.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1716551.8 | 100% | 100% | 0% | 100% | 1716551.8 | 0% | 0 |  | 0
5 | Wall 50% of total lift work |  | 15% | 1287413.85 |  | 0 |  | 0 | 50% | 643706.925 | 50% | 643706.925 | 50% | 643706.925 | 50% | 643706.925 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1287413.85 | 100% | 100% | 0% | 100% | 1287413.85 | 0% | 0 |  | 0
6 | Walls (balance 50% of Total Lift work) |  | 15% | 1287413.85 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1287413.85 | 100% | 1287413.85 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1287413.85 | 100% | 95% | 5% | 80% | 1029931.08 | 20% | 257482.77 | 0% | 0
7 | Column & Beam |  | 10% | 858275.9 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 858275.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 858275.9
8 | Ground Floor Slab |  | 8% | 686620.72 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 686620.72 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Hydro Testing /Finishing works |  | 5% | 429137.95 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 429137.95 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
ii | Construction of Raw Sewage Pump House | 1000000 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1000000 | 0 | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Column & Beam |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
2 | Roof Slab |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
3 | Brickwork |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | Plaster |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iii | Construction of Inlet Chamber & Screen Channel | 2874828 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2874828 | 2069876.16 | 72% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  | 2% | 57496.56 | 100% | 57496.56 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 57496.56 | 100% | 100% | 0% | 100% | 57496.56 | 0% | 0 |  | 0
2 | Excavation |  | 10% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 | 100% | 287482.8 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 287482.8 | 100% | 100% | 0% | 100% | 287482.8 | 0% | 0 |  | 0
3 | PCC |  | 15% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 431224.2 | 100% | 100% | 0% | 100% | 431224.2 | 0% | 0 |  | 0
4 | RCC Foundation/Raft |  | 15% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 215612.1 | 50% | 215612.1 | 50% | 215612.1 | 50% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 431224.2 | 100% | 100% | 0% | 100% | 431224.2 | 0% | 0 |  | 0
5 | Wall 50% of total lift work |  | 15% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 431224.2 | 100% | 100% | 0% | 100% | 431224.2 | 0% | 0 |  | 0
6 | Walls (balance 50% of Total Lift work) |  | 15% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 431224.2 | 100% | 80% | 20% | 0% | 0 | 100% | 431224.2 | 0% | 0
7 | Column & Beam |  | 10% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 287482.8
8 | Ground Floor Slab |  | 8% | 229986.24 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 229986.24 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
9 | Walkway/Platform |  | 5% | 143741.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 143741.4 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
10 | Hydro Testing /Finishing works |  | 5% | 143741.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 143741.4 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
C | SEWER SYSTEM AREA | 9066560 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9066560 | 7865240.7996 | 86.75% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
2 | Supply of pipes |  | 80% | 7253248 | 87.92% | 6377489.6416 | 12.1% | 875758.358 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 7253247.9996 | 100% | 100% | 0% | 100% | 7254698.6496 | 0% | 0 |  | 0
3 | Excavation and Laying of pipes including bed preperation & backfilling |  | 7.5% | 679992 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 509994 | 75% | 509994 | 25% | 169998 | 15% | 101998.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 90% | 611992.8 | 90% | 90% | 0% | 0% | 0 | 90% | 611992.8 |  | 0
4 | Manholes |  | 7.5% | 679992 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 509994 |  | 0 | 25% | 169998 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Flow Testing |  | 5% | 453328 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 226508.72 |  | 0 | 50% | 226819.28 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
D | I & D Work | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3037751 | 0 | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
(i) | Approach Channel | 674400 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Excavation |  | 10.1% | 68100 |  | 0 |  |  |  | 0 |  | 0 | 100% | 68100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 68100
2 | PCC |  | 25.21% | 170000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 170000
3 | RCC Foundation/Raft |  | 30.4% | 205000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 205000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | wall |  | 25.21% | 170000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 22% | 37237 |  | 0 | 59% | 100463 |  | 0 | 19% | 32300 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Hydro Testing /Finishing works |  | 9.09% | 61300 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 61300 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
(ii) | Inlet Chamber | 848200 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Excavation |  | 10.13% | 85900 |  | 0 |  |  |  | 0 |  | 0 | 100% | 85900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 85900
2 | PCC |  | 25.35% | 215000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 215000
3 | RCC Foundation/Raft |  | 30.06% | 255000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 255000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | wall |  | 25.35% | 215000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Hydro Testing /Finishing works |  | 9.113% | 77300 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 77300 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
(iii) | Screen Channel | 680845 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Excavation |  | 10.09% | 68700 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 68700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 68700
2 | PCC |  | 25.25% | 171900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 171900
3 | RCC Foundation/Raft |  | 30.31% | 206370 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 206370 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | wall |  | 25.26% | 171975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Hydro Testing /Finishing works |  | 9.092% | 61900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 61900 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
(iv) | Grit Chamber | 698620 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Excavation |  | 10.12% | 70670 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 70670 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 70670
2 | PCC |  | 25.29% | 176675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 176675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 176675
3 | RCC Foundation/Raft |  | 30.35% | 212000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 212000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | wall |  | 25.15% | 175675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 175675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Hydro Testing /Finishing works |  | 9.104% | 63600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 63600 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
(v) | Collection Chamber | 135686 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Excavation |  | 10.1% | 13710 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 13710 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 13710
2 | PCC |  | 25.26% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 34273
3 | RCC Foundation/Raft |  | 30.31% | 41130 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 41130 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
4 | wall |  | 25.26% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
5 | Hydro Testing /Finishing works |  | 9.065% | 12300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 12300 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
E | EFFLUENT DISPOSAL SYSTEM |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2780620 | 0 | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
[6 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
1 | Site Clearance |  |  | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
2 | Construction of Effluent Channel |  |  | 2530620 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 31.2% | 789287.44 |  | 0 | 68.8% | 1741332.56 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
F | E&M WORK |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 87488000 | 47775636.47 | 54.61% | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
i) | GRIT CHAMBER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.On supply - Grit Scraper Mechanism |  | 0% | 2285000 |  | 0 |  | 0 | 100% | 1828000 | 100% | 1828000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1828000 | 100% | 100% | 0% | 100% | 1828000 | 0% | 0 |  | 0
| B.On Installation - Grit Scraper Mechanism |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 457000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
ii) | SLUDGE THICKENER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Sludge Thickener |  | 0% | 880000 |  | 0 |  | 0 | 100% | 704000 | 100% | 704000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 704000 | 100% | 100% | 0% | 100% | 704000 | 0% | 0 |  | 0
| B.Installation - Sludge Thickener |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 176000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iii) | TRANSFORMER YARD AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Transformer |  | 80% | 3025000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2420000 | 100% | 2420000 |  | 0 |  | 0 |  |  |  | 100% | 2420000 | 100% | 100% | 0% | 0% | 0 | 100% | 2420000 |  | 0
| B.Installation - Transformer |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 605000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
iv) | DG SHED AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - DG |  | 80% | 3875000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3100000 | 100% | 3100000 |  | 0 |  | 0 |  |  |  | 100% | 3100000 | 100% | 100% | 0% | 100% | 3100000 | 0% | 0 |  | 0
| B.Installation - DG |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 775000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
v) | MEP |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Screen |  | 0% | 4180000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3344000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 3344000
| B.Installation - Screen |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 836000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| C.Supply - Hoist |  | 0% | 585000 |  | 0 |  | 0 | 100% | 468000 | 100% | 468000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 468000 | 100% | 100% | 0% | 100% | 468000 | 0% | 0 |  | 0
| D.Installation - Hoist |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 117000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| E.Supply - Pumps & Motors(MEP) |  | 0% | 8680000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 3472000 | 50% | 3472000 | 50% | 3472000 | 50% | 3472000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 6944000 | 100% | 100% | 0% | 100% | 6944000 | 0% | 0 |  | 0
| F.Installation - Pumps & Motors(MEP) |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1736000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| G.Supply - Gates |  | 0% | 1430000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1144000 | 100% | 1144000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1144000 | 100% | 0% | 100% | 0% | 0 | 100% | 1430000 | 0% | 0
| H.Supply - Valves(MPS) |  | 80% | 1430000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 1144000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 1144000
| I.Installation - Gate & Valves(MPS) |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 286000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| J.Installation - Gate & Valves(MPS) |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 286000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| K.Supply Instruments(like flow meter, Guages, level, Transmiter) |  | 0% | 1760000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1408000 | 70% | 985600 |  |  |  | 70% | 985600 | 70% | 70% | 0% | 0% | 0 | 70% | 1232000 |  | 0
| L.Installation - Instruments(like flow meter, Guages, level, Transmiter) |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 352000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
vi) | INLET CHAMBER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Gates |  | 0% | 1155000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 462000 | 50% | 462000 | 50% | 462000 | 50% | 462000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 924000 | 100% | 0% | 100% | 0% | 0 | 100% | 1155000 | 0% | 0
| B.Supply - Valves(STP) |  | 80% | 1155000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 924000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 924000
| C.Installation - Gates |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 231000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| D.Installation - Valves(STP) |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 231000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
vii) | FINE SCREEN AREA |  |  |  |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.On supply -Fine Screen |  | 80% | 1760000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 1408000 | 100% | 1408000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 1408000 | 100% | 0% | 100% | 0% | 0 | 100% | 1760000 | 0% | 0
| B.On Installation -Fine Screen |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 352000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
viii) | SBR BASIN AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A..On supply - Decanter Equipment |  | 0% | 9315000 |  | 0 | 100% | 7452000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 7452000 | 100% | 100% | 0% | 100% | 7452000 | 0% | 0 |  | 0
| B..Installation - Decanter Equipment |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1863000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| C.On supply - Diffuser |  | 0% | 10615000 |  | 0 | 100% | 8492000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 8492000 | 100% | 100% | 0% | 100% | 8492000 | 0% | 0 |  | 0
| D.On Installation - Diffuser |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2123000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| E.On supply - RAS Pump, SAS Pump |  | 0% | 3470000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2776000 | 100% | 2776000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 2776000 | 100% | 100% | 0% | 100% | 2776000 | 0% | 0 |  | 0
| F.On Installation - RAS Pump, SAS Pump |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 694000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| G.On supply - Chain Pulley Block |  | 0% | 385000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 308000 | 100% | 308000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 308000 | 100% | 100% | 0% | 100% | 308000 | 0% | 0 |  | 0
| H.On Installation - Chain Pulley Block |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 77000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
ix) | AIR BLOWER ROOM |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Blower |  | 80% | 3800000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3040000 | 100% | 3040000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 3040000 | 100% | 100% | 0% | 90% | 2736000 | 10% | 380000 | 0% | 0
| B. Installation - Blower |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 760000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| C.Supply - Hoist Work |  | 80% | 575000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 460000 | 100% | 460000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 460000 | 100% | 100% | 0% | 100% | 460000 | 0% | 0 |  | 0
| D.Installation - Hoist Work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 115000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
x) | CHLORINATION ROOM AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - Chlorination system(Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work |  | 0% | 1595000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1276000 | 90% | 1148400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 90% | 1148400 | 90% | 90% | 0% | 90% | 1148400 | 0% | 0 | 10% | 127600
| B. Installation - Chlorination system(Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| C.Supply - Chlorine Nutrilisation Tank |  | 0% | 275000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 220000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| D.Installation - Chlorine Nutrilisation tank |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 55000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| E.Supply - Hoist Work |  | 80% | 385000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 308000 | 100% | 308000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 308000 | 100% | 100% | 0% | 100% | 308000 | 0% | 0 |  | 0
| F.Installation - Hoist Work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 77000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xi) | CENTRIFUGE HOUSE & FEED PUMP AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.On supply -Centrifuge |  | 0% | 2832500 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2266000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 100% | 2266000
| B.On supply -Centrifuge Feed Pump |  | 65.99% | 2832500 |  | 0 |  |  | 82.5% | 1869086.47 | 82.5% | 1869086.47 | 17.5% | 396913.53 | 17.5% | 396550 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 2265636.47 | 100% | 0% | 100% | 0% | 0 | 100% | 2832500 |  | 0
| C.On Installation -Centrifuge |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 566500 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| D.On Installation -Centrifuge Feed Pump |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 566500 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xii) | ADMN BUILDING AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - LT/HT Panel |  | 80% | 4690000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3752000 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| B.Installation - LT/HT Panel |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 938000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| C.Supply - PLC/SCADA Automation |  | 80% | 4500000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| D.Installation - PLC/SCADA Automation |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 900000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xiii) | Cable Tray & Earthing work |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply - cable Tray/Earthing material |  | 80% | 1000000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 800000 | 100% | 800000 |  | 0 |  | 0 |  |  |  | 100% | 800000 | 100% | 100% | 0% | 0% | 0 | 100% | 800000 |  | 0
| B.Installation - Cable Tray/Earthing material |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 200000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xiv) | External Electrification (lighting & Pole) |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
| A.Supply |  | 80% | 1000000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 800000 | 100% | 800000 |  | 0 |  | 0 |  |  |  | 100% | 800000 | 100% | 50% | 50% | 0% | 0 | 100% | 1000000 |  | 0
| B.Installation |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 200000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xv) | TESTING OF E&M EQUIPMENT FOR STP & MPS |  | 100% | 7648000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 7648000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
xvi) | EQUIPMENT TOOLS & MISC. |  | 100% | 370000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 370000 |  | 0 |  |  |  | 0% | 0 | 0% | 0% | 0% | 0% | 0 | 0% | 0 |  | 0
III | TRIAL RUN & COMMISSIONING |  |  |  |  | 0 | [7 empty] | 0 |  | 0 | [26 empty] | 0% | 0 |  | 0
1 | Trial Run & Commissioning |  |  |  |  | 0 | [9 empty] | 0 | [26 empty] | 0% |  |  | 0
|  |  |  | 212950200 |  | 26618774.9056 |  | 26618774.6155 |  | 26618774.996 |  | 23927475.8285 |  | 26618774.57 |  | 17890323.805 |  | 26618775.485 |  | 16013722.375 |  | 26618775.2252 |  | 4523915.62 |  | 26618774.9961 |  | 7120000 |  | 26618775.2063 |  | 985600 | 212950200 | 123698587.1496 | 58.09% | 58.09% | 123698587.1496 |  |  |  | 50% | 106477306.408 | 8.588% | 18288365.1952 | 6.78% | 14437949.685
[42 empty] | Need | 12.5% | 26618775
1) Above listed are itemwise major activities, but all required works/items must be included & completed as per approved drawings & design, as project is turnkey basis;
2) variation clause applicable
3) Items/Payments shall be as per relevant clauses of Concessionaire Agreement
[33 empty] | 425900400 | 247397174.2992 | 58.09%
| Total Cost | 170806127 | 100%
| Design & Drawing Approval | 0 | 0%
| Civil work Cost | 122635007 | 1603%
| Mechanical Work Cost | 26308120 | 344%
| Electrical Work Cost | 5165000 | 67.53%
| Instrumentation Work Cost | 8680000 | 113.5%
| Testing of E&M Equipments | 7648000 | 100%
| MISC. | 370000 | 4.838%
| 1st milestone |  |  |  | = | 26618774.9056 | [35 empty] | Now | 8.588% | 18288365.1952
| 2nd milestone |  |  |  | = | 26618774.6155 | [35 empty] | To complete 5th Milestone we need to achieve | Civil | 6632349.685
| 3rd Milestone |  |  |  | = | 23927475.8285 | [36 empty] | MEI | 7805600
| 4th Milestone |  |  |  | = | 17890323.805 | [36 empty] | 6.78% | 14437949.685
| 5th Milestone |  |  |  | = | 16013722.375
| 6th Milestone |  |  |  | = | 4523915.62
| 7th Milestone |  |  |  | = | 7120000
| 8th Milestone |  |  |  | = | 0
| Total Amount |  |  |  | = | 122712987.1496
| Total % as on 31.12.2022 |  |  |  | = | 57.63%