## Unnao
PROGRESS REPORT FOR 15 MLD UNNAO SITE | [30 empty] | Claculation for 7th Milestone
Sr. No. | Description of Items | BOQ Amount | Milestone-1 (From 11th Oct.'19 to 25th Sept'20) |  | Milestone-2 (From 26th Sep'20 to 06th Dec.'20) |  | Milestone-3 (From 07th Dec.'20 to 25th Mar'21) |  | Milestone-4 (From 26th Mar'21 to 07th Aug'21) |  | Milestone-5 (From 08th Aug'21 to 15th Nov'21 ) |  | Milestone-6 (From 16th Nov'21 to 25th Mar'22 ) |  | Achived for 6th Milestone |  | Milestone-7 (From 26th Mar'22 to 25th Apr'22 ) |  | Achived for 7th Milestone |  | Milestone-8 (From 26th Apr'22 to 15th May'22 ) |  | Achived for 8th Milestone |  | Total Scope | Achieved | Percentage | Upto Oct'22 | Upto Sept'22 | For Sept'22 | Cumulative |  | Upto 6th Milestone |  | For 7th Milestone
|  |  | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount | % | [5 empty] | % | Amount | % | Amount
I | Design & Drawing & STP & Sewer Laying works | [23 empty] | 38269000 | 38269000 | 100%
1 | On approval of BEP | 19134500 | 100% | 19134500 | [11 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 19134500 | 100% | 19134500 | 0% | 0 | 0
2 | On approval of design & drawings for Civil & Sewerage works | 19134500 | 25% | 4783625 | 75% | 14350875 | [9 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 19134500 | 100% | 19134500 | 0% | 0 | 0
|  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
II | CONSTRUCTION | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
A | UNNAO STP (15 MLD) | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
i) | SBR Basin Area | 0 | [22 empty] | 41576698.88 | 39736698.88 | 95.57% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 500000 | 100% | 500000 | [11 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 500000 | 100% | 500000 | 0% | 0 | 0
2 | Excavation wall footing | 2246137.6 | 100% | 2246137.6 | [11 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2246137.6 | 100% | 2246137.6 | 0% | 0 | 0
3 | PCC wall footing | 2746137.6 | 100% | 2746137.6 | [11 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 100% | 2746137.6 | 0% | 0 | 0
4 | RCC Foundation/Raft of wall | 5492275.2 |  | 0 | 100% | 5492275.2 | [9 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 5492275.2 | 100% | 5492275.2 | 0% | 0 | 0
5 | Wall 50% of total upto base slab | 5492275.2 |  | 0 | 19.94% | 1095110.2444 | 80.06% | 4397164.9556 | [7 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 5492275.2 | 100% | 5492275.2 | 0% | 0 | 0
6 | Walls (balance 50% of upto base slab) | 5492275.2 |  | 0 |  | 0 | 100% | 5492275.2 |  | 0 | [5 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 5492275.2 | 100% | 5492275.2 | 0% | 0 | 0
7 | PCC Base Slab | 2746137.6 |  | 0 |  | 0 | 100% | 2746137.6 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 100% | 2746137.6 | 0% | 0 | 0
8 | RCC Foundation base slab | 2746137.6 |  | 0 |  | 0 | 25% | 686534.4 | 75% | 2059603.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 100% | 2746137.6 | 0% | 0 | 0
9 | Wall 50% of total lift work | 2746137.6 |  | 0 |  | 0 |  | 0 | 10% | 274613.76 | 90% | 2471523.84 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 100% | 2746137.6 | 0% | 0 | 0
40 | Walls (balance 50% of Total Lift work) | 2746137.6 |  | 0 |  | 0 |  | 0 |  | 0 | 75% | 2059603.2 | 25% | 686534.4 | 25% | 686534.4 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 100% | 2746137.6 | 0% | 0 | 0
11 | Walkway/Platform | 2746137.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 1922296.32 | 70% | 1922296.32 | 30% | 823841.28 | 30% | 823841.28 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2746137.6 | 90% | 2471523.84 | 10% | 274613.76 | 0
12 | Piping & fitting works | 2196910.08 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1098455.04 | 50% | 1098455.04 | 50% | 1098455.04 | 50% | 1098455.04 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2196910.08 | 50% | 1098455.04 | 50% | 1098455.04 | 0
13 | Testing /Finishing works | 3680000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3680000 | 50% | 1840000 |  | 0 |  | 0 |  |  |  | 50% | 85% | -35% | 50% | 1840000 | 25% | 920000 | 25% | 920000 | -1288000
ii | Sludge Thickener Area | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3089404.6 | 3074004.6 | 99.5% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 364900.8 | 100% | 364900.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 364900.8 | 100% | 364900.8 | 0% | 0 | 0
3 | PCC | 514900.8 | 49.37% | 254185.9289 | 50.63% | 260714.8711 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 514900.8 | 100% | 514900.8 | 0% | 0 | 0
4 | RCC Foundation Wall/base slab | 686534.4 |  | 0 | 50% | 343267.2 | 50% | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4 | 100% | 686534.4 | 0% | 0 | 0
5 | Wall 50% of total lift work | 686534.4 |  | 0 | 100% | 686534.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4 | 100% | 686534.4 | 0% | 0 | 0
6 | Walls (balance 50% of Total Lift work) | 378534.2 |  | 0 |  | 0 | 71.22% | 269576.9159 | 28.78% | 108957.2841 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 378534.2 | 100% | 378534.2 | 0% | 0 | 0
7 | Testing /Finishing works | 308000 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 77000 | 60% | 184800 | 60% | 184800 | 15% | 46200 | 10% | 30800 |  | 0 |  | 0 |  |  |  | 95% | 90% | 5% | 95% | 292600 | 85% | 261800 | 10% | 30800 | 15400
iii | Supernatant Sump Area | 0 |  | 0.6339% |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 858168 | 841008 | 98% | 0% | 0% | 0% | 0% | 0.0063391 | 0% | 0.0063391 | 0% | 0 | 0
1 | Site Clearance | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 100000 | 100% | 100000 | 0% | 0 | 0
2 | Excavation | 114422.4 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
3 | PCC | 114422.4 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
4 | RCC Foundation wall/base slab | 128844.8 | 100% | 128844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 128844.8 | 100% | 128844.8 | 0% | 0 | 0
5 | Wall 50% of total lift work | 143044.8 |  | 0 | 100% | 143044.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 143044.8 | 100% | 143044.8 | 0% | 0 | 0
6 | Walls (balance 50% of Total Lift work) | 171633.6 |  | 0 |  | 0 | 100% | 171633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 171633.6 | 100% | 171633.6 | 0% | 0 | 0
7 | Testing /Finishing works | 85800 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 21450 | 50% | 42900 | 50% | 42900 | 25% | 21450 | 5% | 4290 |  | 0 |  | 0 |  |  |  | 80% | 90% | -10% | 80% | 68640 | 75% | 64350 | 5% | 4290 | -8580
iv | Chlorination Tank Area | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4576896 | 4348396 | 95.01% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 422112 | 100% | 422112 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 422112 | 100% | 422112 | 0% | 0 | 0
3 | PCC | 572112 | 100% | 572112 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 572112 | 100% | 572112 | 0% | 0 | 0
4 | RCC Foundation/Raft | 915000 | 100% | 915000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 915000 | 100% | 915000 | 0% | 0 | 0
5 | Wall 50% of total lift work | 858168 |  | 0 | 100% | 858168 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 858168 | 100% | 858168 | 0% | 0 | 0
6 | Walls (balance 50% of Total Lift work) | 858168 |  | 0 |  | 0 | 100% | 858168 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 858168 | 100% | 858168 | 0% | 0 | 0
7 | Baffle Walls work | 344336 |  | 0 |  | 0 | 100% | 344336 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 344336 | 100% | 344336 | 0% | 0 | 0
8 | Testing /Finishing works | 457000 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 457000 | 50% | 228500 |  | 0 |  | 0 |  |  |  | 50% | 95% | -45% | 50% | 228500 | 50% | 228500 | 0% | 0 | -205650
v | Air Blower Room Area | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5835542.4 | 5573192.4 | 95.5% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 250000 | 100% | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 250000 | 100% | 250000 | 0% | 0 | 0
2 | Excavation | 343267.2 | 100% | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 100% | 343267.2 | 0% | 0 | 0
3 | PCC | 343267.2 | 100% | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 100% | 343267.2 | 0% | 0 | 0
4 | RCC Foundation/column footing | 686534.4 |  | 0 | 100% | 686534.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4 | 100% | 686534.4 | 0% | 0 | 0
5 | Column & Beam | 629801.6 |  | 0 | 100% | 629801.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 629801.6 | 100% | 629801.6 | 0% | 0 | 0
6 | RCC Roof Slab | 829801.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 829801.6 | 100% | 829801.6 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 829801.6 | 100% | 829801.6 | 0% | 0 | 0
7 | Cable Trench Work | 686534.4 |  | 0 |  | 0 |  | 0 | 100% | 686534.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4 | 100% | 686534.4 | 0% | 0 | 0
8 | RCC Ground floor Grade Slab | 686534.4 |  | 0 |  | 0 |  | 0 | 25% | 171633.6 | 75% | 514900.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4 | 100% | 686534.4 | 0% | 0 | 0
9 | Brick work | 625168 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 437617.6 | 70% | 437617.6 | 30% | 187550.4 | 30% | 187550.4 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 625168 | 90% | 562651.2 | 10% | 62516.8 | 0
10 | Plaster | 171633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171633.6 | 100% | 171633.6 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 171633.6 | 80% | 137306.88 | 20% | 34326.72 | 0
11 | Testing/Finishing work | 583000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 583000 | 55% | 320650 |  | 0 |  | 0 |  |  |  | 55% | 90% | -35% | 55% | 320650 | 0% | 0 | 55% | 320650 | -204050
vi | Staff Quarter Area (G+1) | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 920000 | 888175 | 96.54% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 50000 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 50000 | 100% | 50000 | 0% | 0 | 0
2 | Excavation | 71000 | 100% | 71000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 71000 | 100% | 71000 | 0% | 0 | 0
3 | PCC | 71000 | 100% | 71000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 71000 | 100% | 71000 | 0% | 0 | 0
4 | RCC Foundation/column footing | 92000 | 100% | 92000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 92000 | 100% | 92000 | 0% | 0 | 0
5 | Column & Beam | 92000 |  | 0 | 100% | 92000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 92000 | 100% | 92000 | 0% | 0 | 0
6 | RCC Ground floor Slab | 92000 |  | 0 | 100% | 92000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 92000 | 100% | 92000 | 0% | 0 | 0
7 | RCC 1st floor Slab | 92000 |  | 0 |  | 0 | 100% | 92000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 92000 | 100% | 92000 | 0% | 0 | 0
8 | RCC Roof Slab | 92000 |  | 0 |  | 0 | 100% | 92000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 92000 | 100% | 92000 | 0% | 0 | 0
9 | Brick work | 67000 |  | 0 |  | 0 |  | 0 | 60% | 40200 | 40% | 26800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 67000 | 100% | 67000 | 0% | 0 | 0
10 | Plaster | 67000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 33500 | 50% | 33500 | 50% | 33500 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 67000 | 50% | 33500 | 50% | 33500 | 0
11 | Plumbing, fixtures , sanitary works, AC work | 67000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 33500 | 50% | 33500 | 50% | 33500 | 20% | 13400 |  | 0 |  | 0 |  |  |  | 70% | 0% | 70% | 70% | 46900 | 0% | 0 | 70% | 46900 | 46900
12 | Electrification work | 33500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 16750 | 50% | 16750 | 50% | 16750 | 25% | 8375 |  | 0 |  | 0 |  |  |  | 75% | 0% | 75% | 75% | 25125 | 0% | 0 | 75% | 25125 | 25125
13 | Finishing works | 33500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 23450 | 70% | 23450 | 30% | 10050 | 20% | 6700 |  | 0 |  | 0 |  |  |  | 90% | 80% | 10% | 90% | 30150 | 0% | 0 | 90% | 30150 | 3350
vii | Guard Room Area | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1144223.6 | 1087349.1 | 95.03% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 50000 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 50000 | 100% | 50000 | 0% | 0 | 0
2 | Excavation | 82211.2 | 100% | 82211.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 82211.2 | 100% | 82211.2 | 0% | 0 | 0
3 | PCC | 82211.2 | 100% | 82211.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 82211.2 | 100% | 82211.2 | 0% | 0 | 0
4 | RCC Foundation/column footing | 114422.4 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
5 | Column & Beam | 114422.4 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
6 | RCC Ground floor Slab | 114422.4 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
7 | RCC Roof Slab | 114422.4 |  | 0 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
8 | Brick work | 114422.4 |  | 0 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
9 | Plaster | 114422.4 |  | 0 | 100% | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 114422.4 | 100% | 114422.4 | 0% | 0 | 0
10 | Plumbing, fixtures | 114422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 57211.2 | 50% | 57211.2 | 50% | 57211.2 | 20% | 22884.48 |  | 0 |  | 0 |  |  |  | 70% | 0% | 70% | 70% | 80095.68 | 0% | 0 | 70% | 80095.68 | 80095.68
11 | Sanitary works, AC work | 64422.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 32211.2 | 50% | 32211.2 | 50% | 32211.2 | 30% | 19326.72 |  | 0 |  | 0 |  |  |  | 80% | 0% | 80% | 80% | 51537.92 | 0% | 0 | 80% | 51537.92 | 51537.92
12 | Electrification work | 32211 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 16105.5 | 50% | 16105.5 | 50% | 16105.5 | 30% | 9663.3 |  | 0 |  | 0 |  |  |  | 80% | 0% | 80% | 80% | 25768.8 | 0% | 0 | 80% | 25768.8 | 25768.8
13 | Finishing works | 32211 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 16105.5 | 50% | 16105.5 | 50% | 16105.5 | 40% | 12884.4 |  | 0 |  | 0 |  |  |  | 90% | 80% | 10% | 90% | 28989.9 | 0% | 0 | 90% | 28989.9 | 3221.1
viii | Chlorination Room Area | 0 | [22 empty] | 4119206.4 | 4016456.4034 | 97.51% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 457689.6 | 100% | 457689.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 457689.6 | 100% | 457689.6 | 0% | 0 | 0
3 | PCC | 457689.6 | 50% | 228844.8 | 50% | 228844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 457689.6 | 100% | 457689.6 | 0% | 0 | 0
4 | RCC Foundation/Column footing | 457689.6 |  | 0 | 100% | 457689.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 457689.6 | 100% | 457689.6 | 0% | 0 | 0
5 | Column & Beam | 457689.6 |  | 0 | 100% | 457689.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 457689.6 | 100% | 457689.6 | 0% | 0 | 0
6 | Ground floor Slab | 686534.4 |  | 0 | 35% | 240287.04 | 65% | 446247.3634 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 686534.4034 | 100% | 686534.4034 | 0% | 0 | 0
7 | Roof Slab | 486534.4 |  | 0 |  | 0 | 50% | 243267.2 | 50% | 243267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 486534.4 | 100% | 486534.4 | 0% | 0 | 0
8 | Brickwork | 296689.6 |  | 0 |  | 0 |  | 0 | 10% | 29668.96 | 90% | 267020.64 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 296689.6 | 100% | 296689.6 | 0% | 0 | 0
9 | Plaster | 257689.6 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 128844.8 | 50% | 128844.8 | 50% | 128844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 257689.6 | 90% | 231920.64 | 10% | 25768.96 | 0
10 | Testing/Finishing works | 411000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 205500 | 50% | 205500 | 50% | 205500 | 25% | 102750 |  | 0 |  | 0 |  |  |  | 75% | 75% | 0% | 75% | 308250 | 0% | 0 | 75% | 308250 | 0
ix | Admin Bldg Area (G+1) | 0 | [22 empty] | 1387148.4193 | 1300998.5573 | 93.79% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Excavation | 78958.7 |  | 0 |  | 0 | 100% | 78958.7 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 78958.7 | 100% | 78958.7 | 0% | 0 | 0
3 | PCC | 78958.7 |  | 0 |  | 0 | 50% | 39479.35 | 50% | 39479.35 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 78958.7 | 100% | 78958.7 | 0% | 0 | 0
4 | Column footings/Foundation | 118438.05 |  | 0 |  | 0 | 50% | 59219.025 |  | 0 | 50% | 59219.025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 118438.05 | 100% | 118438.05 | 0% | 0 | 0
5 | Column & Beam up to First Floor | 118438.05 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 118438.05 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 118438.05 | 100% | 118438.05 | 0% | 0 | 0
6 | 1st Floor Slab | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 135357.7714 | 100% | 135357.7714 | 0% | 0 | 0
7 | Column & Beam First Floor to Roof Slab | 118438.05 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 118438.05 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 118438.05 | 100% | 118438.05 | 0% | 0 | 0
8 | Roof Slab | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 135357.7714 | 100% | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 135357.7714 | 100% | 135357.7714 | 0% | 0 | 0
9 | Brickwork | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 135357.7714 | 100% | 135357.7714 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 135357.7714 | 90% | 121821.9943 | 10% | 13535.7771 | 0
10 | Plaster | 106594.245 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 80% | 85275.396 | 80% | 85275.396 | 20% | 21318.849 | 20% | 21318.849 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 106594.245 | 90% | 95934.8205 | 10% | 10659.4245 | 0
11 | Electrification, plumbing, fixtures , sanitary works, AC work | 222249.31 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 66674.793 | 30% | 66674.793 | 70% | 155574.517 | 50% | 111124.655 |  | 0 |  | 0 |  |  |  | 80% | 50% | 30% | 80% | 177799.448 | 0% | 0 | 80% | 177799.448 | 66674.793
12 | finishing works | 139000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 69500 | 50% | 69500 | 50% | 69500 | 20% | 27800 |  | 0 |  | 0 |  |  |  | 70% | 80% | -10% | 70% | 97300 | 0% | 0 | 70% | 97300 | -13900
x | Sludge Dewatering System Area (Centrifuge Pump House, Sludge sump & Poly dosing tank) | 0 | [22 empty] | 3510972 | 3335472 | 95% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 |  | 0 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 184788 |  | 0 |  | 0 | 100% | 184788 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184788 | 100% | 184788 | 0% | 0 | 0
3 | PCC | 184788 |  | 0 |  | 0 | 100% | 184788 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184788 | 100% | 184788 | 0% | 0 | 0
4 | RCC Foundation | 369576 |  | 0 |  | 0 | 100% | 369576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 369576 | 100% | 369576 | 0% | 0 | 0
5 | Column & Beam Upto First Floor | 369576 |  | 0 |  | 0 | 100% | 369576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 369576 | 100% | 369576 | 0% | 0 | 0
6 | First Floor Slab | 369576 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 369576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 369576 | 100% | 369576 | 0% | 0 | 0
7 | Column & Beam First Floor to Roof Slab | 338576 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 84644 | 75% | 253932 | 75% | 253932 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 338576 | 100% | 338576 | 0% | 0 | 0
8 | Roof Slab | 319576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319576 | 100% | 319576 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 319576 | 100% | 319576 | 0% | 0 | 0
9 | Brickwork | 369576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 258703.2 | 70% | 258703.2 | 30% | 110872.8 | 30% | 110872.8 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 369576 | 90% | 332618.4 | 10% | 36957.6 | 0
10 | Plaster | 319576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 127830.4 | 40% | 127830.4 | 60% | 191745.6 | 60% | 191745.6 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 319576 | 40% | 127830.4 | 60% | 191745.6 | 0
11 | Piping & fiittings Work | 184364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184364 | 100% | 184364 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184364 | 0% | 0 | 100% | 184364 | 0
12 | Testing/Finishing works | 351000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 351000 | 50% | 175500 |  | 0 |  | 0 |  |  |  | 50% | 75% | -25% | 50% | 175500 | 0% | 0 | 50% | 175500 | -87750
xi | Inlet Chamber Area | 0 | [22 empty] | 1882958 | 1751358 | 93.01% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 |  | 0 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation & PCC | 209217.6 |  | 0 |  | 0 | 50% | 104608.8 |  | 0 | 50% | 104608.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 209217.6 | 100% | 209217.6 | 0% | 0 | 0
3 | RCC Foundation/Column footing | 418435.2 |  | 0 |  | 0 | 0% | 0 |  | 0 | 100% | 418435.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 418435.2 | 100% | 418435.2 | 0% | 0 | 0
4 | Column & Beam | 313826.4 |  | 0 |  | 0 | 0% | 0 |  | 0 | 25% | 78456.6 | 75% | 235369.8 | 75% | 235369.8 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 313826.4 | 100% | 313826.4 | 0% | 0 | 0
5 | RCC Slab | 313826.4 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | 30% | 94147.92 | 30% | 94147.92 | 70% | 219678.48 | 70% | 219678.48 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 313826.4 | 100% | 313826.4 | 0% | 0 | 0
6 | RCC Wall | 289652.4 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 289652.4 | 100% | 289652.4 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 289652.4 | 0% | 0 | 100% | 289652.4 | 0
7 | Testing/Finishing works | 188000 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 188000 | 30% | 56400 |  | 0 |  | 0 |  |  |  | 30% | 85% | -55% | 30% | 56400 | 0% | 0 | 30% | 56400 | -103400
xii | Manual & Mechanical Fine Bar Screen Chamber Area | 0 | [22 empty] | 1544702.4 | 1390702.4 | 90.03% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 |  | 0 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 121633.6 |  | 0 |  | 0 | 100% | 121633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 121633.6 | 100% | 121633.6 | 0% | 0 | 0
3 | PCC | 157450.4 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 157450.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 157450.4 | 100% | 157450.4 | 0% | 0 | 0
4 | RCC Foundation | 182450.4 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 182450.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 182450.4 | 100% | 182450.4 | 0% | 0 | 0
5 | Column & Beam | 182450.4 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 45612.6 | 75% | 136837.8 | 75% | 136837.8 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 182450.4 | 100% | 182450.4 | 0% | 0 | 0
6 | RCC Slab | 257450.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 128725.2 | 50% | 128725.2 | 50% | 128725.2 | 50% | 128725.2 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 257450.4 | 100% | 257450.4 | 0% | 0 | 0
7 | RCC Wall | 171633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171633.6 | 100% | 171633.6 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 171633.6 | 0% | 0 | 100% | 171633.6 | 0
8 | Walkway/Platform | 167633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 167633.6 | 100% | 167633.6 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 167633.6 | 0% | 0 | 100% | 167633.6 | 0
9 | Testing/Finishing works | 154000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 154000 | 0% | 0 |  | 0 |  | 0 |  |  |  | 0% | 85% | -85% | 0% | 0 | 0% | 0 | 0% | 0 | -130900
xiii | Grit Chamber Area | 0 | [22 empty] | 2040003.2 | 1891683.2 | 92.73% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 |  | 0 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 223844.8 |  | 0 |  | 0 | 100% | 223844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 223844.8 | 100% | 223844.8 | 0% | 0 | 0
3 | PCC | 268267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 268267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 268267.2 | 100% | 268267.2 | 0% | 0 | 0
4 | RCC Foundation | 268267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 268267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 268267.2 | 100% | 268267.2 | 0% | 0 | 0
5 | Column & Beam | 243267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 60816.8 | 75% | 182450.4 | 75% | 182450.4 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 243267.2 | 100% | 243267.2 | 0% | 0 | 0
6 | RCC Slab | 243267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 243267.2 | 100% | 243267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 243267.2 | 100% | 243267.2 | 0% | 0 | 0
7 | RCC Wall | 228844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 91537.92 | 40% | 91537.92 | 60% | 137306.88 | 60% | 137306.88 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 228844.8 | 0% | 0 | 100% | 228844.8 | 0
8 | Walkway/Platform | 228844.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 228844.8 | 100% | 228844.8 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 228844.8 | 0% | 0 | 100% | 228844.8 | 0
9 | Testing/Finishing works | 185400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 185400 | 20% | 37080 |  | 0 |  | 0 |  |  |  | 20% | 85% | -65% | 20% | 37080 | 0% | 0 | 20% | 37080 | -120510
xiv | Parshall Flume Channel Area | 0 | [22 empty] | 2831904 | 2608820.64 | 92.12% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 |  | 0 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 243267.2 |  | 0 |  | 0 | 100% | 243267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 243267.2 | 100% | 243267.2 | 0% | 0 | 0
3 | PCC | 293267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 293267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 293267.2 | 100% | 293267.2 | 0% | 0 | 0
4 | RCC Foundation | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 100% | 343267.2 | 0% | 0 | 0
5 | Column & Beam | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 | 25% | 85816.8 | 75% | 257450.4 | 75% | 257450.4 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 100% | 343267.2 | 0% | 0 | 0
6 | RCC Slab | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 137306.88 | 40% | 137306.88 | 60% | 205960.32 | 60% | 205960.32 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 40% | 137306.88 | 60% | 205960.32 | 0
7 | RCC Wall | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 102980.16 | 30% | 102980.16 | 70% | 240287.04 | 70% | 240287.04 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 0% | 0 | 100% | 343267.2 | 0
8 | Walkway/Platform | 343267.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 343267.2 | 100% | 343267.2 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 343267.2 | 0% | 0 | 100% | 343267.2 | 0
9 | Piping & fitting Work | 171633.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171633.6 | 90% | 154470.24 |  | 0 |  | 0 |  |  |  | 90% | 50% | 40% | 90% | 154470.24 | 0% | 0 | 90% | 154470.24 | 68653.44
10 | Testing | 257400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 257400 | 20% | 51480 |  | 0 |  | 0 |  |  |  | 20% | 0% | 20% | 20% | 51480 | 0% | 0 | 20% | 51480 | 51480
xv | Sludge Storage Platform Area | [23 empty] | 900000 | 885000 | 98.33% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 100000 |  | 0 |  | 0 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 100000 | 100% | 100000 | 0% | 0 | 0
2 | Excavation | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 100000 | 0% | 0 | 100% | 100000 | 0
3 | PCC | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 | 100% | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 250000 | 0% | 0 | 100% | 250000 | 0
4 | Foundation Work | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 210000 | 70% | 210000 | 30% | 90000 | 30% | 90000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 300000 | 0% | 0 | 100% | 300000 | 0
5 | Finishing work | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 150000 | 90% | 135000 |  | 0 |  | 0 |  |  |  | 90% | 30% | 60% | 90% | 135000 | 0% | 0 | 90% | 135000 | 90000
xvi | Transformer Yard Area | 0 | [22 empty] | 1164135 | 1164135 | 100% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Excavation | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 388045 | 100% | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 388045 | 100% | 388045 | 0% | 0 | 0
3 | PCC | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 388045 | 100% | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 388045 | 100% | 388045 | 0% | 0 | 0
4 | Foundation Work | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 388045 | 100% | 388045 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 388045 | 100% | 388045 | 0% | 0 | 0
xvii | DG Shed Area | 0 | [22 empty] | 1309665 | 1178698.5 | 90% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Excavation | 436555 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 436555 | 100% | 436555 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 436555 | 100% | 436555 | 0% | 0 | 0
3 | PCC | 436555 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 436555 | 100% | 436555 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 436555 | 100% | 436555 | 0% | 0 | 0
4 | Foundation Work | 436555 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 305588.5 | 70% | 305588.5 | 30% | 130966.5 | 0% | 0 |  | 0 |  | 0 |  |  |  | 70% | 100% | -30% | 70% | 305588.5 | 70% | 305588.5 | 0% | 0 | -130966.5
xviii | EXTERNAL DEVELOPMENT | [23 empty] | 6709119.95 | 5338052.682 | 79.56% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| Boundary Wall with Gate | 0 |  | 0 |  | 0 | 0% | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 0 | 100% | 0 | 0% | 0 | 0
2 | Excavation | 334750 | 40% | 133900 | 50% | 167223 | 10% | 33474 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 334597 | 100% | 334597 | 0% | 0 | 0
3 | PCC | 502125 | 40% | 200850 | 45% | 225956.25 |  | 0 | 7% | 35148.75 | 5% | 25106.25 | 3% | 15063.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 97% | 97% | 0% | 97% | 487061.25 | 97% | 487061.25 | 0% | 0 | 0
4 | RCC Column footing | 502125 | 40% | 200850 | 45% | 225956.25 |  | 0 | 7% | 35148.75 | 5% | 25106.25 | 3% | 15063.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 97% | 97% | 0% | 97% | 487061.25 | 97% | 487061.25 | 0% | 0 | 0
5 | RCC Column & Beam | 502352.95 | 40% | 200941.18 | 25% | 125588.2375 | 19% | 95447.0605 |  | 0 | 12% | 60282.354 | 4% | 20094.118 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 96% | 96% | 0% | 96% | 482258.832 | 96% | 482258.832 | 0% | 0 | 0
6 | Brickwork | 502125 | 15% | 75318.75 | 25% | 125531.25 | 30% | 150637.5 |  | 0 | 22% | 110467.5 | 8% | 40170 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 92% | 92% | 0% | 92% | 461955 | 92% | 461955 | 0% | 0 | 0
7 | Plaster | 501548 |  | 0 |  | 0 | 20% | 100309.6 |  | 0 | 40% | 200619.2 | 20% | 100309.6 | 20% | 100309.6 | 20% | 100309.6 |  | 0 |  | 0 |  | 0 |  |  |  | 80% | 60% | 20% | 80% | 401238.4 | 60% | 300928.8 | 20% | 100309.6 | 100309.6
8 | Retaining wall | 1611035 |  | 0 |  | 0 |  | 0 |  | 0 | 39% | 628303.65 | 40% | 644414 | 40% | 644414 | 21% | 338317.35 | 6% | 96662.1 |  | 0 |  | 0 |  |  |  | 85% | 79% | 6% | 85% | 1369379.75 | 79% | 1272717.65 | 6% | 96662.1 | 96662.1
9 | Finishing Work | 502125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 251062.5 | 50% | 251062.5 | 50% | 251062.5 | 20% | 100425 |  | 0 |  | 0 |  |  |  | 70% | 50% | 20% | 70% | 351487.5 | 50% | 251062.5 | 20% | 100425 | 100425
| Earthfilling, Internal Roads ,Landscaping | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Earthfilling, Internal Roads ,Landscaping | 1750934 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 1050560.4 | 55% | 963013.7 | 40% | 700373.6 |  | 0 |  | 0 |  | 0 |  |  |  | 55% | 20% | 35% | 55% | 963013.7 | 0% | 0 | 55% | 963013.7 | 612826.9
B | I & D Work | [23 empty] | 3042310.6 | 2904031.7721 | 95.45% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
(i) | Approach Channel | [26 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Excavation | 68186.6 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 34093.3 | 50% | 34093.3 | 50% | 34093.3 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 68186.6 | 90% | 61367.94 | 10% | 6818.66 | 0
2 | PCC | 170466.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170466.5 | 100% | 170466.5 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 170466.5 | 90% | 153419.85 | 10% | 17046.65 | 0
3 | RCC Foundation/Raft | 204559.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 204559.8 | 100% | 204559.8 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 204559.8 | 90% | 184103.82 | 10% | 20455.98 | 0
4 | wall | 170466.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 102279.9 | 60% | 102279.9 | 40% | 68186.6 | 40% | 68186.6 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 170466.5 | 90% | 153419.85 | 10% | 17046.65 | 0
5 | Testing/Finishing work | 61300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 61300 | 50% | 30650 |  | 0 |  | 0 |  |  |  | 50% | 0% | 50% | 50% | 30650 | 0% | 0 | 50% | 30650 | 30650
(ii) | Inlet Chamber | [26 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Excavation | 85968.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 85968.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 85968.2 | 100% | 85968.2 | 0% | 0 | 0
2 | PCC | 214920.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 214920.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 214920.5 | 100% | 214920.5 | 0% | 0 | 0
3 | RCC Foundation/Raft | 257904.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 257904.6 | 100% | 257904.6 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 257904.6 | 100% | 257904.6 | 0% | 0 | 0
4 | wall | 214920.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 214920.5 | 100% | 214920.5 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 214920.5 | 90% | 193428.45 | 10% | 21492.05 | 0
5 | Testing/Finishing work | 77300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 77300 | 50% | 38650 |  | 0 |  | 0 |  |  |  | 50% | 0% | 50% | 50% | 38650 | 0% | 0 | 50% | 38650 | 38650
(iii) | Screen Channel | [26 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Excavation | 68789.7 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 68789.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 68789.7 | 100% | 68789.7 | 0% | 0 | 0
2 | PCC | 171974.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171974.25 | 100% | 171974.25 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 171974.25 | 100% | 171974.25 | 0% | 0 | 0
3 | RCC Foundation/Raft | 206369.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 206369.1 | 100% | 206369.1 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 206369.1 | 100% | 206369.1 | 0% | 0 | 0
4 | wall | 171974.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 103184.55 | 60% | 103184.55 | 40% | 68789.7 | 40% | 68789.7 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 171974.25 | 80% | 137579.4 | 20% | 34394.85 | 0
5 | Testing/Finishing work | 61900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 61900 | 50% | 30950 |  | 0 |  | 0 |  |  |  | 50% | 0% | 50% | 50% | 30950 | 0% | 0 | 50% | 30950 | 30950
(iv) | Grit Chamber | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Excavation | 70669.7 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 70669.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 70669.7 | 100% | 70669.7 | 0% | 0 | 0
2 | PCC | 176674.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 176674.25 | 100% | 176674.25 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 176674.25 | 100% | 176674.25 | 0% | 0 | 0
3 | RCC Foundation/Raft | 212009.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 212009.1 | 100% | 212009.1 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 212009.1 | 100% | 212009.1 | 0% | 0 | 0
4 | wall | 176674.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 176674.25 | 100% | 176674.25 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 176674.25 | 80% | 141339.4 | 20% | 35334.85 | 0
5 | Testing/Finishing work | 63600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 100% | 63600 | 50% | 31800 |  | 0 |  | 0 |  |  |  | 50% | 0% | 50% | 50% | 31800 | 0% | 0 | 50% | 31800 | 31800
(v) | Collection Chamber | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Excavation | 13709.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 13709.2 | 100% | 13709.2 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 13709.2 | 100% | 13709.2 | 0% | 0 | 0
2 | PCC | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 34273 | 100% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 34273 | 100% | 34273 | 0% | 0 | 0
3 | RCC Foundation/Raft | 41127.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 41127.6 | 100% | 41127.6 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 41127.6 | 100% | 41127.6 | 0% | 0 | 0
4 | wall | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 80.23% | 27497.2279 | 80% | 27418.4 | 19.77% | 6775.7721 | 19.77% | 6775.7721 |  | 0 |  | 0 |  |  |  | 99.77% | 99.77% | 0% | 99.77% | 34194.1721 | 80% | 27418.4 | 19.77% | 6775.7721 | 0
5 | Testing/Finishing work | 12300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 12300 | 50% | 6150 |  | 0 |  | 0 |  |  |  | 50% | 0% | 50% | 50% | 6150 | 0% | 0 | 50% | 6150 | 6150
C | MPS-40 MLD | 0 | [22 empty] | 12366416.6667 | 12320891.6667 | 99.63% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| Civil Work | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
i | Construction of Raw Sewage Sump | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 500000 | 100% | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 500000 | 100% | 500000 | 0% | 0 | 0
2 | Excavation | 1591480 |  | 0 | 25% | 397869 | 75% | 1193610 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1591479 | 100% | 1591479 | 0% | 0 | 0
3 | PCC | 591480 |  | 0 |  | 0 | 100% | 591480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 591480 | 100% | 591480 | 0% | 0 | 0
4 | RCC Foundation/Raft | 687220 |  | 0 |  | 0 |  | 0 | 100% | 687220 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 687220 | 100% | 687220 | 0% | 0 | 0
5 | Wall 50% of total lift work | 687220 |  | 0 |  | 0 |  | 0 | 20% | 137444 | 80% | 549776 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 687220 | 100% | 687220 | 0% | 0 | 0
6 | Walls (balance 50% of Total Lift work) | 887220 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 798498 | 10% | 88722 | 10% | 88722 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 887220 | 100% | 887220 | 0% | 0 | 0
7 | Column & Beam | 787220 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 787220 | 100% | 787220 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 787220 | 100% | 787220 | 0% | 0 | 0
8 | Ground Floor Slab | 591480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 591480 | 100% | 591480 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 591480 | 100% | 591480 | 0% | 0 | 0
9 | Testing/Finishing work | 591480 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 177444 | 30% | 177444 | 70% | 414036 | 65% | 384462 |  | 0 |  | 0 |  |  |  | 95% | 75% | 20% | 95% | 561906 | 0% | 0 | 95% | 561906 | 118296
ii | Construction of Raw Sewage Pump House | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Column & Beam | 924187.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 462093.75 | 50% | 462093.75 | 50% | 462093.75 | 50% | 462093.75 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 924187.5 | 100% | 924187.5 | 0% | 0 | 0
2 | Roof Slab | 924187.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 277256.25 | 30% | 277256.25 | 70% | 646931.25 | 70% | 646931.25 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 924187.5 | 70% | 646931.25 | 30% | 277256.25 | 0
3 | Brickwork | 924187.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 924187.5 | 100% | 924187.5 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 924187.5 | 0% | 0 | 100% | 924187.5 | 0
4 | Plaster | 924187.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 924187.5 | 100% | 924187.5 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 924187.5 | 0% | 0 | 100% | 924187.5 | 0
iii | Construction of Inlet Chamber & Screen Channel | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 150000 | 100% | 150000 | 0% | 0 | 0
2 | Excavation | 184837.5 |  | 0 |  | 0 | 100% | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
3 | PCC | 184837.5 |  | 0 |  | 0 |  | 0 | 100% | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
4 | RCC Foundation/Raft | 184837.5 |  | 0 |  | 0 |  | 0 | 100% | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
5 | Wall 50% of total lift work | 184837.5 |  | 0 |  | 0 |  | 0 | 15% | 27725.625 | 85% | 157111.875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
6 | Walls (balance 50% of Total Lift work) | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 92418.75 | 50% | 92418.75 | 50% | 92418.75 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
7 | Column & Beam | 151504.1667 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 151504.1667 | 100% | 151504.1667 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 151504.1667 | 100% | 151504.1667 | 0% | 0 | 0
8 | Ground Floor Slab | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184837.5 | 100% | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 100% | 184837.5 | 0% | 0 | 0
9 | Walkway/Platform | 184837.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184837.5 | 100% | 184837.5 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 184837.5 | 50% | 92418.75 | 50% | 92418.75 | 0
10 | Testing/Finishing work | 159500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 159500 | 90% | 143550 |  | 0 |  | 0 |  |  |  | 90% | 75% | 15% | 90% | 143550 | 0% | 0 | 90% | 143550 | 23925
D | SEWER SYSTEM AREA (3.2 Km) | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 73746525.28 | 65634143.1385 | 89% | 100% | 100% | 0% | 100% | 0 | 100% | 0 | 0% | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Supply of pipes | 55309038.5 | 20% | 11063230.7904 | 35% | 19360021.8365 | 43% | 23785113.9165 | 2% | 1100672.77 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 55309039.3135 | 100% | 55309039.3135 | 0% | 0 | 0
3 | Excavation and Laying of pipes including bed preperation & backfilling | 5530711.83 |  | 0 |  | 0 | 13% | 718992.5379 | 24.12% | 1333945.6934 | 25.56% | 1407075.0937 | 24.44% | 1351705.9713 | 24.44% | 1351705.9713 | 13% | 718992.5379 | 13% | 718992.5379 |  | 0 |  | 0 |  |  |  | 100.1% | 100.1% | 0% | 100.1% | 5530711.8342 | 86.68% | 4787384.1642 | 13.44% | 743327.67 | 0
4 | Manholes | 3688157.95 |  | 0 |  | 0 |  | 0 | 10% | 368815.795 |  | 0 | 25% | 922039.4875 | 25% | 922039.4875 | 65% | 2397302.6675 | 65% | 2397302.6675 |  | 0 |  | 0 |  |  |  | 100% | 90% | 10% | 100% | 3688157.95 | 10% | 368815.795 | 90% | 3319342.155 | 368815.795
5 | Flow/Hydroulic Testing | 7374893.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 7374893.6 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
6 | Road restoration work | 1843723.4 |  | 0 |  | 0 |  | 0 |  | 0 | 50.26% | 926507.3808 | 10% | 179726.66 | 10% | 179726.66 | 40% | 737489.36 |  | 0 |  | 0 |  | 0 |  |  |  | 60.26% | 60.26% | 0% | 60.26% | 1106234.0408 | 60.26% | 1110879.7208 | 0% | -4645.68 | 0
E | RISING MAIN PIPING WORK (100 m) | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 685000 | 616500 | 90% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Supply of pipes | 548000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 274000 | 25.2% | 137994.48 | 25.2% | 137994.48 | 25% | 136005.52 | 25% | 136005.52 |  | 0 |  | 0 |  |  |  | 100.2% | 100.2% | 0% | 100.2% | 548000 | 100% | 548000 | 0.201% | 0 | 0
3 | Cutting,Excavtion,Laying of Pipes, backfilling | 68500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 13700 | 20% | 13700 | 50% | 34250 | 50% | 34250 | 30% | 20550 | 30% | 20550 |  |  |  | 100% | 100% | 0% | 100% | 68500 | 0% | 0 | 100% | 68500 | 0
4 | Testing | 68500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 68500 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
F | EFFLUENT DISPOSAL SYSTEM | 0 | [25 empty] | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3779999.93 | 3723299.9311 | 98.5% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
1 | Site Clearance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
2 | Construction of Effluent Channel from Distribution Chamber to Agriculture Land | 1511999.972 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1360799.9748 | 90% | 1360799.9748 | 10% | 151199.9972 | 10% | 151199.9972 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1511999.972 | 90% | 1360799.9748 | 10% | 151199.9972 | 0
3 | Construction of Rectangular Channel from STP to Distribution Chamber | 1133999.979 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1020599.9811 | 90% | 1020599.9811 | 10% | 113399.9979 | 10% | 113399.9979 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1133999.979 | 90% | 1020599.9811 | 10% | 113399.9979 | 0
4 | Construction of Distribution Chamber | 1133999.979 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1020599.9811 | 90% | 1020599.9811 | 10% | 113399.9979 | 5% | 56699.999 |  | 0 |  | 0 |  |  |  | 95% | 95% | 0% | 95% | 1077299.9801 | 50% | 566999.9895 | 45% | 510299.9906 | 0
G | E&M WORK | [18 empty] | 0 |  |  |  | 0 | 165400000 | 152063466.02 | 91.94% | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
i) | GRIT CHAMBER AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.On supply - Grit Scraper Mechanism | 2700000 |  | 0 |  | 0 | 100% | 2160000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2160000 | 100% | 2160000 | 0% | 0 | 0
| B.On Installation - Grit Scraper Mechanism |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 540000 | 100% | 540000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 540000 | 0% | 0 | 100% | 540000 | 0
ii) | SLUDGE THICKENER AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Sludge Thickener | 1600000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1280000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1280000 | 100% | 1280000 | 0% | 0 | 0
| B.Installation - Sludge Thickener |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 320000 | 100% | 320000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 320000 | 80% | 256000 | 20% | 64000 | 0
iii) | TRANSFORMER YARD AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Transformer | 5500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 4400000 | 100% | 4400000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 4400000 | 100% | 4400000 | 0% | 0 | 0
| B.Installation - Transformer |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1100000 | 100% | 1100000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1100000 | 0% | 0 | 100% | 1100000 | 0
iv) | DG SHED AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - DG | 12500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 10000000 | 100% | 10000000 |  |  |  | 100% | 100% | 0% | 100% | 10000000 | 100% | 10000000 | 0% | 0 | 0
| B.Installation - DG |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2500000 | 100% | 2500000 |  |  |  | 100% | 100% | 0% | 100% | 2500000 | 0% | 0 | 100% | 2500000 | 0
v) | MEP |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Screen | 7600000 |  | 0 |  | 0 |  | 0 | 100% | 6080000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 6080000 | 100% | 6080000 | 0% | 0 | 0
| B.Installation - Screen |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1520000 | 100% | 1520000 |  |  |  | 100% | 100% | 0% | 100% | 1520000 | 0% | 0 | 100% | 1520000 | 0
| C.Supply - Hoist | 700000 |  | 0 |  | 0 |  | 0 | 100% | 560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 560000 | 100% | 560000 | 0% | 0 | 0
| D.Installation - Hoist |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 140000 | 100% | 140000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 140000 | 0% | 0 | 100% | 140000 | 0
| E.Supply - Pumps & Motors(MEP) | 11600000 |  | 0 |  | 0 |  | 0 | 25.07% | 2326496 | 74.93% | 6953504 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 9280000 | 100% | 9280000 | 0% | 0 | 0
| F.Installation - Pumps & Motors(MEP) |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 50% | 1160000 | 50% | 1160000 | 50% | 1160000 | 50% | 1160000 |  |  |  | 100% | 100% | 0% | 100% | 2320000 | 0% | 0 | 100% | 2320000 | 0
| G.Supply - Gate & Valves(MPS) | 5200000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 2080000 | 50% | 2080000 | 50% | 2080000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 4160000 | 100% | 4160000 | 0% | 0 | 0
| H.Installation - Gate & Valves(MPS) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1040000 | 100% | 1040000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1040000 | 0% | 0 | 100% | 1040000 | 0
| I.Supply Instruments(like flow meter, Guages, level, Transmiter) | 3200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2560000 | 100% | 2560000 |  | 0 |  | 0 |  |  |  | 100% | 90% | 10% | 100% | 2560000 | 0% | 0 | 100% | 2560000 | 320000
| J.Installation - Instruments(like flow meter, Guages, level, Transmiter) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 640000 | 65% | 416000 |  |  |  | 65% | 60% | 5% | 65% | 416000 | 0% | 0 | 65% | 416000 | 0
vi) | INLET CHAMBER AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Gate & Valves(STP) | 4200000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1680000 | 50% | 1680000 | 50% | 1680000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 3360000 | 100% | 3360000 | 0% | 0 | 0
| B.Installation - Gate & Valves(STP) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 167998 | 20% | 167998 | 80% | 672000 | 80% | 672000 |  |  |  | 100% | 100% | 0% | 100% | 839998 | 0% | 0 | 100% | 839998 | 0
vii) | FINE SCREEN AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.On supply -Fine Screen | 3200000 |  | 0 |  | 0 |  | 0 | 100% | 2560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2560000 | 100% | 2560000 | 0% | 0 | 0
| B.On Installation -Fine Screen |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 640000 | 100% | 640000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 640000 | 0% | 0 | 100% | 640000 | 0
viii) | SBR BASIN AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A..On supply - Decanter Equipment | 19300000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 15440000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 15440000 | 100% | 15440000 | 0% | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| B..Installation - Decanter Equipment |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1930000 | 50% | 1930000 | 50% | 1930000 | 50% | 1930000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 3860000 | 0% | 0 | 100% | 3860000 | 0
| C.On supply - Diffuser | 19300000 |  | 0 |  | 0 |  | 0 | 100% | 15440000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 15440000 | 100% | 15440000 | 0% | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| D.On Installation - Diffuser |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3860000 | 100% | 3860000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 3860000 | 0% | 0 | 100% | 3860000 | 0
| E.On supply - RAS Pump, SAS Pump | 5400000 |  | 0 |  | 0 |  | 0 | 100% | 4320000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 4320000 | 100% | 4320000 | 0% | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| F.On Installation - RAS Pump, SAS Pump |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1080000 | 100% | 1080000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 1080000 | 0% | 0 | 100% | 1080000 | 0
| G.On supply - Chain Pulley Block | 700000 |  | 0 |  | 0 | 100% | 560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 560000 | 100% | 560000 | 0% | 0 | 0
| H.On Installation - Chain Pulley Block |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 140000 | 100% | 140000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 140000 | 0% | 0 | 100% | 140000 | 0
ix) | AIR BLOWER ROOM |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Blower | 6000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60.29% | 2893920 | 60% | 2880000 | 39.71% | 1906080 | 40% | 1920000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 4800000 | 0% | 0 | 100% | 4800000 | 0
| B. Installation - Blower |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 39.4% | 471457 | 39.4% | 471457 | 60.6% | 728581 | 61% | 732000 |  |  |  | 100.4% | 100.4% | 0% | 100.4% | 1203457 | 0% | 0 | 100.4% | 1203457 | 0
| C.Supply - Hoist Work | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 400000 | 100% | 400000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 400000 | 100% | 400000 | 0% | 0 | 0
| D.Installation - Hoist Work |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 100000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 100000 | 0% | 0 | 100% | 100000 | 0
x) | CHLORINATION ROOM AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - Chlorination system (Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work | 2900000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1160000 | 40% | 928000 | 40% | 928000 | 10% | 232000 | 10% | 232000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2320000 | 50% | 1160000 | 50% | 1160000 | 0
| B. Installation - Chlorination system(Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 232000 | 40% | 232000 | 60% | 348000 | 50% | 290000 |  |  |  | 90% | 70% | 20% | 90% | 522000 | 0% | 0 | 90% | 522000 | 0
| C.Supply - Chlorine Nutrilisation Tank | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 400000 | 100% | 400000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 400000 | 0% | 0 | 100% | 400000 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| D.Installation - Chlorine Nutrilisation tank |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 100000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 100000 | 0% | 0 | 100% | 100000 | 0
| E.Supply - Hoist Work | 700000 |  | 0 |  | 0 |  | 0 | 100% | 560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 560000 | 100% | 560000 | 0% | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| F.Installation - Hoist Work |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 140000 | 100% | 140000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 140000 | 0% | 0 | 100% | 140000 | 0
xi) | CENTRIFUGE HOUSE & FEED PUMP AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.On supply -Centrifuge & Feed Pump | 10300000 |  | 0 |  | 0 |  | 0 | 100% | 8240000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 8240000 | 100% | 8240000 | 0% | 0 | 0
| B.On Installation -Centrifuge & Feed Pump |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1853997.28 | 90% | 1853997.28 | 10% | 206002.72 | 10% | 206000 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 2059997.28 | 84% | 1730400 | 16% | 329597.28 | 0
xii) | ADMN BUILDING AREA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| A.Supply - PMCC work | 11800000 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 4720000 | 50% | 4720000 | 50% | 4720000 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 100% | 100% | 0% | 100% | 9440000 | 50% | 4720000 | 50% | 4720000 | 0
| B.Installation - PMCC work |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 47.25% | 1115037 | 47% | 1109137 | 45.19% | 1066460.74 | 45.19% | 1066460.74 | 7.56% | 178618.64 | 7.56% | 178416 |  |  |  | 99.75% | 99.75% | 0% | 99.75% | 2354013.74 | 0% | 0 | 99.75% | 2354013.74 | 0
| C.Supply - PLC/SCADA Automation of MPS,STP,D.G set) | 10000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 8000000 | 100% | 8000000 |  |  |  | 100% | 100% | 0% | 100% | 8000000 | 40% | 3200000 | 60% | 4800000 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
| D.Installation - PLC/SCADA Automation of MPS,STP,D.G set) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2000000 | 40% | 800000 |  |  |  | 40% | 40% | 0% | 40% | 800000 | 0% | 0 | 40% | 800000 | 0
xiii) | TESTING OF E&M EQUIPMENT FOR STP & MPS | 19400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 19400000 | 42% | 8148000 |  |  |  | 42% | 22% | 20% | 42% | 8148000 | 0% | 0 | 42% | 8148000 | 3880000
xiv) | EQUIPMENT TOOLS & MISC. | 600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 600000 |  | 0 |  |  |  | 0% | 0% | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0
III | TRIAL RUN & COMMISSIONING | [26 empty] | 0% | 0 | [7 empty] | 0
1 | Trial Run & Commissioning | [35 empty] | 0
|  | 382690000.326 |  | 47836249.6557 |  | 47836249.7795 |  | 47836250.0248 |  | 47836250.1375 |  | 47836250.28 |  | 47836250.1502 |  | 47638413.0043 |  | 47836249.8665 |  | 34684905.0156 |  | 47836249.64 |  | 34436966 | 382690000.326 | 355941533.891 | 93.01% |  |  |  | 93.01% | 355941533.8973 | 75% | 287008427.295 | 18.01% | 68933106.6023
| 1st milestone |  | = | 47836249.6557 | [28 empty] | Need for 7th Milestone |  | 12.5% | 47836250.0407
| 2nd milestone |  | = | 47836249.7795 | [28 empty] | Balance to achieve |  | -5.513% | -21096856.5616
| 3rd Milestone |  | = | 47836250.0248
| 4th Milestone |  | = | 47836250.1375
| 5th Milestone |  | = | 47836250.28
| 6th Milestone |  | = | 47638413.0043
| 7th Milestone |  | = | 34684905.0156
| 8th Milestone |  | = | 34436966
| Total Amount |  | = | 355941533.8973
| Total % as on 31.01.2023 |  | = | 93.01%
Note:
1) Above listed are itemwise major activities, but all required works/items must be included & completed as per approved drawings & design, as project is turnkey basis;
2) variation clause applicable
3) Items/Payments shall be as per relevant clauses of Concessionaire Agreement