**ANNEXURE 1: Progress of Work – HAM Project Kanpur**

| **Date** | **Name of Activity#** | **Date of Receipt** | **Date of Approval**  **(Vet/ Comment)** | **No. of day taken** | **Time as per contract**  **(days)** | **Delay if any (No. of days)**  **[7=6-5]** | **Reason for delay\*** | **Key Personnel deployed** | **Man-days of each Key Personnel** | **Delay by Concessionaire** | **Reason for delay** | **Step taken by PE to avoid such delays** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) |
| 01.02.2023 | Completion of 5th Milestone for 05 MLD Shuklaganj STP | 25.01.2023 K-2789 | - | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | Under Review |
| 02.02.2023 | Observation on Monthly Activity Report of 210 MLD STP Bingawan facilities for the month of Dec-2022 | 12.01.2023 K-271 (Hard copy received on 16.01.2023) | - | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | Under Review |
| 03.02.2023 | Observation on Monthly Activity Report of 210 MLD STP Bingawan facilities for the month of Dec-2022 | 12.01.2023 K-271 (Hard copy received on 16.01.2023) | 03.02.2023 S-1970 | 18 | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report |
| 03.02.2023 | Inspection Report of 210 MLD STP Bingawan for Inspection held on 04.01.2023 & 16.01.2023. | - | 03.02.2023 S-1969 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report |
| 03.02.2023 | Inspection report of associated works of 210 MLD Bingawan STP (IPS Rakhimandi, Munshipurwa and Halwakanda) for the inspection done on 28.01.2023 | - | 03.02.2023 S-1971 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report. |
| 03.02.2023 | Balance Works Status for 30 MLD STP at Pankha as of 02 Feb 2023 | - | 03.02.2023 S-1973A | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report. |
| 03.02.2023 | Balance Works Status for 15MLD STP at Unnao as of 02 Feb 2023 | - | 03.02.2023 S-1972 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report. |
| 03.02.2023 | Balance Works Status for 130 MLD STP at Jajmau as of 01 Feb 2023 | - | 03.02.2023 S-1974 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report. |
| 03.02.2023 | Completion of 5th Milestone for 05 MLD Shuklaganj STP | 25.01.2023 K-2789 | 03.02.2023 S-1975 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observation and requested UPJN to direct concessionaire to submit compliance report. |
| 04.02.2023 | Submission of DO Analyzer documents for 130 MLD at Jajmau | 14.01.2023 K-2784 | - | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | Under Review |
| 05.02.2023 | **Sunday** | | | | | | | | | | | | |
| 06.02.2023 | Submission of DO Analyzer documents for 130 MLD at Jajmau | 14.01.2023 K-2784 |  |  | 20 | - | - | Anil Priyesh  Ajay  Rahul  Divya  Karamveer | 1+1+1+1+1+1 | - | - | - | Under Review |
| 07.02.2023 | Inspection report for 30 MLD Pankha facility , inspection done on 7.2.23. | - | 07.02.2023 S-1977 | - | 20 | - | - | Anil  Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 07.02.2023 | Submission of DO Analyzer documents for 130 MLD at Jajmau | 14.01.2023 K-2784 | 07.02.2023 S-1976 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 08.02.2023 | Observation on monthly activity report of 42 MLD STP Sajari facilities for the month of Jan-23 | 08.02.2023 K-253 | - | - | 20 | - | - | Anil  Prasoon Preetam Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | Under Review |
| 09.02.2023 | STC observation on monthly activity report for the month of january 2023 of 43 MLD STP jajmau facilities phase-II | 09.02.2023 K-254 | - | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | Under Review |
| 10.02.2023 | Submission of DO analyzer and conductivity type LS & Float operated LS document for 130 MLD STP at Jajmau | - | 10.02.2023 S-1981 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Inspection report of 42 MLD Sajari facilities, Inspection done on 9.2.23 | - | 10.02.2023 S-1982 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Rejected Drg: letter 2755 submisson of Design calculation civil assignment drawing and structural drawing for DG set foundation for 130 MLD STP Jajmau facilities | - | 10.01.2023 S-1978 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Recommendation for your approval of structural drawing for flare structural foundation drawing for 130 MLD STP Jajmau facilities | - | 10.02.2023 S-1979 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Observation on monthly activity report of 42 MLD STP Sajari facilities for the month of Jan-23 | 08.02.2023 K-253 | 10.02.2023 S-1983 | 2 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Regarding pending RFI (civil) for Raw Sewage Sump and pump house,  inlet chamber and screen chamber, Meter room cum staff quarter, Guard room, Transformer  and DG set area, at IPS located at Sundar nagar and ICI Nallah. | KRMPL RFI dated 04.02.2023 | 10.02.2023 S-1984 | 6 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1=1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | Regarding submission of micro work plan of E&M work for 130 MLD STP Jajmau. | - | 10.02.2023 S-1985 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | STC observation on monthly activity report for the month of january 2023 of 43 MLD STP jajmau facilities phase-II | 09.02.2023 K-254 | 10.02.2023 S-1986 | 1 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 10.02.2023 | 5th Milestone completion certificate for the 5MLD Shuklaganj STP | 08.02.2023 K-2812 | 10.02.2023 S-1980 | 2 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 11.02.2023 | **Second Saturday** | | | | | | | | | | | | |
| 12.02.2023 | **Sunday** | | | | | | | | | | | | |
| 13.02.2023 | Inspection report of 30 MLD Pankha STP, Inspection done on 7/1/23. | - | 13.02.2023 S-1987 | - | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 13.02.2023 | STC Observation on monthly activity report for the month of January 2023 of 130 MLD STP Jajmau facilities phase-1 | 09.02.2023 K-255 | 13.02.2023 S-1988 | 4 | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 14.02.2023 | Submission of MPR for the month of January 23 | - | 14.02.2023 S-1989 | - | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 14.02.2023 | 05 MLD STP Shuklaganj site inspection report of dated 11th Feb | - | 14.02.2023 S-1990 | - | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 14.02.2023 | Inspection Report of 130 MLD Jajmau phase I STP, Inspection done on 13.2.23 | - | 14.02.2023 S-1991 | - | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 15.02.2023 | Observation on monthly activity report of 210 MLD STP Bingawan facilities | 15.02.2023 K-261 | 15.02.2023 S-1992 | 1 | 20 | - | - | Anil  Satish Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 16.02.2023 | Pending supply of Mechanical items for 130 MLD Jajmau STP | - | 16.02.2023 S-1993 | - | 20 | - | - | Anil  Satish Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 17.02.2023 | STC comments on compliance given by KRMPL for STC observation on MAR of 42 MLD Sajari for the month of Jan-23 | 15.02.2023 K-270 | - | - | 20 | - | - | Anil  Satish Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | Under Review |
| 18.02.2023 | **Maha Shiv Ratri** | | | | | | | | | | | | |
| 19.02.2023 | **Sunday** | | | | | | | | | | | | |
| 20.02.2023 | STC comments on compliance given by KRMPL for STC observation on MAR of 42 MLD Sajari for the month of Jan-23 | 15.02.2023 K-270 | 20.02.2023 S-1994 | 1 | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 21.02.2023 | Final Commissioning & Electrical testing of equipments at 15 MLD STP Unnao | KRMPL RFI issued on 17.02.2023 | 21.02.2023 S-1995 | 4 | 20 | - | - | Anil  Sunil Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 22.02.2023 | Inspection report for 15 MLD STP Unnao inspection done on 20.02.2023 | - | 22.02.2023 S-1996 | - | 20 | - | - | Anil  Satish Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions for the information and record. |
| 22.02.2023 | Recommendation for approval of Pump documents for Parmat pump House no.03 at 130 MLD STP Jajmau facilities | 08.02.2023 K-2807 | 22.02.2023 S-1997 | 14 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 22.03.2023 | Regarding change in dimension of new construction work of CCT at 130 MLD STP Jajmau | - | 22.02.2023 S-1998 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 22.03.2023 | Regarding for not clear drawing of Bypass Arrangement at 210 MLD STP Bingawan | 17.02.2023 K-258 | 22.03.2023 S-1999 | 5 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 23.02.2023 | Observation on Annual Maintenance Plan of Bingawan year 03 (10.08.2022 to 09.08.2023) | 20.01.2023 K-231 | 23.02.2023 S-2000 | 3 | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 23.02.2023 | Submission of compliance regarding operation & control philosophy & interlocking P&ID for130 MLD STP at Jajmau | - | 23.02.2023 S-2001 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 23.02.2023 | Submission of compliance regarding operation & control philosophy & interlocking P&ID for 15 <LD STP Unnao & 5 MLD STP Shuklaganj | - | 23.02.2023 S-2002 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 23.02.2023 | Submission of " Pressure Gauge" documents for 130 MLD at Jajmau | - | 23.02.2023 S-2003 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 23.02.2023 | Submission data sheet & QAP of DULT,ULT,PT and RLT document for 130 MLD STP at Jajmau | - | 23.02.2023 S-2004 | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 24.02.2023 | Regarding Time Extension for 130 MLD STP Jajmau facility | - | 24.02.2023 Draft sent through email to UPJN | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 25.02.2023 | Submission of connecting channel drawing from PTU to SBR for 05 MLD STP Shuklaganj | 21.02.2023 K-2820 | - | - | 20 | - | - | Anil  Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | Under review |
| 26.02.2023 | **Sunday** | | | | | | | | | | | | |
| 27.02.2023 | Inspection Report of 130 MLD IPS facilities Phase I for inspection done on  22.02.2023 | - | 27.02.2023 S-2005 | - | 20 |  |  | Anil  Sunil Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions |
| 27.02.2023 | Inspection Report of 43 MLD IPS facilities Phase II for inspection done on  22.02.2023 | - | 27.02.2023 S-2006 | - | 20 | - | - | Anil  Sunil Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 27.02.2023 | Inspection Report of 43 MLD STP Jajmau facilities, Inspection done on 10.02.2023 | - | 27.02.2023 S-2007 | - | 20 | - | - | Anil  Sunil Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 27.02.2023 | Inspection report of associated works of 210 MLD Bingawan STP (IPS Rakhimandi, Munshipurwa and Halwakanda) for the inspection done on 10.02.2023 | - | 27.02.2023 S-2008 | - | 20 | - | - | Anil  Sunil Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 27.02.2023 | Inspection Report of 210 MLD STP Bingawan for Inspection held on 03.02.2023 and 16.02.2023 | - | 27.02.2023 S-2009 | - | 20 | - | - | Anil  Sunil Prasoon Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Observation on Submission of Operation and maintenance Manual for 30 MLD STP Pankha | - | 28.02.2023 S-2010 | - | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Regarding Installation of centrifuge feed pumps -2 nos, dosing pumps 2nos, supretentant sump agitator 1no, sludge sump agitator 1 no, sludge sump agitator 1no, poly dosing sump agitator, fine bar mechanical screen -2 nos at PTU manual screen -1 no at PTU, Air blower-3 nos at 15 MLD STP Unnao Faclities | - | 28.02.2023 S-2011 | - | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Inspection Report of 130 MLD STP Jajmau facilities ,Inspection done on 01.02.2023, 04.02.2023, 13.02.2023 and 15.02.2023 | - | 28.02.2023 S-2012 | - | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Request letter for Time Extension for 30 MLD STP Pankha | 10.02.2023 K-2815 | 28.02.2023 S-2013 | 18 | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Request letter for Time Extension for 130 MLD STP Jajmau Facilities | 10.02.2023 K-2814 | 28.02.2023 S-2014 | 18 | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Regarding for Leakage in civil water retaining structure for 30 MLD STP Pankha. | - | 28.02.2023 S-2015 | - | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
| 28.02.2023 | Regarding missing Data for submission of connecting channel drawing from PTU to SBR for 05 MLD STP Shuklaganj | 21.02.2023 K-2820 | 28.02.2023 S-2016 | 7 | 20 | - | - | Anil  Sunil Priyesh  Ajay  Rahul  Divya  Karamveer  Indra Dev | 1+1+1+1+1+1+1+1 | - | - | - | PE submitted their observations for information and necessary actions. |
|  | | | | | | | | | | | | | |

**Note:** Man-days and respective inputs of experts for the month of February 2023 are:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **SN** | **Name** | **Designation** | **Total Man-days** | **Input** |
|  | Mr. Anil Kumar Seth | Team Leader cum waste water expert | 28 | Timesheet attached |
|  | Mr. Preetam Walunjkar | Senior Structure Engineer | 01 | Timesheet attached |
|  | Mr. Satish Kamaraju | Senior Process Engineer | 10 | Timesheet attached |
|  | Mr. Sunil Basutkar | Senior Mechanical Engineer | 04 | Timesheet attached |
|  | Mr. Prasoon Bhardwaj | Instrumentation Engineer | 15 | Timesheet attached |