## Pankha
PROGRESS REPORT FOR 30 MLD PANKHA SITE
Sl. No. | Description of Items | Total Amount | % | BOQ Amount | Milestone-1 (From 26th Nov.'19 to 25th Sep'20) |  | Milestone-2 (From 26th Sep.'20 to 25th Nov.'20) |  | Milestone-3 (From 26th Nov.'20 to 22nd Feb'21) |  | Milestone-4 (From 23rd Feb'21 to 01 July'21) |  | Milestone-5 (From 2nd July'21 to 06th September'21) |  | Milestone-6 (From 07th September'21 to 06th December'21) |  | Milestone-7 (From 07th December'21 to 25th Mar'22) |  | Achieved for 7th Milestone |  | Milestone-8 (From 26th Mar'22 to 25th Apr'22) |  | Achieved for 8th Milestone |  |  | Total Amount | Amount Achieved | Percentage | Upto Oct'22 | upto Sept'22 | For Oct'22
[5 empty] | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.)
A | Design & Drawing & STP & Sewer Laying works | 49935900 | [23 empty] | 49935900 | 49935900 | 100%
| A. On approval of BEP |  | 0.5 | 24967950 | 100% | 24967950 | [13 empty] | 0 |  |  |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| B. On approval of design & drawings for Civil & Sewerage works |  | 0.5 | 24967950 | 100% | 24967950 | [13 empty] | 0 |  |  |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
B | CONSTRUCTION | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| STP (30 MLD) | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
1 | SBR Basin Area | [18 empty] | 0 |  |  |  | 0 | 0% | 236210000 | 235435695.36 | 99.67% | 0% | 0% | 0% | 0
| CIVIL WORK | 137576000 | [17 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Site Clearance |  |  | 250000 | 100% | 250000 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  | 7.1512 | 9838400 | 100% | 9838400 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 14757600 | 100% | 14757600 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  | 17.8781 | 24596000 | 40% | 9838400 | 60% | 14757600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  | 17.8781 | 24596000 |  | 0 | 100% | 24596000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  | 17.8781 | 24596000 |  | 0 |  | 0 | 60% | 14757600 | 38% | 9346480 | 2% | 491920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Baffle Walls work |  | 8.9391 | 12298000 |  | 0 |  | 0 | 55% | 6763900 | 38% | 4673240 | 7% | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  | 8.9391 | 12298000 |  | 0 |  | 0 |  | 0 | 47.13% | 5796063.27 | 27.87% | 3427436.73 | 19.64% | 2415095.36 | 5.36% | 659172.8 | 5% | 614900 |  | 0 |  | 0 | 100% |  |  |  | 99.64% | 99.64% | 0% | 0
| Finishing Work |  | 10.6094 | 14596000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 4378800 | 40% | 5838400 | 40% | 5838400 | 30% | 4378800 | 25% | 3649000 | 100% |  |  |  | 95% | 85% | 10% | 1459600
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| A. DECANTERS | 36894000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 31359900 | [7 empty] | 0 |  | 0 | 100% | 31359900 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 3689400 | [7 empty] | 0 |  | 0 |  | 0 | 50% | 1844700 | 50% | 1844700 | 50% | 1844700 | 50% | 1844700 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1844700 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 1844700 | 100% |  |  |  | 100% | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| B. DIFFUSERS | 24596000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 20906600 | [7 empty] | 0 | 100% | 20906600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 2459600 | [9 empty] | 0 |  | 0 | 50% | 1229800 | 50% | 1229800 | 50% | 1229800 | 50% | 1229800 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1229800 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 1229800 | 100% |  |  |  | 100% | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| C. RAS & SAS PUMPS | 24596000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 20906600 | [6 empty] | 50% | 10453300 | 50% | 10453300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 2459600 | [7 empty] | 0 |  | 0 | 50% | 1229800 | 50% | 1229800 | 50% | 1229800 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1229800 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 1229800 | 100% |  |  |  | 100% | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| D. PIPES & FITTINGS | 12298000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 10453300 | [7 empty] | 0 |  | 0 | 100% | 10453300 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 1229800 | [7 empty] | 0 |  | 0 | 75% | 922350 | 25% | 307450 | 25% | 307450 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 614900 | [7 empty] | 0 |  | 0 | 20% | 122980 |  | 0 |  | 0 | 80% | 491920 | 80% | 491920 | 100% |  |  |  | 100% | 100% | 0% | 0
2 | Chlorine Contact Tank Area | 18597000 | [17 empty] | 0 |  |  |  | 0 | 0% | 18597000 | 18320295 | 98.51% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 737880 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1106820 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 4611750 |  | 0 | 100% | 4611750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Baffle Walls work |  |  | 3689400 |  | 0 |  | 0 | 70% | 2582580 | 25% | 922350 | 3% | 110682 | 2% | 73788 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 80% | 2213640 | 80% | 2213640 | 20% | 553410 | 10% | 276705 | 100% |  |  |  | 90% | 80% | 10% | 276705
3 | Chlorination House Area | [18 empty] | 0 |  |  |  | 0 | 0% | 18547000 | 17929025.5 | 96.67% | 0% | 0% | 0% | 0
| CIVIL WORK | 12090550 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 368940 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 553410 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Column footing |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 | 50% | 461175 | 50% | 461175 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground floor Slab |  |  | 922350 |  | 0 |  | 0 |  | 0 | 50% | 461175 | 50% | 461175 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Roof Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1844700 |  | 0 |  | 0 |  | 0 | 10% | 184470 | 20% | 368940 | 70% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 90% | 1660230 |  | 0 |  | 0 | 100% |  |  |  | 90% | 90% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| A. CHLORINATION SYSTEM | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 3135990 | 100% | 3135990 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 368940 |  | 0 |  | 0 | 100% |  |  |  | 100% | 95% | 5% | 18447 | 100
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| B. HOIST WORKS | 922350 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 783997.5 | [6 empty] | 100% | 783997.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 92235 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 92235 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 46117.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 46117.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| ELECRICAL & INSTRUMENTATION WORK | 1844700 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1567995 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 1567995 | 100% | 1567995 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 90% | 166023 | 100% |  |  |  | 90% | 60% | 30% | 55341 | 90
| (iii) On completion of Testing of equipment |  |  | 92235 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 92235 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
4 | Sludge Thickener Area | [18 empty] | 0 |  |  |  | 0 | 0% | 18547000 | 18362530 | 99.01% | 0% | 0% | 0% | 0
| CIVIL WORK | 13012900 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 737880 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1106820 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation wall/base slab |  |  | 3689400 |  | 0 | 100% | 3689400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 | 60% | 1660230 | 40% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 | 40% | 737880 | 10% | 184470 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 90% | 90% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| SLUDGE THICKENER MECHANISM | 5534100 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4703985 | [7 empty] | 0 |  | 0 | 100% | 4703985 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 553410 | [7 empty] | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 276705 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 276705 | 100% | 276705 | 100% |  |  |  | 100% | 100% | 0% | 0
5 | Inlet / Stilling Chamber Area | [18 empty] | 0 |  |  |  | 0 | 0% | 6199000 | 6076020 | 98.02% | 0% | 0% | 0% | 0
| Site Clearance | 6199000 |  | 50000 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Column footing |  |  | 1229800 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Slab |  |  | 922350 |  | 0 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 50% | 614900 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Final finishing including Staircases,Railing,Shade,Painting, etc. |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 50% | 614900 | 40% | 491920 |  | 0 |  | 0 | 100% |  |  |  | 90% | 85% | 5% | 61490
6 | Manual & Mechanical Fine Bar Screen Chamber Area | 8658600 | [17 empty] | 0 |  |  |  | 0 | 0% | 8658600 | 8535620 | 98.58% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Slab |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 15.95% | 196164.88 | 84.05% | 1033635.12 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 245960 | 80% | 983840 | 70% | 860860 |  | 0 |  | 0 | 100% |  |  |  | 90% | 85% | 5% | 61490
7 | Grit Chamber (Mechanical Cleaned) & (Manually Cleaned) | 8658600 | [17 empty] | 0 |  |  |  | 0 | 0% | 25875800 | 25814317 | 99.76% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Slab |  |  | 1229800 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 45% | 553410 | 5% | 61490 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1106820 |  | 0 | 10% | 122980 | 10% | 122980 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 20% | 245960 | 30% | 368940 | 30% | 368940 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1106820 | 90% | 1106820 | 10% | 122980 | 5% | 61490 | 100% |  |  |  | 95% | 85% | 10% | 122980
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| A.MECHANICAL FINE SCREEN | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 | 100% | 2090660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% |  |  |  | 100% | 100% | 0% | 0
| B.MANUAL FINE SCREEN | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [7 empty] | 0 | 100% | 3135990 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 | 100% |  |  |  | 100% | 100% | 0% | 0
| C.GATES | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 2090660 | 100% | 2090660 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 245960 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% |  |  |  | 100% | 100% | 0% | 0
| D.CONVEYOR BELTS | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 | 100% | 2090660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 245960 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% |  |  |  | 100% | 100% | 0% | 0
| E. GRIT MECHANISM | 6149000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5226650 | [5 empty] | 0 | 100% | 5226650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 614900 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 614900 | 100% | 614900 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 100% | 307450 | 100% |  |  |  | 100% | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
8 | Flow Measurement Channel Area | 12348000 | [17 empty] | 0 |  |  |  | 0 | 0% | 12348000 | 12102040 | 98.01% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 50% | 922350 | 40% | 737880 |  | 0 | 10% | 184470 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Slab |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Wall |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 2213640 | 10% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1106820 | 10% | 122980 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 491920 | 80% | 1967680 | 70% | 1721720 |  | 0 |  | 0 | 100% |  |  |  | 90% | 70% | 20% | 491920
9 | Admin Bldg Area | 14857600 | [17 empty] | 0 |  |  |  | 0 | 0% | 33105340 | 32703635 | 98.79% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 368940 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 553410 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column footings/Foundation |  |  | 1844700 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 80% | 1475760 | 20% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground Floor Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 | 50% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| 1st Floor Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Roof Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 48% | 1328184 | 52% | 1438866 | 52% | 1438866 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 70% | 1291290 | 70% | 1291290 | 30% | 553410 | 20% | 368940 | 100% |  |  |  | 90% | 70% | 20% | 368940
| ELECTRICAL WORK | 8689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| LT/HT PANEL | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 7385990 | [6 empty] | 50% | 3692995 |  | 0 | 50% | 3692995 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1303410 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 1303410 | 100% | 1303410 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 434470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 434470 | 100% | 434470 | 100% |  |  |  | 100% | 100% | 0% | 0
| PLC/SCADA SYSTEM | 8689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 7385990 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 7385990 | 100% | 7385990 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1303410 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1303410 | 100% | 1303410 | 100% |  |  |  | 100% | 90% | 10% | 130341 | 100
| (iii) On completion of Testing of equipment |  |  | 434470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 434470 | 50% | 217235 | 100% |  |  |  | 50% | 0% | 50% | 217235 | 50
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
10 | Air Blower Room Area | 10092125 | [17 empty] | 0 |  |  |  | 0 | 0% | 20852875 | 20699150 | 99.26% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 100000 |  | 0 |  | 0 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 307450 |  | 0 |  | 0 | 50% | 153725 | 50% | 153725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 461175 |  | 0 |  | 0 | 50% | 230587.5 | 50% | 230587.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column footings/Foundation |  |  | 1537250 |  | 0 |  | 0 | 0% | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1537250 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 100% | 1537250 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23% | 353567.5 | 77% | 1183682.5 | 77% | 1183682.5 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 90% | 1383525 |  | 0 |  | 0 | 100% |  |  |  | 90% | 80% | 10% | 153725
| MECHANICAL WORK | 4611750 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| AIR BLOWER(PUMP) | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3919987.5 | [7 empty] | 0 |  | 0 |  | 0 | 30% | 1175996.25 | 30% | 1175996.25 | 70% | 2743991.25 | 70% | 2743991.25 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 461175 | [7 empty] | 0 |  | 0 |  | 0 | 30% | 138352.5 | 30% | 138352.5 | 70% | 322822.5 | 70% | 322822.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 230587.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 230587.5 | 100% | 230587.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| ELECTRICAL WORK | 6149000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| AIR BLOWER(MOTOR) | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5226650 | [7 empty] | 0 |  | 0 |  | 0 | 30% | 1567995 | 30% | 1567995 | 70% | 3658655 | 70% | 3658655 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 614900 | [7 empty] | 0 |  | 0 |  | 0 | 30% | 184470 | 30% | 184470 | 70% | 430430 | 70% | 430430 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 100% | 307450 | 100% |  |  |  | 100% | 100% | 0% | 0
11 | Staff Quarter Area | 8658600 | [17 empty] | 0 |  |  |  | 0 | 0% | 8658600 | 8572514 | 99.01% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 344344 |  | 0 |  | 0 | 100% | 344344 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 516516 |  | 0 |  | 0 | 100% | 516516 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 860860 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 430430 | 50% | 430430 | 50% | 430430 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electrical work |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 | 100% | 1291290 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 860860 | 90% | 774774 |  | 0 |  | 0 | 100% |  |  |  | 90% | 92% | -2% | -17217.2
12 | Guard Room Area | 3739400 | [17 empty] | 0 |  |  |  | 0 | 0% | 3739400 | 3709884.8 | 99.21% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 147576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 147576 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 221364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 221364 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 368940 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 368940 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electrical work |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 553410 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 92% | 339424.8 |  | 0 |  | 0 | 100% |  |  |  | 92% | 90% | 2% | 7378.8
13 | Sludge Dewatering System Area (Centrifuge Pump House, Sludge sump & Poly dosing tank) | 21621500 | [17 empty] | 0 |  |  |  | 0 | 0% | 30845000 | 30076375 | 97.51% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 100000 |  | 0 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 614900 |  | 0 | 100% | 614900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation |  |  | 1537250 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| 1st Column & Beam |  |  | 3074500 |  | 0 |  | 0 |  | 0 | 50% | 1537250 | 50% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground Floor Slab |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| 2nd Column & Beam |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 1229800 | 10% | 307450 | 50% | 1537250 | 50% | 1537250 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 | 100% | 3074500 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 | 100% | 3074500 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1537250 | 50% | 1537250 | 50% | 1537250 | 40% | 1229800 | 100% |  |  |  | 90% | 80% | 10% | 307450
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| CENTRIFUGE UNIT | 4611750 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3919987.5 | [7 empty] | 0 | 100% | 3919987.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 461175 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 461175 | 100% | 461175 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 230587.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 230587.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| CENTRIFUGE FEED PUMP | 3074500 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2613325 | [6 empty] | 100% | 2613325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 100% | 307450 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 153725 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 153725 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| POLY DOSING PUMPS | 1537250 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1306662.5 | [7 empty] | 0 |  | 0 | 100% | 1306662.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 153725 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 153725 | 100% | 153725 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 76862.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 76862.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
14 | Supernatant Recirculation Sump Area | 12040550 | [17 empty] | 0 |  |  |  | 0 | 0% | 18497000 | 17989707.5 | 97.26% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 737880 |  | 0 |  | 0 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1106820 |  | 0 |  | 0 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation wall/base slab |  |  | 2767050 |  | 0 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 |  | 0 | 40% | 1106820 | 60% | 1660230 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 |  | 0 | 90% | 2490345 | 10% | 276705 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Final finishing including Staircases,Railing,Shade,Painting etc. |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 |  | 0 | 40% | 737880 | 40% | 737880 | 10% | 184470 |  | 0 | 100% |  |  |  | 90% | 80% | 10% | 184470
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| PUMPING SYSTEM | 6456450 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5487982.5 | [7 empty] | 0 | 100% | 5487982.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 645645 | [7 empty] | 0 |  | 0 | 50% | 322822.5 | 50% | 322822.5 | 50% | 322822.5 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 322822.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 322822.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
15 | Transformer Yard Area | 1967680 | [17 empty] | 0 |  |  |  | 0 | 0% | 9223500 | 9186606 | 99.6% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 491920 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 491920 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Foundation Work |  |  | 737880 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 368940 | 50% | 368940 | 45% | 332046 |  | 0 |  | 0 | 100% |  |  |  | 95% | 80% | 15% | 110682
| ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| TRANSFORMER | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [6 empty] | 100% | 3135990 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 | 80% | 295152 | 20% | 73788 | 20% | 73788 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| CABLE & CABLE TRAY | 3566420 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3031457 | [7 empty] | 0 |  | 0 | 100% | 3031457 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 356642 | [7 empty] | 0 |  | 0 | 100% | 356642 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 178321 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 178321 | 100% | 178321 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
16 | DG Area | 1936935 | [17 empty] | 0 |  |  |  | 0 | 0% | 7747740 | 7650893.25 | 98.75% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 553410 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Foundation Work |  |  | 830115 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 830115 | 100% | 830115 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 276705 | 50% | 276705 | 50% | 276705 | 50% | 276705 | 100% |  |  |  | 100% | 100% | 0% | 0
| ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| DG SET | 3873870 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3292789.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 3292789.5 | 100% | 3292789.5 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 387387 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 387387 | 100% | 387387 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 193693.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 193693.5 | 50% | 96846.75 | 100% |  |  |  | 50% | 50% | 0% | 0
| CABLE & CABLE TRAY | 1936935 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1646394.75 | [7 empty] | 0 |  | 0 | 100% | 1646394.75 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 193693.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 193693.5 | 100% | 193693.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 96846.75 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 96846.75 | 100% | 96846.75 | 100% |  |  |  | 100% | 100% | 0% | 0
17 | Sludge Storage Platform | 800000 | [17 empty] | 0 |  |  |  | 0 | 0% | 800000 | 700000 | 87.5% | 0% | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 | 100% | 300000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Foundation Work |  |  | 400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 400000 | 100% | 400000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing work |  |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 50% | 50000 | 100% |  |  |  | 50% | 0% | 50% | 50000
18 | EXTERNAL DEVELOPMENT | 43345000 | [17 empty] | 0 |  |  |  | 0 | 0% | 43345000 | 40030279.43 | 92.35% | 0% | 0% | 0% | 0
A. | Roads, Storm Water Drain & Miscellaneous work |  |  | 12600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9.04% | 1138649.43 | 60.96% | 7681350.57 | 61% | 7686000 | 30% | 3780000 | 10% | 1260000 | 100% |  |  |  | 80.04% | 70.04% | 10% | 1260000
B. | Compound Wall with Gate |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 6149000 | 40% | 2459600 | 28.5% | 1752465 | 31.5% | 1936935 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Column footing |  |  | 6149000 | 40% | 2459600 | 20% | 1229800 | 30% | 1844700 | 5% | 307450 | 5% | 307450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Column & Beam |  |  | 6149000 | 40% | 2459600 | 20% | 1229800 | 28% | 1721720 | 7% | 430430 | 5% | 307450 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 6149000 |  | 0 | 25% | 1537250 | 23% | 1414270 | 32% | 1967680 | 10% | 614900 |  | 0 | 10% | 614900 | 7% | 430430 |  | 0 |  | 0 | 100% |  |  |  | 97% | 95% | 2% | 122980
| Finishing Work |  |  | 6149000 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 2459600 | 30% | 1844700 | 30% | 1844700 | 20% | 1229800 |  | 0 |  | 0 | 100% |  |  |  | 90% | 80% | 10% | 614900
19 | MPS-2 ( 115MLD) | [18 empty] | 0 |  |  |  | 0 | 0% | 74348360 | 74268458.75 | 99.89% | 0% | 0% | 0% | 0
| CIVIL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 29553660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 3451734 | 15% | 517760.1 | 85% | 2933973.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 2301156 |  | 0 | 100% | 2301156 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 5752890 |  | 0 | 100% | 5752890 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 3835260 |  | 0 |  | 0 | 100% | 3835260 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 3835260 |  | 0 |  | 0 | 15% | 575289 | 35% | 1342341 | 7% | 268468.2 | 43% | 1649161.8 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 3835260 |  | 0 |  | 0 | 10% | 383526 | 40% | 1534104 | 30% | 1150578 | 20% | 767052 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground Floor Slab |  |  | 3835260 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3835260 | 100% | 3835260 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 2556840 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556840 | 100% | 2556840 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 8572800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 681824 |  | 0 |  | 0 | 100% | 681824 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1022736 |  | 0 |  | 0 | 100% | 1022736 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 25% | 426140 | 72% | 1227283.2 | 3% | 51136.8 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
C | Construction of Raw Sewage Pump House | 6392100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Column & Beam |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 639210 | 60% | 958815 | 60% | 958815 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Roof Slab |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 | 100% | 1598025 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10% | 159802.5 | 70% | 1118617.5 | 70% | 1118617.5 | 20% | 319605 | 20% | 319605 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 | 95% | 1518123.75 | 100% |  |  |  | 95% | 80% | 15% | 239703.75
D | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Coarese Screen mechanical & manual | 5326750 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4527737.5 | [7 empty] | 0 | 25% | 1131934.375 | 75% | 3395803.125 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 532675 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 532675 | 100% | 532675 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 266337.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 266337.5 | 100% | 266337.5 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Piping & Support work | 5326750 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4527737.5 | [7 empty] | 0 | 75% | 3395803.125 | 25% | 1131934.375 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 532675 | [7 empty] | 0 |  | 0 | 75% | 399506.25 | 25% | 133168.75 | 25% | 133168.75 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 266337.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 266337.5 | 100% | 266337.5 | 100% |  |  |  | 100% | 0% | 100% | 266337.5 | 100
| Gate Work | 7457450 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 6338832.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 6338832.5 | 100% | 6338832.5 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 745745 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 745745 | 100% | 745745 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 372872.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 372872.5 | 100% | 372872.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Pumps | 11718850 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 9961022.5 | [7 empty] | 0 | 100% | 9961022.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1171885 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 1171885 | 100% | 1171885 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 585942.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 585942.5 | 100% | 585942.5 | 100% |  |  |  | 100% | 100% | 0% | 0
20 | ICI Nala IPS | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| CIVIL |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 16764000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 16764000 | 16252800 | 96.95% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 1533600 |  | 0 | 100% | 1533600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1022400 |  | 0 | 100% | 1022400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft | 2556000 |  | 2556000 |  | 0 | 50% | 1278000 | 50% | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2556000 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 1022400 |  | 0 |  | 0 |  | 0 | 60% | 1533600 | 60% | 1533600 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground Floor Slab |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 2556000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1278000 | 60% | 766800 | 100% |  |  |  | 60% | 60% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 4310000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 4310000 | 4054400 | 94.07% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 340800 |  | 0 |  | 0 |  | 0 | 100% | 340800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 511200 |  | 0 |  | 0 |  | 0 | 100% | 511200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 852000 |  | 0 |  | 0 |  | 0 | 100% | 852000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 852000 |  | 0 |  | 0 |  | 0 | 10% | 85200 | 90% | 766800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 852000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 852000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 426000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing work |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 40% | 170400 | 100% |  |  |  | 40% | 40% | 0% | 0
C | Construction of Raw Sewage Pump House | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 3196050 | 2397037.5 | 75% | 0% | 0% | 0% | 0
| Column & Beam |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Roof Slab |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
D | Construction of Office Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130000 | 1704000 | 80% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 | 100% | 639000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 127800 | 60% | 127800 | 40% | 85200 | 40% | 85200 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
E | Construction of Guard Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130000 | 1704000 | 80% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 | 100% | 639000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
F | Transformer Yard,DG Yard | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 | 100% | 3196050 | 2237235 | 70% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 639210 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639210 | 100% | 639210 | 100% |  |  |  | 100% | 100% | 0% | 0
| Foundation Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 | 100% | 1598025 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 958815 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958815 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
G | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 7883590 | 7713134 | 97.84% | 0% | 0% | 0% | 0
| Piping & Support work | 1065350 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 905547.5 | [7 empty] | 0 | 30% | 271664.25 |  | 0 | 70% | 633883.25 | 70% | 633883.25 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 106535 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 106535 | 100% | 106535 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 53267.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 53267.5 | 100% | 53267.5 | 100% |  |  |  | 100% | 0% | 100% | 53267.5 | 100
| Screen Channel | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Pumps | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% |  |  |  | 100% | 20% | 80% | 136364.8 | 100
H | ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 7031310 | 6443236.8 | 91.64% | 0% | 0% | 0% | 0
| Cable Tray & Earthing Work | 1278420 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1086657 | [7 empty] | 0 |  | 0 | 50% | 543328.5 |  | 0 |  | 0 | 50% | 543328.5 | 50% | 543328.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 127842 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 127842 | 90% | 115057.8 | 100% |  |  |  | 90% | 90% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 63921 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 63921 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Transformer | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 2897752 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| DG | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1992204.5 | 100% | 1992204.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 | 100% | 234377 | 100% |  |  |  | 100% | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 | 100% | 117188.5 | 100% |  |  |  | 100% | 100% | 0% | 0
I | Construction of Boundary wall & Internal Road | 1704560 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130700 | 1309315.15 | 61.45% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation & PCC |  |  | 319605 |  | 0 |  | 0 |  | 0 | 30% | 95881.5 | 40% | 127842 |  | 0 | 10% | 31960.5 | 10% | 31960.5 | 20% | 63921 | 17% | 54332.85 | 100% |  |  |  | 97% | 97% | 0% | 0
| RCC Column footing |  |  | 426140 |  | 0 |  | 0 |  | 0 | 33% | 140626.2 | 35% | 149149 |  | 0 | 2% | 8522.8 | 2% | 8522.8 | 30% | 127842 | 27% | 115057.8 | 100% |  |  |  | 97% | 97% | 0% | 0
| RCC Column & Beam |  |  | 319605 |  | 0 |  | 0 |  | 0 | 20% | 63921 | 48% | 153410.4 |  | 0 | 2% | 6392.1 | 2% | 6392.1 | 30% | 95881.5 | 20% | 63921 | 100% |  |  |  | 90% | 90% | 0% | 0
| Brickwork & Plaster |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 | 45% | 143822.25 |  | 0 |  | 0 |  | 0 | 55% | 175782.75 | 35% | 111861.75 | 100% |  |  |  | 80% | 80% | 0% | 0
| Finishing |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Construction of Internal road |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426140 | 10% | 42614 | 100% |  |  |  | 10% | 0% | 10% | 42614
21 | IPS-6 (Sundar Nagar- 20 MLD)-Pankha Area | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| CIVIL |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 16764000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 16764000 | 15486000 | 92.38% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation |  |  | 1533600 | 11% | 168696 | 89% | 1364904 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| PCC |  |  | 1022400 |  | 0 | 100% | 1022400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 2556000 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2556000 |  | 0 |  | 0 | 90% | 2300400 | 10% | 255600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 40% | 1022400 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 1533600 | 60% | 1533600 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 25% | 639000 | 20% | 511200 | 55% | 1405800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Ground Floor Slab |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 2556000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1278000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130000 | 1917000 | 90% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation & PCC |  |  | 426000 |  | 0 |  | 0 | 70% | 298200 | 30% | 127800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 426000 |  | 0 |  | 0 |  | 0 | 80% | 340800 | 20% | 85200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 426000 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 127800 | 70% | 298200 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Walkway/Platform |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
C | Construction of Raw Sewage Pump House | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 3196050 | 2357086.875 | 73.75% | 0% | 0% | 0% | 0
| Column & Beam |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Roof Slab |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brickwork & Plaster |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 95% | 759061.875 | 100% |  |  |  | 95% | 50% | 45% | 359555.625
| Finishing Work |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
D | Construction of Office Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130000 | 1693350 | 79.5% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 | 100% | 639000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 95% | 202350 | 100% |  |  |  | 95% | 50% | 45% | 95850
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
E | Construction of Guard Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130000 | 1661400 | 78% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 | 100% | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 | 50% | 106500 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 106500 | 50% | 106500 | 100% |  |  |  | 100% | 50% | 50% | 106500
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 0% | 100% | 213000
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% |  |  |  | 100% | 0% | 100% | 213000
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 80% | 170400 | 100% |  |  |  | 80% | 0% | 80% | 170400
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
F | Transformer Yard,DG Yard | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 3196050 | 2237235 | 70% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 639210 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639210 | 100% | 639210 | 100% |  |  |  | 100% | 100% | 0% | 0
| Foundation Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 | 100% | 1598025 | 100% |  |  |  | 100% | 100% | 0% | 0
| Finishing Work |  |  | 958815 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958815 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
G | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 8096660 | 6984434.6 | 86.26% | 0% | 0% | 0% | 0
| Piping & Support work | 1278420 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1086657 | [7 empty] | 0 | 25% | 271664.25 |  | 0 | 75% | 814992.75 | 75% | 814992.75 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 127842 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 127842 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 63921 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 63921 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Screen Channel | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 30% | 102273.6 | 100% |  |  |  | 30% | 0% | 30% | 102273.6 | 30
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Pumps | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
H | ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 8096660 | 6882161 | 85% | 0% | 0% | 0% | 0
| Cable Tray & Earthing Work | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 | 50% | 996102.25 |  | 0 |  | 0 | 50% | 996102.25 | 50% | 996102.25 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Transformer | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 2897752 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| DG | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1992204.5 | 100% | 1992204.5 | 100% |  |  |  | 100% | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
I | Construction of Boundary wall & Internal Road | 2130700 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 2130700 | 383526 | 18% | 0% | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Excavation & PCC |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 | 50% | 159802.5 | 100% |  |  |  | 50% | 50% | 0% | 0
| RCC Column footing |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426140 | 30% | 127842 | 100% |  |  |  | 30% | 30% | 0% | 0
| RCC Column & Beam |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 | 30% | 95881.5 | 100% |  |  |  | 30% | 30% | 0% | 0
| Brickwork & Plaster |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Construction of Internal road |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426140 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Finishing |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
22 | I&D Works | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
A | ICI Nala | 5560000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 5560000 | 4670400 | 84% | 0% | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 13% | 289120 | 81% | 1801440 | 6% | 133440 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1112000 | 100% | 1112000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 1000800 | 60% | 1000800 | 40% | 667200 | 20% | 333600 | 100% |  |  |  | 80% | 80% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
B | Thermal Nala -A | 5560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 5560000 | 5560000 | 100% | 0% | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 13% | 289120 | 30% | 667200 | 30% | 667200 | 10% | 222400 | 17% | 378080 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 667200 | 40% | 444800 | 40% | 444800 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1668000 | 100% | 1668000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 | 100% | 556000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
C | Thermal Nala -B | 5560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 5560000 | 3558400 | 64% | 0% | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 14% | 311360 |  | 0 |  | 0 | 5% | 111200 |  | 0 | 31% | 689440 | 31% | 689440 | 50% | 1112000 | 50% | 1112000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1112000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 667200 | 40% | 667200 | 60% | 1000800 | 40% | 667200 | 100% |  |  |  | 80% | 80% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
23 | Rising Main Works | [18 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
A | ICI Nala Area | 6000000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 6000000 | 5677314.82 | 94.62% | 0% | 0% | 0% | 0
| Site Cleance from Client |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Supply of Pipes |  |  | 5100000 |  | 0 |  | 0 | 5.55% | 283314.82 | 44% | 2244000 | 25% | 1275000 |  | 0 | 11.26% | 573995.18 | 11% | 561000 | 14.19% | 723690 | 14% | 714000 | 100% |  |  |  | 99.55% | 99.55% | 0% | 0
| Excavation,Laying & backfilling of Pipes |  |  | 600000 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 360000 |  | 0 |  | 0 |  | 0 | 40% | 240000 | 40% | 240000 | 100% |  |  |  | 100% | 100% | 0% | 0
| Testing |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
B | Sundar Nagar IPS Area | 6000000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 6000000 | 5490000 | 91.5% | 0% | 0% | 0% | 0
| Site Cleance from Client |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Supply of Pipes |  |  | 5100000 |  | 0 |  | 0 |  | 0 | 100% | 5100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation,Laying & backfilling of Pipes |  |  | 600000 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 360000 |  | 0 |  | 0 |  | 0 | 40% | 240000 | 5% | 30000 | 100% |  |  |  | 65% | 65% | 0% | 0
| Testing |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
24 | Sewer System Area (RCC Pipes-NP3 Types) | 200567840 | [21 empty] | 0 | 0% | 200567840 | 188191504.556 | 93.83% | 0% | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 | [11 empty] | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Supply of pipes |  |  | 160454272 | 16% | 25670093.9 | 25% | 40120136.1 | 29% | 46531738.88 | 13% | 20859055.36 | 8.5% | 13638613.12 | 0.5% | 802271.36 | 8% | 12832363.28 | 8% | 12836341.76 |  | 0 |  | 0 | 100% |  |  |  | 100% | 99% | 1% | 1604542.72
| Excavation and Laying of pipes including bed preperation & backfilling |  |  | 10028392 |  | 0 |  | 0 | 15% | 1504258.8 | 14% | 1403974.88 | 20.55% | 2060570.556 | 27.45% | 2753057.604 | 7% | 701987.44 | 7% | 701987.44 | 16% | 1604542.72 | 10% | 1002839.2 | 100% |  |  |  | 94% | 89% | 5% | 501419.6
| Manholes |  |  | 10028392 |  | 0 |  | 0 |  | 0 | 34% | 3409653.28 | 6% | 601703.52 | 11.55% | 1158015.276 | 12.07% | 1210247.9144 | 12% | 1203407.04 | 36.38% | 3649004.0096 | 26% | 2607381.92 | 100% |  |  |  | 89.55% | 83.55% | 6% | 601703.52
| Testing |  |  | 10028392 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 10028392 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| Road Restoration work |  |  | 10028392 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 35.38% | 3547990.0896 | 35% | 3509937.2 | 64.62% | 6480401.9104 | 58% | 5816467.36 | 100% |  |  |  | 93% | 85% | 8% | 802271.36
25 | Design ,Supply,Testing & Commissioning of Sewer line (crossing National Highway-2 & Railway Track) | 18747225 | [21 empty] | 0 | 0% | 18747225 | 18278544.375 | 97.5% | 0% | 0% | 0% | 0
| Statutory approvals from Railway & Road dept |  |  |  |  | 0 |  | 0 |  | 0 | 50% | [8 empty] | 0 |  |  |  | 0 | 50% |  |  |  | 50% | 50% | 0% | 0
| Supply of Carrier & Casing Pipes |  |  | 11248335 |  | 0 |  | 0 |  | 0 | 57% | 6411550.95 | 30% | 3374500.5 |  | 0 | 13% | 1462283.55 | 13% | 1462283.55 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Construction of Pit |  |  | 937361.25 |  | 0 |  | 0 |  | 0 | 65% | 609284.8125 |  | 0 |  | 0 | 35% | 328076.4375 | 35% | 328076.4375 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Excavation & Laying of Pipes thru Jack push method |  |  | 5624167.5 |  | 0 |  | 0 |  | 0 | 50% | 2812083.75 |  | 0 |  | 0 | 50% | 2812083.75 | 50% | 2812083.75 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Testing |  |  | 937361.25 |  | 0 |  | 0 |  | 0 |  | 0 | 27% | 253087.5375 |  | 0 | 23% | 215593.0875 | 23% | 215593.0875 | 50% | 468680.625 |  | 0 | 100% |  |  |  | 50% | 50% | 0% | 0
26 | Design ,Supply,Testing & Commissioning of Treated Effulent line from STP to River Pandu | 8000000 | [17 empty] | 0 |  |  |  | 0 | 0% | 8000000 | 7200000 | 90% | 0% | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% |  |  |  | 0% | 0% | 0% | 0
| Construction of Effluent line from STP to River Pandu |  |  | 7200000 |  | 0 |  | 0 |  | 0 |  | 0 | 35% | 2520000 | 25% | 1800000 | 40% | 2880000 | 40% | 2880000 |  | 0 |  | 0 | 100% |  |  |  | 100% | 100% | 0% | 0
| Testing |  |  | 800000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 800000 |  | 0 |  | 0 |  | 0 | 100% |  |  |  | 0% | 0% | 0% | 0
| TRIAL RUN & COMMISSIONING | [16 empty] | 0 | [6 empty] | 0% | [5 empty] | 0% | 0
| Trial Run & Commissioning | [16 empty] | 0 | [6 empty] | 0% | [5 empty] | 0% | 0
| Total Amount | 999728920 |  | 998718000 |  | 124839750 |  | 124839750 |  | 124839750 |  | 124839750.0025 |  | 124839750.3935 |  | 124839750 |  | 124839749.999 |  | 121887530.965 |  | 124839749.765 |  | 89266423.905 |  | 998718000 | 960142462.266 | 96.14%
Note:- Item rates will be remaining same. But billable items may be interchanged at actual during billing.
| 1st milestone |  |  |  | = | 124839750
| 2nd milestone |  |  |  | = | 124839750
| 3rd Milestone |  |  |  | = | 124839750
| 4th Milestone |  |  |  | = | 124839750.0025
| 5th Milestone |  |  |  | = | 124839750.3935
| 6th Milestone |  |  |  | = | 124839750
| 7th Milestone |  |  |  | = | 121887530.965
| 8th Milestone |  |  |  | = | 89266423.905
| Total Amount |  |  |  | = | 960192455.266
| Total % as on 30.04.2023 |  |  |  | = | 96.14%