## Shuklaganj
DETAILS OF PAYMENT MILESTONE FOR 05 MLD SHUKLAGANJ SITE
Sr. No. | Description of Items | Amount | % | Proposed BOQ Amount | Milestone-1 (From 15th March.'21 to 1st Sep'21) |  | Milestone-2 (From 2nd Sep'21 to 27th Dec'21 ) |  | Milestone-3 (From 28th Dec'21 to 04th April'22 ) |  | Milestone-4 (From 05th April'22 to 29th June'22 ) |  | Milestone-5 (From 30th June'22 to 13th Dec'22 ) |  | Achieved for 5th Milestone |  | Milestone-6 (From 14th Dec'22 to 13th Feb'23 ) |  | Achieved for 6th Milestone |  | Milestone-7 (From 14th Feb'23 to 13th Apr'23) |  | Achieved for 7th Milestone |  | Milestone-8 (From 14th Apr'23 to 13th June'23 ) |  | Achieved for 8th Milestone |  | Cumulative Achieved | Upto October'23 | For November'23
[5 empty] | % | Amount | % | Amount | % | Amount | % | Amount | % | Amount |  |  | % | Amount |  |  | % | Amount |  |  | % | Amount
[6 empty] | 26618774.9056 |  | 26618774.6155 |  | 26618774.8095 |  | 26618774.9974 |  | 26618775.0441 |  |  |  | 26618774.6725 |  |  |  | 26622683.5125 |  |  |  | 26618775.4425
I | Design & Drawing of STP | 10647510
1 | On approval of BEP |  | 50% | 5323755 | 100% | 5323755 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | On approval of design & drawings for Civil & Sewerage works |  | 50% | 5323755 | 90% | 4791379.5 |  | 0 | 10% | 532375.5 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
[29 empty] | 0% | 0% | 0%
II | CONSTRUCTION | [27 empty] | 0% | 0% | 0%
A | SHUKLAGANJ STP (5 MLD) | 106475100 | [26 empty] | 0% | 0% | 0%
i) | SBR Basin Area | 23956898 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 479137.96 | 100% | 479137.96 | 0% |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation wall footing |  | 8% | 1916551.84 | 60% | 1149931.104 | 40% | 766620.736 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC wall footing |  | 10% | 2395689.8 |  | 0 | 53% | 1268992.594 | 47% | 1126697.206 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/Raft of wall |  | 12% | 2874827.76 |  | 0 |  | 0 | 100% | 2874827.76 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total upto base slab |  | 10% | 2395689.8 |  | 0 |  | 0 | 100% | 2395689.8 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of upto base slab) |  | 10% | 2395689.8 |  | 0 |  | 0 | 100% | 2395689.8 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | PCC Base Slab |  | 15% | 3593534.7 |  | 0 |  | 0 |  | 0 | 100% | 3593534.7 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | RCC Foundation base slab |  | 11% | 2635258.78 |  | 0 |  | 0 |  | 0 | 66.1% | 1741906.0536 | 33.9% | 893352.7264 | 34% | 893352.7264 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100.1% | 100.1% | 0%
9 | Wall 50% of total lift work |  | 10% | 2395689.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 2395689.8 | 100% | 2395689.8 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
10 | Walls (balance 50% of Total Lift work) |  | 7% | 1676982.86 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 1676982.86 | 100% | 1676982.86 |  | 0 |  |  | 100% | 100% | 0%
11 | Hydro Testing /Finishing works |  | 5% | 1197844.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 1197844.9 |  | 0 | 0% | 0% | 0%
ii | Chlorination Tank Area | 2395690 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 311439.7 |  | 0 |  |  | 100% | 311439.7 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 359353.5 |  | 0 |  | 0 | 100% | 359353.5 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/Raft |  | 25% | 598922.5 |  | 0 |  | 0 | 100% | 598922.5 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total lift work |  | 15% | 359353.5 |  | 0 |  | 0 |  | 0 | 80% | 287482.8 | 20% | 71870.7 | 20% | 71870.7 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of Total Lift work) |  | 20% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 479138 | 100% | 479138 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Baffle Walls work |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 | 100% | 119784.5 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Hydro Testing /Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
iii | Chlorination Room Area | 2395690 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 8% | 191655.2 |  | 0 |  | 0 | 100% | 191655.2 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 10% | 239569 |  | 0 |  | 0 | 100% | 239569 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/Column footing |  | 25% | 598922.5 |  | 0 |  | 0 | 50% | 299461.25 | 50% | 299461.25 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 359353.5 |  | 0 |  | 0 |  | 0 | 80% | 287482.8 | 20% | 71870.7 | 20% | 71870.7 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Ground floor Slab |  | 10% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 239569 | 100% | 239569 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Roof Slab |  | 15% | 359353.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 359353.5 | 100% | 359353.5 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Brickwork |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 | 100% | 119784.5 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
9 | Plaster |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 119784.5 | 100% | 119784.5 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
10 | Testing/Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 50% | 59892.25 | 50% | 59892.25 | 50% | 59892.25 |  |  |  | 0 |  |  | 50% | 50% | 0%
iv | Guard Room Area | 1676983 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 33539.66 | 100% | 33539.66 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 8% | 134158.64 | 100% | 134158.64 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 10% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/column footing |  | 10% | 167698.3 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 251547.45 | 100% | 251547.45 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Ground floor Slab |  | 15% | 251547.45 |  | 0 |  | 0 | 100% | 251547.45 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | RCC Roof Slab |  | 5% | 83849.15 |  | 0 |  | 0 | 100% | 83849.15 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Brick work |  | 10% | 167698.3 |  | 0 |  | 0 |  | 0 | 100% | 167698.3 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
9 | Plumbing, fixtures |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  |  | 100% | 100% | 0%
10 | Sanitary works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  |  | 100% | 100% | 0%
11 | Electrification work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 83849.15 | 100% | 83849.15 | 100% | 100% | 0%
12 | Plaster |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
13 | Finishing works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 50% | 41924.575 | 50% | 41924.575 | 50% | 41924.575 |  |  |  | 0 |  |  | 50% | 30% | 20%
iv | Admin Bldg Area (G+1) | 5270517 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 105410.34 | 100% | 105410.34 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 5% | 263525.85 |  | 0 | 100% | 263525.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 7% | 368936.19 |  | 0 |  | 0 | 100% | 368936.19 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | Column footings/Foundation |  | 10% | 527051.7 |  | 0 |  | 0 | 100% | 527051.7 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam up to Floor Base slab |  | 15% | 790577.55 |  | 0 |  | 0 | 80% | 632462.04 | 20% | 158115.51 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Floor base Slab |  | 15% | 790577.55 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 790577.55 | 100% | 790577.55 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Column & Beam upto Roof Slab |  | 8% | 421641.36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 421641.36 | 100% | 421641.36 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | 1st Floor Roof Slab |  | 13% | 685167.21 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 685167.21 | 50% | 342583.605 |  | 0 |  |  |  | 0 |  |  | 50% | 50% | 0%
9 | Brickwork |  | 8% | 421641.36 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 421641.36 | 50% | 210820.68 |  | 0 |  |  | 50% | 50% | 0%
10 | Electrification, plumbing, fixtures , sanitary works |  | 7% | 368936.19 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 368936.19 |  |  |  | 0 |  |  | 0% | 0% | 0%
11 | Plaster |  | 5% | 263525.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 263525.85 | 40% | 105410.34 |  | 0 |  |  | 40% | 40% | 0%
12 | finishing works |  | 5% | 263525.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 50% | 131762.925 |  |  | 50% | 131762.925 |  |  | 0% | 0% | 0%
v | Air Blower Room Area | 4791380 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 95827.6 | 100% | 95827.6 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 8% | 383310.4 |  | 0 | 100% | 383310.4 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 718707 |  | 0 |  | 0 | 100% | 718707 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/column footing |  | 15% | 718707 |  | 0 |  | 0 | 100% | 718707 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 718707 |  | 0 |  | 0 | 80% | 574965.6 | 20% | 143741.4 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Roof Slab |  | 20% | 958276 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958276 | 50% | 479138 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 50% | 50% | 0%
7 | Cable Trench Work |  | 10% | 479138 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 479138 | 100% | 479138 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Brick work |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 239569 | 50% | 239569 |  | 0 |  |  |  | 0 |  |  | 50% | 50% | 0%
9 | Plaster |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 239569 | 40% | 239569 |  | 0 |  |  |  | 0 |  |  | 40% | 40% | 0%
10 | Testing/Finishing work |  | 5% | 239569 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 239569 |  |  |  | 0 |  |  | 0% | 0% | 0%
vi | Staff Quarter Area (G+1) | 1676983 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 33539.66 | 100% | 33539.66 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 8% | 134158.64 | 100% | 134158.64 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 10% | 167698.3 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/column footing |  | 10% | 167698.3 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam upto ground floor slab |  | 15% | 251547.45 |  | 0 |  | 0 | 100% | 251547.45 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Ground floor Slab (Base floor slab) |  | 10% | 167698.3 |  | 0 |  | 0 |  | 0 | 100% | 167698.3 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Column upto roof slab & RCC 1st floor Slab |  | 20% | 335396.6 |  | 0 |  | 0 |  | 0 | 100% | 335396.6 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Brick work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 | 50% | 41924.575 | 50% | 41924.575 | 50% | 41924.575 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
9 | Plumbing, fixtures , sanitary works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 83849.15 | 50% | 41924.575 |  | 0 |  |  | 50% | 50% | 0%
10 | Electrification work |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
11 | Plaster |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 83849.15 | 100% | 83849.15 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
12 | Finishing works |  | 5% | 83849.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 70% | 58694.405 | 30% | 25154.745 | 30% | 25154.745 |  |  | 30% | 30% | 0%
vii | Inlet Chamber Area | 1437414 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 28748.28 |  | 0 |  | 0 | 100% | 28748.28 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation & PCC |  | 13% | 186863.82 |  | 0 |  |  | 50% | 93431.91 | 50% | 93431.91 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Column footing |  | 15% | 215612.1 |  | 0 |  |  |  | 0 | 100% | 215612.1 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | Column & Beam |  | 25% | 359353.5 |  | 0 |  | 0 |  | 0 | 25.45% | 91455.4658 | 74.55% | 267898.0343 | 74.55% | 267898.0343 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | RCC Slab |  | 20% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 287482.8 | 50% | 143741.4 |  | 0 |  |  |  | 0 |  |  | 50% | 50% | 0%
6 | RCC Wall |  | 20% | 287482.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 287482.8 | 50% | 143741.4 |  | 0 |  |  |  | 0 |  |  | 50% | 50% | 0%
7 | Hydro Testing /Finishing works |  | 5% | 71870.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 70% | 50309.49 |  |  | 30% | 21561.21 |  |  | 0% | 0% | 0%
viii | Manual & Mechanica Fine Bar Screen Chamber AreaArea | 1437414 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 28748.28 |  | 0 |  | 0 | 100% | 28748.28 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 186863.82 |  | 0 |  |  | 100% | 186863.82 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 215612.1 |  | 0 |  |  |  | 0 | 100% | 215612.1 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 | 100% | 287482.8 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 215612.1 |  | 0 |  |  |  | 0 | 25.45% | 54873.2795 | 74.55% | 160738.8206 | 74.55% | 160738.8206 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Slab |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 287482.8 | 60% | 172489.68 |  | 0 |  |  |  | 0 |  |  | 60% | 60% | 0%
7 | RCC Wall |  | 5% | 71870.7 |  | 0 |  |  |  | 0 | 60% | 43122.42 |  | 0 |  |  | 40% | 28748.28 | 20% | 14374.14 |  | 0 |  |  |  | 0 |  |  | 80% | 60% | 20%
8 | Walkway/Platform |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 71870.7 | 60% | 43122.42 |  | 0 |  |  |  | 0 |  |  | 60% | 50% | 10%
9 | Hydro Testing /Finishing works |  | 5% | 71870.7 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 71870.7 |  |  | 0% | 0% | 0%
ix | Grit Chamber Area | 3114397 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 62287.94 |  | 0 |  | 0 | 100% | 62287.94 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 404871.61 |  | 0 |  |  | 100% | 404871.61 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 467159.55 |  | 0 |  |  |  | 0 | 100% | 467159.55 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation |  | 20% | 622879.4 |  | 0 |  |  |  | 0 | 100% | 622879.4 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 467159.55 |  | 0 |  |  |  | 0 | 25.42% | 118751.9576 | 74.58% | 348407.5924 | 74.58% | 348407.5924 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Slab |  | 20% | 622879.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 622879.4 | 100% | 622879.4 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | RCC Wall |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 155719.85 | 60% | 93431.91 |  | 0 |  |  |  | 0 |  |  | 60% | 50% | 10%
8 | Walkway/Platform |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 155719.85 | 60% | 93431.91 |  | 0 |  |  |  | 0 |  |  | 60% | 50% | 10%
9 | Hydro Testing /Finishing works |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 70% | 109003.895 |  |  | 30% | 46715.955 |  |  | 0% | 0% | 0%
x | Parshall Flume Channel Area | 3114397 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 62287.94 |  | 0 |  | 0 | 100% | 62287.94 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 404871.61 |  | 0 |  |  | 60% | 242922.966 |  | 0 | 40% | 161948.644 | 40% | 161948.644 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam |  | 15% | 467159.55 |  | 0 |  |  |  | 0 |  | 0 | 100% | 467159.55 | 100% | 467159.55 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | RCC Slab |  | 20% | 622879.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 622879.4 | 100% | 622879.4 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | RCC Wall |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 155719.85 | 60% | 93431.91 |  | 0 |  |  |  | 0 |  |  | 60% | 50% | 10%
8 | Walkway/Platform |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 155719.85 | 60% | 93431.91 |  | 0 |  |  |  | 0 |  |  | 60% | 50% | 10%
9 | Piping & fitting Work |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 155719.85 |  |  |  | 0 |  |  | 0% | 0% | 0%
10 | Hydro Testing /Finishing works |  | 5% | 155719.85 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 70% | 109003.895 |  |  | 30% | 46715.955 |  |  | 0% | 0% | 0%
xi | Sludge Dewatering System Area (Centrifuge Pump House, Sludge sump & Poly dosing tank) | 4312242 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 86244.84 |  | 0 |  | 0 | 100% | 86244.84 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215612.1 | 100% | 215612.1 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 8% | 344979.36 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 344979.36 | 100% | 344979.36 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 431224.2 | 100% | 429520.2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Column & Beam Upto First Floor |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | First Floor Slab |  | 15% | 646836.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 646836.3 | 100% | 646836.3 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Column & Beam First Floor to Roof Slab |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Roof Slab |  | 15% | 646836.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 646836.3 | 30% | 194050.89 |  | 0 |  |  | 30% | 30% | 0%
9 | Brickwork |  | 10% | 431224.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 431224.2 | 30% | 129367.26 |  | 0 |  |  | 30% | 30% | 0%
10 | Plaster |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 215612.1 | 30% | 64683.63 |  | 0 |  |  | 30% | 30% | 0%
11 | Piping & fiittings Work |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 50% | 107806.05 |  | 0 | 50% | 107806.05 |  |  | 0% | 0% | 0%
12 | Hydro Testing /Finishing works |  | 5% | 215612.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 215612.1 |  |  | 0% | 0% | 0%
xii | Sludge Thickener Area | 3353966 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 67079.32 | 100% | 67079.32 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 436015.58 | 100% | 436015.58 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 503094.9 | 100% | 503094.9 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation Wall/base slab |  | 25% | 838491.5 |  | 0 | 100% | 838491.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total lift work |  | 20% | 670793.2 |  | 0 |  |  | 100% | 670793.2 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of Total Lift work) |  | 20% | 670793.2 |  | 0 |  |  | 80% | 536634.56 | 8% | 53663.456 | 12% | 80495.184 | 12% | 80495.184 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Hydro Testing /Finishing works |  | 5% | 167698.3 |  | 0 |  |  |  | 0 |  | 0 | 100% | 167698.3 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
xiii | Supernatant Sump Area | 2395690 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 47913.8 | 100% | 47913.8 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 13% | 311439.7 |  | 0 | 100% | 311439.7 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 359353.5 |  | 0 | 100% | 359353.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation wall/base slab |  | 25% | 598922.5 |  | 0 | 100% | 598922.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total lift work |  | 20% | 479138 |  | 0 | 100% | 479138 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of Total Lift work) |  | 20% | 479138 |  | 0 |  | 0 | 100% | 479138 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Hydro Testing /Finishing works |  | 5% | 119784.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 119784.5 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
xiv | Sludge Storage Platform Area | 1916552 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 5% | 95827.6 |  | 0 |  |  | 100% | 95827.6 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 20% | 383310.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 383310.4 | 100% | 383310.4 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 30% | 574965.6 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 574965.6 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
4 | Foundation Work |  | 40% | 766620.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 766620.8 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
5 | Finishing work |  | 5% | 95827.6 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 95827.6 |  |  |  | 0 |  |  | 0% | 0% | 0%
xv | Transformer Yard Area | 1437414 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 5% | 71870.7 |  | 0 |  |  | 100% | 71870.7 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 | 100% | 287482.8 | 100% | 287482.8 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 30% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | Foundation Work |  | 45% | 646836.3 |  | 0 |  |  |  | 0 |  | 0 | 100% | 646836.3 | 100% | 646836.3 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
xvi | DG Shed Area | 1437414 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 5% | 71870.7 |  | 0 |  |  | 100% | 71870.7 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 20% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 | 100% | 287482.8 | 100% | 287482.8 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 30% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | Foundation Work |  | 45% | 646836.3 |  | 0 |  |  |  | 0 |  | 0 | 100% | 646836.3 | 100% | 646836.3 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
xvii | EXTERNAL DEVELOPMENT | 17997165 | [26 empty] | 0% | 0% | 0%
| Boundary Wall with Gate |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
1 | Site Clearance |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
2 | Excavation |  | 15% | 2699574.75 | 50% | 1349787.375 | 5% | 134978.7375 | 6% | 161974.485 |  | 0 |  | 0 |  |  |  | 0 |  |  | 20% | 539914.95 | 20% | 539914.95 | 19% | 512919.2025 | 14% | 377940.465 | 95% | 95% | 0%
3 | PCC |  | 20% | 3599433 | 50% | 1799716.5 |  | 0 | 2% | 71988.66 |  | 0 |  | 0 |  |  |  | 0 |  |  | 20% | 719886.6 | 20% | 719886.6 | 28% | 1007841.24 | 18% | 647897.94 | 90% | 90% | 0%
4 | RCC Column footing |  | 20% | 3599433 | 50% | 1799716.5 |  | 0 | 2% | 71988.66 |  | 0 |  | 0 |  |  |  | 0 |  |  | 25% | 899858.25 | 25% | 899858.25 | 23% | 827869.59 | 13% | 467926.29 | 90% | 90% | 0%
5 | RCC Column & Beam |  | 15% | 2699574.75 | 26% | 701889.435 | 10% | 269957.475 | 7% | 188970.2325 |  | 0 |  | 0 |  |  |  | 0 |  |  | 25% | 674893.6875 | 25% | 674893.6875 | 32% | 863863.92 | 22% | 593906.445 | 90% | 90% | 0%
6 | Brickwork |  | 15% | 2699574.75 |  | 0 | 10% | 269957.475 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 40% | 1079829.9 | 40% | 1079829.9 | 50% | 1349787.375 | 40% | 1079829.9 | 90% | 90% | 0%
7 | Plaster |  | 10% | 1799716.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 50% | 899858.25 | 50% | 899858.25 | 50% | 899858.25 | 20% | 359943.3 | 70% | 60% | 10%
8 | Finishing Work |  | 5% | 899858.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 30% | 274506.475 | 30% | 269957.475 | 70% | 625351.775 | 30% | 269957.475 | 60% | 60% | 0%
| Earthfilling, Internal Roads ,Landscaping |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
1 | Earthfilling, Internal Roads ,Landscaping | 3353966 | 100% | 3353966 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 50% | 1683644 |  | 0 | 50% | 1670321 |  |  | 0% | 0% | 0%
B | MPS-20 MLD | [27 empty] | 0% | 0% | 0%
| Civil Work | [27 empty] | 0% | 0% | 0%
i | Construction of Raw Sewage Sump | 8582759 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 171655.18 | 100% | 171655.18 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 10% | 858275.9 | 40% | 343310.36 | 60% | 514965.54 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 1287413.85 |  | 0 | 100% | 1287413.85 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/Raft |  | 20% | 1716551.8 |  | 0 | 100% | 1716551.8 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total lift work |  | 15% | 1287413.85 |  | 0 |  | 0 | 100% | 1287413.85 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of Total Lift work) |  | 15% | 1287413.85 |  | 0 |  | 0 |  | 0 | 80% | 1029931.08 | 15% | 193112.0775 | 15% | 193112.0775 | 5% | 64370.6925 | 5% | 64370.6925 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Column & Beam |  | 10% | 858275.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 858275.9 | 100% | 858275.9 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Ground Floor Slab |  | 8% | 686620.72 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 686620.72 | 100% | 686620.72 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
9 | Hydro Testing /Finishing works |  | 5% | 429137.95 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 10% | 42913.795 |  | 0 | 90% | 386224.155 |  | 0 |  | 0 |  |  | 0% | 0% | 0%
ii | Construction of Raw Sewage Pump House | 1000000 | [26 empty] | 0% | 0% | 0%
1 | Column & Beam |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 250000 | 100% | 250000 |  | 0 |  |  | 100% | 100% | 0%
2 | Roof Slab |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 250000 |  | 0 |  | 0 |  |  | 0% | 0% | 0%
3 | Brickwork |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 250000 |  | 0 |  | 0 |  |  | 0% | 0% | 0%
4 | Plaster |  | 25% | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 250000 |  | 0 |  | 0 |  |  | 0% | 0% | 0%
iii | Construction of Inlet Chamber & Screen Channel | 2874828 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  | 2% | 57496.56 | 100% | 57496.56 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Excavation |  | 10% | 287482.8 |  | 0 |  |  | 100% | 287482.8 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | PCC |  | 15% | 431224.2 |  | 0 |  | 0 | 100% | 431224.2 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | RCC Foundation/Raft |  | 15% | 431224.2 |  | 0 |  | 0 | 80% | 344979.36 | 20% | 86244.84 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
5 | Wall 50% of total lift work |  | 15% | 431224.2 |  | 0 |  | 0 | 10% | 43122.42 | 90% | 388101.78 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
6 | Walls (balance 50% of Total Lift work) |  | 15% | 431224.2 |  | 0 |  |  |  | 0 |  | 0 | 100% | 431224.2 | 100% | 431224.2 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
7 | Column & Beam |  | 10% | 287482.8 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 287482.8 | 100% | 287482.8 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
8 | Ground Floor Slab |  | 8% | 229986.24 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 229986.24 | 100% | 229986.24 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
9 | Walkway/Platform |  | 5% | 143741.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 143741.4 | 100% | 143741.4 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
10 | Hydro Testing /Finishing works |  | 5% | 143741.4 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 143741.4 |  | 0 | 0% | 0% | 0%
C | SEWER SYSTEM AREA | 9066560 | [26 empty] | 0% | 0% | 0%
1 | Site Clearance |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
2 | Supply of pipes |  | 80% | 7253248 | 87.92% | 6377489.6416 | 12.1% | 875758.358 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | Excavation and Laying of pipes including bed preperation & backfilling |  | 7.5% | 679992 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 611992.8 | 90% | 611992.8 | 10% | 67999.2 | 5% | 33999.6 |  | 0 |  |  |  | 0 |  |  | 95% | 95% | 0%
4 | Manholes |  | 7.5% | 679992 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 50% | 344545 | 50% | 339996 | 50% | 335447 | 40% | 271996.8 |  | 0 |  |  | 90% | 0% | 90%
5 | Flow Testing |  | 5% | 453328 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 453328 |  |  | 0% | 0% | 0%
D | I & D Work | [27 empty] | 0% | 0% | 0%
(i) | Approach Channel | 674400 | [26 empty] | 0% | 0% | 0%
1 | Excavation |  | 10.1% | 68100 |  | 0 |  |  |  | 0 |  | 0 | 100% | 68100 | 100% | 68100 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | PCC |  | 25.21% | 170000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 170000 | 100% | 170000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Raft |  | 30.4% | 205000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 205000 | 95% | 194750 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 95% | 95% | 0%
4 | wall |  | 25.21% | 170000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 170000 | 100% | 170000 |  | 0 |  |  |  | 0 |  |  | 100% | 10% | 90%
5 | Hydro Testing /Finishing works |  | 9.09% | 61300 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 61300 |  |  |  | 0 |  |  | 0% | 0% | 0%
(ii) | Inlet Chamber | 848200 | [26 empty] | 0% | 0% | 0%
1 | Excavation |  | 10.13% | 85900 |  | 0 |  |  |  | 0 |  | 0 | 100% | 85900 | 100% | 85900 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | PCC |  | 25.35% | 215000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 215000 | 100% | 215000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Raft |  | 30.06% | 255000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 255000 | 100% | 255000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | wall |  | 25.35% | 215000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 215000 | 100% | 215000 |  | 0 |  |  |  | 0 |  |  | 100% | 10% | 90%
5 | Hydro Testing /Finishing works |  | 9.113% | 77300 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 77300 |  |  |  | 0 |  |  | 0% | 0% | 0%
(iii) | Screen Channel | 680845 | [26 empty] | 0% | 0% | 0%
1 | Excavation |  | 10.09% | 68700 |  | 0 |  |  |  | 0 |  | 0 | 100% | 68700 | 100% | 68700 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | PCC |  | 25.25% | 171900 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 171900 | 100% | 171900 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Raft |  | 30.31% | 206370 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 206370 | 100% | 206370 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | wall |  | 25.26% | 171975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 171975 | 100% | 171975 |  | 0 |  |  |  | 0 |  |  | 100% | 10% | 90%
5 | Hydro Testing /Finishing works |  | 9.092% | 61900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 61900 |  |  |  | 0 |  |  | 0% | 0% | 0%
(iv) | Grit Chamber | 698620 | [26 empty] | 0% | 0% | 0%
1 | Excavation |  | 10.12% | 70670 |  | 0 |  |  |  | 0 |  | 0 | 100% | 70670 | 100% | 70670 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | PCC |  | 25.29% | 176675 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 176675 | 100% | 176675 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Raft |  | 30.35% | 212000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 212000 | 100% | 212000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | wall |  | 25.15% | 175675 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 175675 | 100% | 175675 |  | 0 |  |  |  | 0 |  |  | 100% | 10% | 90%
5 | Hydro Testing /Finishing works |  | 9.104% | 63600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 63600 |  |  |  | 0 |  |  | 0% | 0% | 0%
(v) | Collection Chamber | 135686 | [26 empty] | 0% | 0% | 0%
1 | Excavation |  | 10.1% | 13710 |  | 0 |  |  |  | 0 |  | 0 | 100% | 13710 | 100% | 13710 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | PCC |  | 25.26% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 34273 | 100% | 34273 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
3 | RCC Foundation/Raft |  | 30.31% | 41130 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 41130 | 100% | 41130 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
4 | wall |  | 25.26% | 34273 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 100% | 34273 | 98% | 33587.54 |  | 0 |  |  |  | 0 |  |  | 98% | 10% | 88%
5 | Hydro Testing /Finishing works |  | 9.065% | 12300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 12300 |  |  |  | 0 |  |  | 0% | 0% | 0%
E | EFFLUENT DISPOSAL SYSTEM | [27 empty] | 0% | 0% | 0%
[6 empty] | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
1 | Site Clearance |  |  | 250000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 250000 | 100% | 250000 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
2 | Construction of Effluent Channel |  |  | 2530620 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 2530620 | 62% | 1571010.4 |  | 0 |  |  |  | 0 |  |  | 62% | 62% | 0%
F | E&M WORK |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
i) | GRIT CHAMBER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.On supply - Grit Scraper Mechanism |  | 0% | 2285000 |  | 0 |  | 0 | 100% | 1828000 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.On Installation - Grit Scraper Mechanism |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 457000 |  |  |  | 0 |  |  | 0% | 0% | 0%
ii) | SLUDGE THICKENER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Sludge Thickener |  | 0% | 880000 |  | 0 |  | 0 | 100% | 704000 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.Installation - Sludge Thickener |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 176000 | 50% | 88000 |  | 0 |  |  | 50% | 40% | 10%
iii) | TRANSFORMER YARD AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Transformer |  | 0% | 3025000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 2420000 | 100% | 2420000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.Installation - Transformer |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 605000 |  |  |  | 0 |  |  | 0% | 0% | 0%
iv) | DG SHED AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - DG |  | 0% | 3875000 |  | 0 |  |  |  | 0 | 100% | 3100000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.Installation - DG |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 775000 |  |  |  | 0 |  |  | 0% | 0% | 0%
v) | MEP |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Screen |  | 0% | 4180000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3344000 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| B.Installation - Screen |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 836000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| C.Supply - Hoist |  | 0% | 585000 |  | 0 |  | 0 | 100% | 468000 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| D.Installation - Hoist |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 117000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| E.Supply - Pumps & Motors(MEP) |  | 0% | 8680000 |  | 0 |  | 0 |  | 0 | 100% | 6944000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| F.Installation - Pumps & Motors(MEP) |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 1736000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| G.Supply - Gates |  | 0% | 1430000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 1144000 | 100% | 1144000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| H.Supply - Valves(MPS) |  | 0% | 1430000 |  | 0 |  |  |  | 0 |  | 0 | 50% | 576549 |  | 0 | 50% | 567451 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| I.Installation - Gate & Valves(MPS) |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 286000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| J.Installation - Gate & Valves(MPS) |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 286000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| K.Supply Instruments(like flow meter, Guages, level, Transmiter) |  | 56% | 1760000 |  | 0 |  |  |  | 0 |  | 0 | 70% | 985600 | 70% | 985600 | 30% | 422400 | 30% | 422400 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| L.Installation - Instruments(like flow meter, Guages, level, Transmiter) |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 352000 |  |  |  | 0 |  |  | 0% | 0% | 0%
vi) | INLET CHAMBER AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Gates |  | 0% | 1155000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 924000 | 100% | 924000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.Supply - Valves(STP) |  | 0% | 1155000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 924000 | 10% | 92400 |  | 0 |  |  |  | 0 |  |  | 10% | 10% | 0%
| C.Installation - Gates |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 231000 | 30% | 70400 |  | 0 |  |  | 30% | 20% | 10%
| D.Installation - Valves(STP) |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 231000 |  |  |  | 0 |  |  | 0% | 0% | 0%
vii) | FINE SCREEN AREA |  |  |  |  | 0 | [19 empty] | 0 |  |  | 0% | 0% | 0%
| A.On supply -Fine Screen |  | 0% | 1760000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 1408000 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| B.On Installation -Fine Screen |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 352000 |  |  |  | 0 |  |  | 0% | 0% | 0%
viii) | SBR BASIN AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A..On supply - Decanter Equipment |  | 0% | 9315000 |  | 0 | 100% | 7452000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B..Installation - Decanter Equipment |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 1863000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| C.On supply - Diffuser |  | 0% | 10615000 |  | 0 | 100% | 8492000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| D.On Installation - Diffuser |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 2123000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| E.On supply - RAS Pump, SAS Pump |  | 80% | 3470000 |  | 0 |  | 0 |  | 0 | 100% | 2776000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| F.On Installation - RAS Pump, SAS Pump |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 694000 |  |  |  | 0 |  |  | 0% | 0% | 0%
| G.On supply - Chain Pulley Block |  | 0% | 385000 |  | 0 |  | 0 |  | 0 | 100% | 308000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| H.On Installation - Chain Pulley Block |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 100% | 77000 |  |  |  | 0 |  |  | 0% | 0% | 0%
ix) | AIR BLOWER ROOM |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Blower |  | 0% | 3800000 |  | 0 |  | 0 | 50% | 1516356 | 40% | 1219610.57 | 10% | 304033.43 | 10% | 304033.43 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B. Installation - Blower |  | 0% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 760000 |  |  | 0% | 0% | 0%
| C.Supply - Hoist Work |  | 80% | 575000 |  | 0 |  | 0 |  | 0 | 100% | 460000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| D.Installation - Hoist Work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 115000 |  |  | 0% | 0% | 0%
x) | CHLORINATION ROOM AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - Chlorination system(Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work |  | 0% | 1595000 |  | 0 |  | 0 | 50% | 637277 | 40% | 510400 | 10% | 128323 | 10% | 127600 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B. Installation - Chlorination system(Dosing pumps, chlorinators, Tonnes, Chemicals & Piping work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 319000 |  |  | 0% | 0% | 0%
| C.Supply - Chlorine Nutrilisation Tank |  | 0% | 275000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 220000 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| D.Installation - Chlorine Nutrilisation tank |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 55000 |  |  | 0% | 0% | 0%
| E.Supply - Hoist Work |  | 0% | 385000 |  | 0 |  |  |  | 0 | 100% | 308000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| F.Installation - Hoist Work |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 77000 |  |  | 0% | 0% | 0%
xi) | CENTRIFUGE HOUSE & FEED PUMP AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.On supply -Centrifuge |  | 0% | 2832500 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 2266000 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| B.On supply -Centrifuge Feed Pump |  | 0% | 2832500 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 100% | 2266000 | 100% | 2266000 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| C.On Installation -Centrifuge |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 566500 |  |  | 0% | 0% | 0%
| D.On Installation -Centrifuge Feed Pump |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 566500 |  |  | 0% | 0% | 0%
xii) | ADMN BUILDING AREA |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply - LT/HT Panel |  | 26% | 4690000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  | 67.5% | 2536509 | 60% | 2255109 | 32.5% | 1219400 |  |  |  | 0 |  |  | 60% | 60% | 0%
| B.Installation - LT/HT Panel |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 938000 |  |  | 0% | 0% | 0%
| C.Supply - PLC/SCADA Automation |  | 0% | 4500000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 3600000 | 100% | 3600000 | 100% | 100% | 0%
| D.Installation - PLC/SCADA Automation |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 900000 |  |  | 0% | 0% | 0%
xiii) | Cable Tray & Earthing work |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply -Cable & cable Tray |  | 0% | 1000000 |  | 0 |  |  |  | 0 |  | 0 | 100% | 800000 | 90% | 720000 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 90% | 90% | 0%
| B.Installation -Cable & cable Tray |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 200000 |  |  | 0% | 0% | 0%
xiv) | External Electrification (lighting & Pole) |  |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0% | 0%
| A.Supply |  | 0% | 1000000 |  | 0 |  |  |  | 0 |  | 0 | 60% | 489176 | 60% | 489176 | 40% | 310824 | 40% | 310824 |  | 0 |  |  |  | 0 |  |  | 100% | 100% | 0%
| B.Installation |  | 20% |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 200000 |  |  | 0% | 0% | 0%
xv) | TESTING OF E&M EQUIPMENT FOR STP & MPS |  | 100% | 7648000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 7648000 | 30% | 1835520 | 30% | 30% | 0%
xvi) | EQUIPMENT TOOLS & MISC. |  | 100% | 370000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 100% | 370000 |  |  | 0% | 0% | 0%
III | TRIAL RUN & COMMISSIONING
1 | Trial Run & Commissioning
|  |  |  | 212950200 |  | 26618774.9056 |  | 26618774.6155 |  | 26618774.8095 |  | 26618774.9974 |  | 26618775.0441 |  | 20311143.7441 |  | 26618774.6725 |  | 19031646.1125 |  | 26622683.5125 |  | 8380689.1925 |  | 26618775.4425 |  | 9316770.965
Note:
| 1st milestone |  |  |  | = | 26618774.9056
| 2nd milestone |  |  |  | = | 26618774.6155
| 3rd Milestone |  |  |  | = | 26618774.8095
| 4th Milestone |  |  |  | = | 26618774.9974
| 5th Milestone |  |  |  | = | 20311143.7441
| 6th Milestone |  |  |  | = | 19031646.1125
| 7th Milestone |  |  |  | = | 8380689.1925
| 8th Milestone |  |  |  | = | 9316770.965
| Total Amount |  |  |  | = | 163515349.3421
| Total % as on 31.08.2024 |  |  |  | = | 76.79%