## Pankha 8th Mile Stone
PROGRESS REPORT FOR 30 MLD PANKHA SITE
Sl. No. | Description of Items | Total Amount | % | BOQ Amount | Milestone-1 (From 26th Nov.'19 to 25th Sep'20) |  | Milestone-2 (From 26th Sep.'20 to 25th Nov.'20) |  | Milestone-3 (From 26th Nov.'20 to 22nd Feb'21) |  | Milestone-4 (From 23rd Feb'21 to 01 July'21) |  | Milestone-5 (From 2nd July'21 to 06th September'21) |  | Milestone-6 (From 07th September'21 to 06th December'21) |  | Milestone-7 (From 07th December'21 to 25th Mar'22) |  | Milestone-8 (From 26th Mar'22 to 15th July'23) |  | Achieved for 8th Milestone |  |  |  | Cumulative Achieve |  |  | Upto May'23 | For June'23
[5 empty] | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.) | % | Amount(Rs.)
A | Design & Drawing & STP & Sewer Laying works | 49935900
| A. On approval of BEP |  | 0.5 | 24967950 | 100% | 24967950 | [16 empty] | 100% | 24967950 | 100% | 0% | 0 | 100% | 0% | 0
| B. On approval of design & drawings for Civil & Sewerage works |  | 0.5 | 24967950 | 100% | 24967950 | [16 empty] | 100% | 24967950 | 100% | 0% | 0 | 100% | 0% | 0
B | CONSTRUCTION | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| STP (30 MLD) | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
1 | SBR Basin Area | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL WORK | 137576000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 250000 | 100% | 250000 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 250000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  | 7.1512 | 9838400 | 100% | 9838400 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 9838400 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 14757600 | 100% | 14757600 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 14757600 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  | 17.8781 | 24596000 | 40% | 9838400 | 60% | 14757600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 24596000 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  | 17.8781 | 24596000 |  | 0 | 100% | 24596000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 24596000 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  | 17.8781 | 24596000 |  | 0 |  | 0 | 60% | 14757600 | 38% | 9346480 | 2% | 491920 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 24596000 | 100% | 0% | 0 | 100% | 0% | 0
| Baffle Walls work |  | 8.9391 | 12298000 |  | 0 |  | 0 | 55% | 6763900 | 38% | 4673240 | 7% | 860860 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 12298000 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  | 8.9391 | 12298000 |  | 0 |  | 0 |  | 0 | 47.13% | 5796063.27 | 27.87% | 3427436.73 | 19.64% | 2415095.36 |  | 0 | 5.362% | 659404.64 | 0% | 0 | 100% | 12298000 | 94.64% | 5.362% | 659404.64 | 100% | -5.362% | -659404.64
| Finishing Work |  | 10.6094 | 14596000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 4378800 | 35% | 5108600 | 35% | 5108600 | 30% | 4378800 | 100% | 14596000 | 95% | 5% | 729800 | 100% | -5% | -729800
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| A. DECANTERS | 36894000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 31359900 | [7 empty] | 0 |  | 0 | 100% | 31359900 |  | 0 |  | 0 |  | 0 | 100% | 31359900 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 3689400 | [7 empty] | 0 |  | 0 |  | 0 | 50% | 1844700 | 50% | 1844700 | 50% | 1844700 | 100% | 3689400 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1844700 | [7 empty] | 0 |  | 0 |  | 0 | 50% | 922350 | 50% | 922350 | 50% | 922350 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| B. DIFFUSERS | 24596000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 20906600 | [7 empty] | 0 | 100% | 20906600 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 20906600 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 2459600 | [9 empty] | 0 |  | 0 | 50% | 1229800 | 50% | 1229800 | 50% | 1229800 | 100% | 2459600 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1229800 | [7 empty] | 0 |  | 0 |  | 0 | 50% | 614900 | 50% | 614900 | 50% | 614900 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| C. RAS & SAS PUMPS | 24596000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 20906600 | [6 empty] | 50% | 10453300 | 50% | 10453300 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 20906600 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 2459600 | [7 empty] | 0 |  | 0 | 50% | 1229800 |  | 0 | 50% | 1229800 | 50% | 1229800 | 100% | 2459600 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 1229800 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 1229800 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| D. PIPES & FITTINGS | 12298000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  | 85 | 10453300 | [7 empty] | 0 |  | 0 | 100% | 10453300 |  | 0 |  | 0 |  | 0 | 100% | 10453300 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  | 10 | 1229800 | [7 empty] | 0 |  | 0 | 75% | 922350 |  | 0 | 25% | 307450 | 25% | 307450 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  | 5 | 614900 | [7 empty] | 0 |  | 0 | 20% | 122980 |  | 0 | 80% | 491920 | 80% | 491920 | 100% | 614900 | 100% | 0% | 0 | 100% | 0% | 0
2 | Chlorine Contact Tank Area | 18597000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 150000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 737880 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1106820 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1106820 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 4611750 |  | 0 | 100% | 4611750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 4611750 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Baffle Walls work |  |  | 3689400 |  | 0 |  | 0 | 70% | 2582580 | 25% | 922350 | 3% | 110682 | 2% | 73788 |  | 0 |  | 0 |  | 0 | 100% | 3689400 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 55% | 1521877.5 | 45% | 1245172.5 | 45% | 1245172.5 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
3 | Chlorination House Area | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL WORK | 12090550 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 368940 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 553410 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Column footing |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 | 50% | 461175 | 50% | 461175 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| Ground floor Slab |  |  | 922350 |  | 0 |  | 0 |  | 0 | 50% | 461175 | 50% | 461175 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| Roof Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1844700 |  | 0 |  | 0 |  | 0 | 10% | 184470 | 20% | 368940 | 70% | 1291290 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 55% | 1014585 | 45% | 830115 | 45% | 830115 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| A. CHLORINATION SYSTEM | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [7 empty] | 0 |  | 0 |  | 0 | 90% | 2822391 | 10% | 313599 | 10% | 313599 | 100% | 3135990 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 368940 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 | 100% | 184470 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| B. HOIST WORKS | 922350 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 783997.5 | [6 empty] | 100% | 783997.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 783997.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 92235 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 92235 | 100% | 92235 | 100% | 92235 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 46117.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 46117.5 | 100% | 46117.5 | 100% | 46117.5 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| ELECRICAL & INSTRUMENTATION WORK | 1844700 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1567995 | [7 empty] | 0 |  | 0 |  | 0 | 50% | 783997.5 | 50% | 783997.5 | 50% | 783997.5 | 100% | 1567995 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 | 100% | 184470 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 92235 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 92235 | 100% | 92235 | 100% | 92235 | 100% | 0% | 0 | 98% | 2% | 1844.7
4 | Sludge Thickener Area | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL WORK | 13012900 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 737880 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1106820 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1106820 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation wall/base slab |  |  | 3689400 |  | 0 | 100% | 3689400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3689400 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 | 60% | 1660230 | 40% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 | 40% | 737880 |  | 0 | 10% | 184470 | 10% | 184470 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| SLUDGE THICKENER MECHANISM | 5534100 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4703985 | [7 empty] | 0 |  | 0 | 100% | 4703985 |  | 0 |  | 0 |  | 0 | 100% | 4703985 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 553410 | [7 empty] | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 276705 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 276705 | 100% | 276705 | 100% | 276705 | 100% | 0% | 0 | 100% | 0% | 0
5 | Inlet / Stilling Chamber Area | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance | 6199000 |  | 50000 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Column footing |  |  | 1229800 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Slab |  |  | 922350 |  | 0 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 50% | 614900 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Final finishing including Staircases,Railing,Shade,Painting, etc. |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 5% | 61490 | 45% | 553410 | 45% | 553410 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
6 | Manual & Mechanical Fine Bar Screen Chamber Area | 8658600 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Slab |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 15.95% | 196164.88 | 84.05% | 1033635.12 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 245960 | 35% | 430430 | 45% | 553410 | 45% | 553410 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
7 | Grit Chamber (Mechanical Cleaned) & (Manually Cleaned) | 8658600 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Slab |  |  | 1229800 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 45% | 553410 | 5% | 61490 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Wall |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1106820 |  | 0 | 10% | 122980 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 614900 | 20% | 245960 | 25% | 307450 | 5% | 61490 | 5% | 61490 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 55% | 676390 | 45% | 553410 | 45% | 553410 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| A.MECHANICAL FINE SCREEN | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 | 100% | 2090660 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2090660 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% | 122980 | 100% | 0% | 0 | 100% | 0% | 0
| B.MANUAL FINE SCREEN | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [7 empty] | 0 | 100% | 3135990 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3135990 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 | 100% | 184470 | 100% | 0% | 0 | 100% | 0% | 0
| C.GATES | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 2090660 |  | 0 |  | 0 | 100% | 2090660 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 |  | 0 | 80% | 196768 | 20% | 49192 | 20% | 49192 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% | 122980 | 100% | 0% | 0 | 100% | 0% | 0
| D.CONVEYOR BELTS | 2459600 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2090660 | [7 empty] | 0 | 100% | 2090660 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2090660 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 245960 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 245960 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 122980 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 122980 | 100% | 122980 | 100% | 122980 | 100% | 0% | 0 | 100% | 0% | 0
| E. GRIT MECHANISM | 6149000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5226650 | [5 empty] | 0 | 100% | 5226650 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 5226650 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 614900 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 614900 | 60% | 368940 | 100% | 614900 | 60% | 40% | 245960 | 100% | -40% | -245960
| (iii) On completion of Testing of equipment |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 60% | 184470 | 100% | 307450 | 60% | 40% | 122980 | 100% | -40% | -122980
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
8 | Flow Measurement Channel Area | 12348000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 245960 |  | 0 |  | 0 | 100% | 245960 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 245960 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 368940 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation |  |  | 1229800 |  | 0 |  | 0 | 100% | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 50% | 922350 | 40% | 737880 |  | 0 | 10% | 184470 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Slab |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2459600 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Wall |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 2213640 | 10% | 245960 |  | 0 |  | 0 |  | 0 | 100% | 2459600 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 1229800 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 1106820 | 10% | 122980 |  | 0 |  | 0 |  | 0 | 100% | 1229800 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 2459600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 491920 | 35% | 860860 | 45% | 1106820 | 0% | 0 | 100% | 2459600 | 55% | 45% | 1106820 | 100% | -45% | -1106820
9 | Admin Bldg Area | 14857600 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 100000 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 368940 | 100% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 553410 | 100% | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| Column footings/Foundation |  |  | 1844700 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1844700 |  | 0 |  | 0 | 80% | 1475760 | 20% | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Ground Floor Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 | 50% | 922350 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| 1st Floor Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Roof Slab |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1844700 |  | 0 |  | 0 |  | 0 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 48% | 1328184 | 32% | 885456 | 20% | 553410 | 20% | 553410 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 55% | 1014585 | 45% | 830115 | 45% | 830115 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| ELECTRICAL WORK | 8689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| LT/HT PANEL | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 7385990 | [6 empty] | 50% | 3692995 |  | 0 | 50% | 3692995 |  | 0 |  | 0 |  | 0 | 100% | 7385990 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1303410 | [7 empty] | 0 |  | 0 |  | 0 | 80% | 1042728 | 20% | 260682 | 20% | 260682 | 100% | 1303410 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 434470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 434470 | 100% | 434470 | 100% | 434470 | 100% | 0% | 0 | 100% | 0% | 0
| PLC/SCADA SYSTEM | 8689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 7385990 | [7 empty] | 0 |  | 0 |  | 0 | 40% | 2954396 | 60% | 4431594 | 60% | 4431594 | 100% | 7385990 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1303410 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 1303410 | 100% | 1303410 | 100% | 1303410 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 434470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 434470 | 100% | 434470 | 100% | 434470 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
10 | Air Blower Room Area | 10092125 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 100000 |  | 0 |  | 0 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 307450 |  | 0 |  | 0 | 50% | 153725 | 50% | 153725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 461175 |  | 0 |  | 0 | 50% | 230587.5 | 50% | 230587.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 461175 | 100% | 0% | 0 | 100% | 0% | 0
| Column footings/Foundation |  |  | 1537250 |  | 0 |  | 0 | 0% | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1537250 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 23% | 353567.5 | 77% | 1183682.5 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 768625 | 50% | 768625 | 50% | 768625 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | 4611750 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| AIR BLOWER(PUMP) | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3919987.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 3919987.5 |  | 0 |  | 0 | 100% | 3919987.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 461175 | [7 empty] | 0 |  | 0 |  | 0 | 90% | 415057.5 | 10% | 46117.5 | 10% | 46117.5 | 100% | 461175 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 230587.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 230587.5 | 100% | 230587.5 | 100% | 230587.5 | 100% | 0% | 0 | 100% | 0% | 0
| ELECTRICAL WORK | 6149000 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| AIR BLOWER(MOTOR) | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5226650 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 5226650 |  | 0 |  | 0 | 100% | 5226650 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 614900 | [7 empty] | 0 |  | 0 |  | 0 | 90% | 553410 | 10% | 61490 | 10% | 61490 | 100% | 614900 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 307450 | 100% | 307450 | 100% | 307450 | 100% | 0% | 0 | 100% | 0% | 0
11 | Staff Quarter Area | 8658600 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 344344 |  | 0 |  | 0 | 100% | 344344 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 344344 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 516516 |  | 0 |  | 0 | 100% | 516516 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 516516 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1291290 |  | 0 |  | 0 |  | 0 | 100% | 1291290 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 860860 |  | 0 |  | 0 |  | 0 | 100% | 860860 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 430430 | 50% | 430430 |  | 0 |  | 0 | 100% | 860860 | 100% | 0% | 0 | 100% | 0% | 0
| Electrical work |  |  | 1291290 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 80% | 1033032 | 20% | 258258 | 20% | 258258 | 100% | 1291290 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 860860 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 430430 | 50% | 430430 | 50% | 430430 | 100% | 860860 | 100% | 0% | 0 | 100% | 0% | 0
12 | Guard Room Area | 3739400 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 147576 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 147576 |  | 0 |  | 0 |  | 0 | 100% | 147576 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 221364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 221364 |  | 0 |  | 0 |  | 0 | 100% | 221364 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground Floor Slab |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 368940 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| Electrical work |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 368940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 184470 | 50% |  | 50% | 184470 | 100% | 184470 | 100% | 0% | 0 | 100% | 0% | 0
13 | Sludge Dewatering System Area (Centrifuge Pump House, Sludge sump & Poly dosing tank) | 21621500 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 100000 |  | 0 | 100% | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 614900 |  | 0 | 100% | 614900 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 614900 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 922350 |  | 0 |  | 0 | 100% | 922350 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 922350 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation |  |  | 1537250 |  | 0 |  | 0 |  | 0 | 100% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1537250 | 100% | 0% | 0 | 100% | 0% | 0
| 1st Column & Beam |  |  | 3074500 |  | 0 |  | 0 |  | 0 | 50% | 1537250 | 50% | 1537250 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| Ground Floor Slab |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 |  | 0 |  | 0 |  | 0 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| 2nd Column & Beam |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 1229800 | 10% | 307450 | 50% | 1537250 |  | 0 |  | 0 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 |  | 0 |  | 0 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3074500 |  | 0 |  | 0 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 3074500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1537250 | 50% | 1537250 | 50% | 1537250 | 100% | 3074500 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CENTRIFUGE UNIT | 4611750 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3919987.5 | [7 empty] | 0 | 100% | 3919987.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3919987.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 461175 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 461175 |  | 0 |  | 0 | 100% | 461175 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 230587.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 230587.5 | 85% | 195999.375 | 100% | 230587.5 | 85% | 15% | 34588.125 | 100% | -15% | -34588.125
| CENTRIFUGE FEED PUMP | 3074500 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2613325 | [6 empty] | 100% | 2613325 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2613325 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 307450 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 307450 |  | 0 |  | 0 | 100% | 307450 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 153725 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 153725 | 85% | 130666.25 | 100% | 153725 | 85% | 15% | 23058.75 | 100% | -15% | -23058.75
| POLY DOSING PUMPS | 1537250 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1306662.5 | [7 empty] | 0 |  | 0 | 100% | 1306662.5 |  | 0 |  | 0 |  | 0 | 100% | 1306662.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 153725 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 153725 | 100% | 153725 | 100% | 153725 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 76862.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 76862.5 | 100% | 76862.5 | 100% | 76862.5 | 100% | 0% | 0 | 100% | 0% | 0
14 | Supernatant Recirculation Sump Area | 12040550 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 737880 |  | 0 |  | 0 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1106820 |  | 0 |  | 0 | 100% | 1106820 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1106820 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation wall/base slab |  |  | 2767050 |  | 0 |  | 0 | 100% | 2767050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2767050 |  | 0 |  | 0 | 40% | 1106820 | 60% | 1660230 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2767050 |  | 0 |  | 0 |  | 0 | 90% | 2490345 | 10% | 276705 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2767050 | 100% | 0% | 0 | 100% | 0% | 0
| Final finishing including Staircases,Railing,Shade,Painting etc. |  |  | 1844700 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 922350 |  | 0 |  | 0 | 50% | 922350 | 50% | 922350 | 100% | 1844700 | 100% | 0% | 0 | 100% | 0% | 0
| MECHANICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| PUMPING SYSTEM | 6456450 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 5487982.5 | [7 empty] | 0 | 100% | 5487982.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 5487982.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 645645 | [7 empty] | 0 |  | 0 | 50% | 322822.5 | 50% | 322822.5 |  | 0 |  | 0 | 100% | 645645 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 322822.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 322822.5 | 100% | 322822.5 | 100% | 322822.5 | 100% | 0% | 0 | 100% | 0% | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
15 | Transformer Yard Area | 1967680 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 491920 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 491920 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 491920 | 100% | 0% | 0 | 100% | 0% | 0
| Foundation Work |  |  | 737880 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 737880 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 737880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 368940 |  | 0 | 50% | 368940 | 50% | 368940 | 100% | 737880 | 100% | 0% | 0 | 100% | 0% | 0
| ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| TRANSFORMER | 3689400 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3135990 | [6 empty] | 100% | 3135990 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3135990 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 368940 | [7 empty] | 0 |  | 0 | 80% | 295152 | 20% | 73788 |  | 0 |  | 0 | 100% | 368940 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 184470 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 184470 | 100% | 184470 | 100% | 184470 | 100% | 0% | 0 | 100% | 0% | 0
| CABLE & CABLE TRAY | 3566420 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3031457 | [7 empty] | 0 |  | 0 | 100% | 3031457 |  | 0 |  | 0 |  | 0 | 100% | 3031457 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 356642 | [7 empty] | 0 |  | 0 | 100% | 356642 |  | 0 |  | 0 |  | 0 | 100% | 356642 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 178321 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 178321 | 100% | 178321 | 100% | 178321 | 100% | 0% | 0 | 100% | 0% | 0
16 | DG Area | 1936935 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 |  | 0 |  | 0 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| Foundation Work |  |  | 830115 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 830115 |  | 0 |  | 0 | 100% | 830115 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 553410 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 553410 | 100% | 553410 | 100% | 553410 | 100% | 0% | 0 | 100% | 0% | 0
| ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| DG SET | 3873870 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 3292789.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 3292789.5 |  | 0 |  | 0 | 100% | 3292789.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 387387 | [7 empty] | 0 |  | 0 |  | 0 | 60% | 232432.2 | 40% | 154954.8 | 40% | 154954.8 | 100% | 387387 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 193693.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 193693.5 | 100% | 193693.5 | 100% | 193693.5 | 100% | 0% | 0 | 100% | 0% | 0
| CABLE & CABLE TRAY | 1936935 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1646394.75 | [7 empty] | 0 |  | 0 | 100% | 1646394.75 |  | 0 |  | 0 |  | 0 | 100% | 1646394.75 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 193693.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 193693.5 | 100% | 193693.5 | 100% | 193693.5 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 96846.75 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 96846.75 | 100% | 96846.75 | 100% | 96846.75 | 100% | 0% | 0 | 100% | 0% | 0
17 | Sludge Storage Platform | 800000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 |  | 0 |  | 0 | 100% | 300000 | 100% | 0% | 0 | 100% | 0% | 0
| Foundation Work |  |  | 400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 400000 | 100% | 400000 | 100% | 400000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 100000 | 100% | 100000 | 100% | 100000 | 100% | 0% | 0 | 100% | 0% | 0
18 | EXTERNAL DEVELOPMENT | 43345000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
A. | Roads, Storm Water Drain & Miscellaneous work |  |  | 12600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 9.04% | 1138649.43 | 40.96% | 5160960 | 50% | 6300390.57 | 15% | 1890390.57 | 100% | 12600000 | 65% | 35% | 4410000 | 97% | -32% | -4032000
B. | Compound Wall with Gate |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 6149000 | 40% | 2459600 | 28.5% | 1752465 | 31.5% | 1936935 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 6149000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column footing |  |  | 6149000 | 40% | 2459600 | 20% | 1229800 | 30% | 1844700 | 5% | 307450 | 5% | 307450 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 6149000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column & Beam |  |  | 6149000 | 40% | 2459600 | 20% | 1229800 | 28% | 1721720 | 7% | 430430 | 5% | 307450 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 6149000 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 6149000 |  | 0 | 25% | 1537250 | 23% | 1414270 | 32% | 1967680 | 10% | 614900 |  | 0 |  | 0 | 10% | 614900 | 9% | 553410 | 100% | 6149000 | 99% | 1% | 61490 | 99% | 0% | 0
| Finishing Work |  |  | 6149000 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 2459600 | 30% | 1844700 |  | 0 | 30% | 1844700 | 29% | 1783210 | 100% | 6149000 | 99% | 1% | 61490 | 99% | 0% | 0
19 | MPS-2 ( 115MLD) | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 29553660 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 150000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 3451734 | 15% | 517760.1 | 85% | 2933973.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3451734 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 2301156 |  | 0 | 100% | 2301156 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2301156 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 5752890 |  | 0 | 100% | 5752890 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 5752890 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 3835260 |  | 0 |  | 0 | 100% | 3835260 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3835260 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 3835260 |  | 0 |  | 0 | 15% | 575289 | 35% | 1342341 | 7% | 268468.2 | 43% | 1649161.8 |  | 0 |  | 0 |  | 0 | 100% | 3835260 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 3835260 |  | 0 |  | 0 | 10% | 383526 | 40% | 1534104 | 30% | 1150578 | 20% | 767052 |  | 0 |  | 0 |  | 0 | 100% | 3835260 | 100% | 0% | 0 | 100% | 0% | 0
| Ground Floor Slab |  |  | 3835260 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 3835260 |  | 0 |  | 0 | 100% | 3835260 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 2556840 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 1278420 | 50% | 1278420 | 50% | 1278420 | 100% | 2556840 | 100% | 0% | 0 | 100% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 8572800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 681824 |  | 0 |  | 0 | 100% | 681824 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 681824 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1022736 |  | 0 |  | 0 | 100% | 1022736 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1022736 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1704560 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1704560 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 1704560 |  | 0 |  | 0 |  | 0 | 25% | 426140 | 72% | 1227283.2 | 3% | 51136.8 |  | 0 |  | 0 |  | 0 | 100% | 1704560 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 1704560 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1704560 |  | 0 |  | 0 |  | 0 | 100% | 1704560 | 100% | 0% | 0 | 100% | 0% | 0
C | Construction of Raw Sewage Pump House | 6392100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Column & Beam |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 639210 | 60% | 958815 |  | 0 |  | 0 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
| Roof Slab |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 |  | 0 |  | 0 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10% | 159802.5 | 70% | 1118617.5 | 20% | 319605 | 20% | 319605 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 799012.5 | 50% | 799012.5 | 50% | 799012.5 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
D | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Coarese Screen mechanical & manual | 5326750 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4527737.5 | [7 empty] | 0 | 25% | 1131934.375 | 75% | 3395803.125 |  | 0 |  | 0 |  | 0 | 100% | 4527737.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 532675 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 532675 |  | 0 |  | 0 | 100% | 532675 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 266337.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 266337.5 | 100% | 266337.5 | 100% | 266337.5 | 100% | 0% | 0 | 100% | 0% | 0
| Piping & Support work | 5326750 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 4527737.5 | [7 empty] | 0 | 75% | 3395803.125 | 25% | 1131934.375 |  | 0 |  | 0 |  | 0 | 100% | 4527737.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 532675 | [7 empty] | 0 |  | 0 | 75% | 399506.25 |  | 0 | 25% | 133168.75 | 25% | 133168.75 | 100% | 532675 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 266337.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 266337.5 | 100% | 266337.5 | 100% | 266337.5 | 100% | 0% | 0 | 100% | 0% | 0
| Gate Work | 7457450 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 6338832.5 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 6338832.5 |  | 0 |  | 0 | 100% | 6338832.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 745745 | [7 empty] | 0 |  | 0 |  | 0 | 100% | 745745 |  | 0 |  | 0 | 100% | 745745 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 372872.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 372872.5 | 100% | 372872.5 | 100% | 372872.5 | 100% | 0% | 0 | 100% | 0% | 0
| Pumps | 11718850 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 9961022.5 | [7 empty] | 0 | 100% | 9961022.5 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 9961022.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 1171885 | [7 empty] | 0 |  | 0 |  | 0 | 80% | 937508 | 20% | 234377 | 20% | 234377 | 100% | 1171885 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 585942.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 585942.5 | 100% | 585942.5 | 100% | 585942.5 | 100% | 0% | 0 | 100% | 0% | 0
20 | ICI Nala IPS | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 16764000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 150000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 1533600 |  | 0 | 100% | 1533600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1533600 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1022400 |  | 0 | 100% | 1022400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1022400 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft | 2556000 |  | 2556000 |  | 0 | 50% | 1278000 | 50% | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2556000 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 | 40% | 1022400 |  | 0 | 60% | 1533600 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Ground Floor Slab |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1278000 | 100% | 1278000 | 100% | 1278000 | 100% | 0% | 0 | 100% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 4310000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 50000 |  | 0 |  | 0 | 100% | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 340800 |  | 0 |  | 0 |  | 0 | 100% | 340800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 340800 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 511200 |  | 0 |  | 0 |  | 0 | 100% | 511200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 511200 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 852000 |  | 0 |  | 0 |  | 0 | 100% | 852000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 852000 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 852000 |  | 0 |  | 0 |  | 0 | 10% | 85200 | 90% | 766800 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 852000 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 852000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 852000 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 852000 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 |  | 0 |  | 0 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 426000 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
C | Construction of Raw Sewage Pump House | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Column & Beam |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Roof Slab |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
D | Construction of Office Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 |  | 0 |  | 0 | 100% | 639000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 50% | 106500 | 100% | 213000 | 50% | 50% | 106500 | 99% | -49% | -104370
E | Construction of Guard Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 |  | 0 |  | 0 | 100% | 639000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 42600 | 80% | 170400 | 80% | 170400 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 99% | 1% | 2130
F | Transformer Yard,DG Yard | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 639210 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 319605 | 50% | 319605 | 50% | 319605 | 100% | 639210 | 100% | 0% | 0 | 100% | 0% | 0
| Foundation Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 50% | 799012.5 | 50% | 799012.5 | 50% | 799012.5 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 958815 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958815 | 95% | 910874.25 | 100% | 958815 | 95% | 5% | 47940.75 | 98% | -3% | -28764.45
G | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Piping & Support work | 1065350 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 905547.5 | [7 empty] | 0 | 30% | 271664.25 |  | 0 | 70% | 633883.25 |  | 0 |  | 0 | 100% | 905547.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 106535 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 106535 | 80% | 85228 | 100% | 106535 | 80% | 20% | 21307 | 100% | -20% | -21307
| (iii) On completion of Testing of equipment |  |  | 53267.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 53267.5 | 80% | 42614 | 100% | 53267.5 | 80% | 20% | 10653.5 | 100% | -20% | -10653.5
| Screen Channel | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 100% | 0% | 0
| Pumps | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 100% | 0% | 0
H | ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Cable Tray & Earthing Work | 1278420 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1086657 | [7 empty] | 0 |  | 0 | 50% | 543328.5 | 50% | 543328.5 |  | 0 |  | 0 | 100% | 1086657 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 127842 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 127842 | 100% | 127842 | 100% | 127842 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 63921 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 63921 | 100% | 63921 | 100% | 63921 | 100% | 0% | 0 | 100% | 0% | 0
| Transformer | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 2897752 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 100% | 0% | 0
| DG | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 1992204.5 | 100% | 1992204.5 | 100% | 1992204.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 | 100% | 234377 | 100% | 234377 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 | 100% | 117188.5 | 100% | 117188.5 | 100% | 0% | 0 | 100% | 0% | 0
I | Construction of Boundary wall & Internal Road | 1704560 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation & PCC |  |  | 319605 |  | 0 |  | 0 |  | 0 | 30% | 95881.5 | 40% | 127842 |  | 0 | 25% | 79901.25 | 5% | 15980.25 | 5% | 15980.25 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column footing |  |  | 426140 |  | 0 |  | 0 |  | 0 | 33% | 140626.2 | 35% | 149149 |  | 0 | 27% | 115057.8 | 5% | 21307 | 5% | 21307 | 100% | 426140 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column & Beam |  |  | 319605 |  | 0 |  | 0 |  | 0 | 20% | 63921 | 48% | 153410.4 |  | 0 | 2% | 6392.1 | 30% | 95881.5 | 30% | 95881.5 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 | 45% | 143822.25 |  | 0 |  | 0 | 55% | 175782.75 | 55% | 175782.75 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 | 100% | 319605 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| Construction of Internal road |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426140 | 80% | 340912 | 100% | 426140 | 80% | 20% | 85228 | 100% | -20% | -85228
21 | IPS-6 (Sundar Nagar- 20 MLD)-Pankha Area | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| CIVIL |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
A | Construction of Raw Sewage Sump | 16764000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 150000 | 100% | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 150000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation |  |  | 1533600 | 11% | 168696 | 89% | 1364904 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1533600 | 100% | 0% | 0 | 100% | 0% | 0
| PCC |  |  | 1022400 |  | 0 | 100% | 1022400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1022400 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 2556000 |  | 0 |  | 0 | 100% | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 2556000 |  | 0 |  | 0 | 90% | 2300400 | 10% | 255600 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 40% | 1022400 |  | 0 |  | 0 | 10% | 255600 | 50% | 1278000 | 50% | 1278000 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 2556000 |  | 0 |  | 0 |  | 0 | 25% | 639000 | 20% | 511200 | 55% | 1405800 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Ground Floor Slab |  |  | 2556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2556000 | 100% | 2556000 | 100% | 2556000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 1278000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1278000 | 100% | 1278000 | 100% | 1278000 | 100% | 0% | 0 | 100% | 0% | 0
B | Construction of Inlet Chamber & Screen Channel | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 | 100% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 0 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation & PCC |  |  | 426000 |  | 0 |  | 0 | 70% | 298200 | 30% | 127800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/Raft |  |  | 426000 |  | 0 |  | 0 |  | 0 | 80% | 340800 | 20% | 85200 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
| Wall 50% of total lift work |  |  | 426000 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
| Walls (balance 50% of Total Lift work) |  |  | 426000 |  | 0 |  | 0 |  | 0 |  | 0 | 30% | 127800 | 70% | 298200 |  | 0 |  | 0 |  | 0 | 100% | 426000 | 100% | 0% | 0 | 100% | 0% | 0
| Walkway/Platform |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
C | Construction of Raw Sewage Pump House | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Column & Beam |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Roof Slab |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 799012.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 799012.5 | 100% | 799012.5 | 100% | 799012.5 | 100% | 0% | 0 | 100% | 0% | 0
D | Construction of Office Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 | 100% | 639000 | 100% | 639000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 50% | 106500 | 100% | 213000 | 50% | 50% | 106500 | 100% | -50% | -106500
E | Construction of Guard Room | 2130000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 213000 |  | 0 |  | 0 | 100% | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Foundation/column footing |  |  | 639000 |  | 0 |  | 0 |  | 0 | 100% | 639000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639000 | 100% | 0% | 0 | 100% | 0% | 0
| Column & Beam |  |  | 213000 |  | 0 |  | 0 |  | 0 | 50% | 106500 |  | 0 |  | 0 |  | 0 | 50% | 106500 | 50% | 106500 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Ground floor Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Roof Slab |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Brick work & Plaster |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Electrification, plumbing, fixtures |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing work |  |  | 213000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 213000 | 100% | 213000 | 100% | 213000 | 100% | 0% | 0 | 100% | 0% | 0
F | Transformer Yard,DG Yard | 3196050 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 639210 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 639210 | 100% | 639210 | 100% | 639210 | 100% | 0% | 0 | 100% | 0% | 0
| Foundation Work |  |  | 1598025 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1598025 | 100% | 1598025 | 100% | 1598025 | 100% | 0% | 0 | 100% | 0% | 0
| Finishing Work |  |  | 958815 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 958815 | 95% | 910874.25 | 100% | 958815 | 95% | 5% | 47940.75 | 100% | -5% | -47940.75
G | MECHANICAL WORK |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Piping & Support work | 1278420 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1086657 | [7 empty] | 0 | 25% | 271664.25 |  | 0 | 75% | 814992.75 |  | 0 |  | 0 | 100% | 1086657 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 127842 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 127842 | 100% | 127842 | 100% | 127842 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 63921 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 63921 | 100% | 63921 | 100% | 63921 | 100% | 0% | 0 | 100% | 0% | 0
| Screen Channel | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 100% | 0% | 0
| Pumps | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 | 100% | 2897752 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 0% | 100% | 170456
H | ELECTRICAL WORK | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Cable Tray & Earthing Work | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 | 50% | 996102.25 | 50% | 996102.25 |  | 0 |  | 0 | 100% | 1992204.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 | 100% | 234377 | 100% | 234377 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 | 100% | 117188.5 | 100% | 117188.5 | 100% | 0% | 0 | 100% | 0% | 0
| Transformer | 3409120 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 2897752 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 2897752 | 100% | 2897752 | 100% | 2897752 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 340912 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 340912 | 100% | 340912 | 100% | 340912 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 170456 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 170456 | 100% | 170456 | 100% | 170456 | 100% | 0% | 0 | 100% | 0% | 0
| DG | 2343770 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| (i) On supply of machinery/equipment at site |  |  | 1992204.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 1992204.5 | 100% | 1992204.5 | 100% | 1992204.5 | 100% | 0% | 0 | 100% | 0% | 0
| (ii) On completion of erection works |  |  | 234377 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 234377 | 100% | 234377 | 100% | 234377 | 100% | 0% | 0 | 100% | 0% | 0
| (iii) On completion of Testing of equipment |  |  | 117188.5 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 100% | 117188.5 | 100% | 117188.5 | 100% | 117188.5 | 100% | 0% | 0 | 100% | 0% | 0
I | Construction of Boundary wall & Internal Road | 2130700 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Excavation & PCC |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 63921 | 80% | 255684 | 80% | 255684 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column footing |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 85228 | 80% | 340912 | 80% | 340912 | 100% | 426140 | 100% | 0% | 0 | 100% | 0% | 0
| RCC Column & Beam |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 20% | 63921 | 80% | 255684 | 80% | 255684 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| Brickwork & Plaster |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 | 100% | 319605 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
| Construction of Internal road |  |  | 426140 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 426140 | 80% | 340912 | 100% | 426140 | 80% | 20% | 85228 | 100% | -20% | -85228
| Finishing |  |  | 319605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 319605 | 100% | 319605 | 100% | 319605 | 100% | 0% | 0 | 100% | 0% | 0
22 | I&D Works | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
A | ICI Nala | 5560000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 13% | 289120 | 81% | 1801440 | 6% | 133440 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 2224000 | 100% | 0% | 0 | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1112000 | 100% | 1112000 | 100% | 1112000 | 100% | 0% | 0 | 100% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 1000800 | 40% | 667200 | 40% | 667200 | 100% | 1668000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 | 100% | 556000 | 100% | 556000 | 100% | 0% | 0 | 100% | 0% | 0
B | Thermal Nala -A | 5560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 13% | 289120 | 30% | 667200 | 30% | 667200 | 10% | 222400 | 17% | 378080 |  | 0 |  | 0 |  | 0 | 100% | 2224000 | 100% | 0% | 0 | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 667200 | 40% | 444800 |  | 0 |  | 0 | 100% | 1112000 | 100% | 0% | 0 | 100% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1668000 |  | 0 |  | 0 | 100% | 1668000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 | 100% | 556000 | 100% | 556000 | 100% | 0% | 0 | 100% | 0% | 0
C | Thermal Nala -B | 5560000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Construction Work |  |  | 2224000 |  | 0 | 14% | 311360 |  | 0 |  | 0 | 5% | 111200 |  | 0 |  | 0 | 81% | 1801440 | 81% | 1801440 | 100% | 2224000 | 100% | 0% | 0 | 100% | 0% | 0
| Tapping of Nallahs |  |  | 1112000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 1112000 | 100% | 1112000 | 100% | 1112000 | 100% | 0% | 0 | 100% | 0% | 0
| Electro-Mechanical work |  |  | 1668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 1000800 | 40% | 667200 | 40% | 667200 | 100% | 1668000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 556000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 556000 | 100% | 556000 | 100% | 556000 | 100% | 0% | 0 | 40% | 60% | 333600
23 | Rising Main Works | [21 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
A | ICI Nala Area | 6000000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Cleance from Client |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Supply of Pipes |  |  | 5100000 |  | 0 |  | 0 | 5.55% | 283314.82 | 44% | 2244000 | 25% | 1275000 |  | 0 | 5% | 255000 | 20.45% | 1042685.18 | 20.45% | 1042685.18 | 100% | 5100000 | 100% | 0% | 0 | 99.55% | 0.45% | 22950
| Excavation,Laying & backfilling of Pipes |  |  | 600000 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 360000 |  | 0 |  | 0 | 40% | 240000 | 40% | 240000 | 100% | 600000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 | 100% | 300000 | 100% | 300000 | 100% | 0% | 0 | 100% | 0% | 0
B | Sundar Nagar IPS Area | 6000000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Cleance from Client |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Supply of Pipes |  |  | 5100000 |  | 0 |  | 0 |  | 0 | 100% | 5100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 5100000 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation,Laying & backfilling of Pipes |  |  | 600000 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 360000 |  | 0 |  | 0 | 40% | 240000 | 40% | 240000 | 100% | 600000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 300000 | 100% | 300000 | 100% | 300000 | 100% | 0% | 0 | 30% | 70% | 210000
24 | Sewer System Area (RCC Pipes-NP3 Types) | 200567840 | [11 empty] | 6.453% | [8 empty] | 0% | 0.064526 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 |  |  | 0% | [11 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Supply of pipes |  |  | 160454272 | 16% | 25670093.9 | 25% | 40120136.1 | 29% | 46531738.88 | 13% | 20859055.36 | 8.5% | 13638613.12 | 0.5% | 802271.36 | 7% | 11231799.04 | 1% | 1600564.24 | 1% | 1600564.24 | 100% | 160454272 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation and Laying of pipes including bed preperation & backfilling |  |  | 10028392 |  | 0 |  | 0 | 15% | 1504258.8 | 14% | 1403974.88 | 20.55% | 2060570.556 | 27.45% | 2753057.604 |  | 0 | 23% | 2306530.16 | 22% | 2206246.24 | 100% | 10028392 | 99% | 1% | 100283.92 | 97% | 2% | 200567.84
| Manholes |  |  | 10028392 |  | 0 |  | 0 |  | 0 | 34% | 3409653.28 | 6% | 601703.52 | 11.55% | 1158015.276 | 23% | 2306530.16 | 25.45% | 2552489.764 | 22% | 2206510.24 | 100% | 10028392 | 96.55% | 3.45% | 345979.524 | 94.55% | 2% | 200567.84
| Testing |  |  | 10028392 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 10028392 | 40% | 4011356.8 | 100% | 10028392 | 40% | 60% | 6017035.2 | 0% | 40% | 4011356.8
| Road Restoration work |  |  | 10028392 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 60% | 6017035.2 | 40% | 4011356.8 | 20% | 2005678.4 | 100% | 10028392 | 80% | 20% | 2005678.4 | 98% | -18% | -1805110.56
25 | Design ,Supply,Testing & Commissioning of Sewer line (crossing National Highway-2 & Railway Track) | 18747225 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Statutory approvals from Railway & Road dept |  |  |  |  | 0 |  | 0 |  | 0 | [12 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Supply of Carrier & Casing Pipes |  |  | 11248335 |  | 0 |  | 0 |  | 0 | 57% | 6411550.95 | 30% | 3374500.5 |  | 0 | 13% | 1462283.55 |  | 0 |  | 0 | 100% | 11248335 | 100% | 0% | 0 | 100% | 0% | 0
| Construction of Pit |  |  | 937361.25 |  | 0 |  | 0 |  | 0 | 65% | 609284.8125 |  | 0 |  | 0 | 35% | 328076.4375 |  | 0 |  | 0 | 100% | 937361.25 | 100% | 0% | 0 | 100% | 0% | 0
| Excavation & Laying of Pipes thru Jack push method |  |  | 5624167.5 |  | 0 |  | 0 |  | 0 | 50% | 2812083.75 |  | 0 |  | 0 | 50% | 2812083.75 |  | 0 |  | 0 | 100% | 5624167.5 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 937361.25 |  | 0 |  | 0 |  | 0 |  | 0 | 27% | 253087.5375 |  | 0 | 23% | 223335.0875 | 50% | 460938.625 | 50% | 460938.625 | 100% | 937361.25 | 100% | 0% | 0 | 50% | 50% | 468680.625
26 | Design ,Supply,Testing & Commissioning of Treated Effulent line from STP to River Pandu | 8000000 | [20 empty] | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Site Clearance |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  |  | 0 | 0% | 0% | 0
| Construction of Effluent line from STP to River Pandu |  |  | 7200000 |  | 0 |  | 0 |  | 0 |  | 0 | 35% | 2520000 | 25% | 1800000 | 40% | 2880000 |  | 0 |  | 0 | 100% | 7200000 | 100% | 0% | 0 | 100% | 0% | 0
| Testing |  |  | 800000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 800000 | 100% | 800000 | 100% | 800000 | 100% | 0% | 0 | 50% | 50% | 400000
| TRIAL RUN & COMMISSIONING | [16 empty] | 0 | [9 empty] | 0% | 0% | 0
| Trial Run & Commissioning | [16 empty] | 0 | [9 empty] | 0% | 0% | 0
[28 empty] | 0% | 0% | 0
| Total Amount | 999728920 |  | 998718000 |  | 124839750 |  | 124839750 |  | 124839750 |  | 124839750.0025 |  | 124839750.458 |  | 124839750 |  | 124839749.825 |  | 124655279.779 |  | 108403883.22 |  |  |  |  | 16435866.559
| 1st milestone |  |  |  | = | 124839750
| 2nd milestone |  |  |  | = | 124839750
| 3rd Milestone |  |  |  | = | 124839750
| 4th Milestone |  |  |  | = | 124839750.0025 | [15 empty] | 16251396.559
| 5th Milestone |  |  |  | = | 124839750.458
| 6th Milestone |  |  |  | = | 124839750
| 7th Milestone |  |  |  | = | 124655279.779
| 8th Milestone |  |  |  | = | 108403883.22
| Total Amount |  |  |  | = | 982097663.4595
| Total % as on 31.07.2024 |  |  |  | = | 98.34%
28
6
7