## Jajmau
PROGRESS REPORT FOR 130 MLD JAJMAU SITE
| Sr. No. | Description of Items | Amount | % | BOQ Amount | 1st Milestone 10th May'21 to 15th Octber'21 |  | 2nd Milestone 16th Oct'21 to 15th March'22 |  | 3rd Milestone 16th March'22 to 28th Feb'23 |  | 4th Milestone 1st March'23 to 31st December'24 |  | 4th Milestone Achieved |  |  | Cumulative Achieve | Upto Oct'24 | Balance Work |  | 1.2.24 |  | 4th Milestone Achievement till date |  |  | Cumulative Achieved | Upto August'23 | For September'23
|  |  | 960640000 |  |  | % | Amount | % | Amount | % | Amount | % | Amount | [5 empty] | % | Amount
| I | Design & Drawing of STP | 96064000
Design | i. | On approval of BEP |  | 50% | 48032000 | 94% | 45150080 | 6% | 2881920 | 0% |  |  |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 48032000 | 0 | #REF! | 100% | #REF! | 100%
Design | ii. | On approval of design & drawings for Civil works |  | 50% | 48032000 | 80% | 38425783 | 10% | 4803017 | 10% | 4803200 |  |  | 0% | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 48032000 | 0 | #REF! | 100% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| II | REHABILITION/ RENOVATION OF EXISTING STP & IPSs | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| A. | Civil Work | 259372800 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil | i. | Retrofication for Collection chamber |  | 2% | 5187456 | 90% | 4668710.4 | 10% | 518745.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | ii. | Retrofication for Fine Screen Channel(Mechanical) |  | 7% | 18156096 | 100% | 18156096 | 0% | 0 | 0% | 0 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | iii. | Retrofication for Fine Screen Channel(Manual) |  | 2% | 5187456 | 90% | 4668710.4 | 10% | 518745.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | iv. | Retrofication for Grit Chamber |  | 7% | 18156096 | 65% | 11801462.4 | 35% | 6354633.6 | 0% | 0 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | v. | Retrofication for Parshall Flume |  | 2% | 5187456 | 99% | 5135581.44 | 1% | 51874.56 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | vi. | Retrofication for Distribution Chamber for Primary Clarifier |  | 2% | 5187456 | 40% | 2074982.4 | 60% | 3112473.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | vii. | Retrofication for Primary Sedimentation Tank |  | 7% | 18156096 | 25% | 4539024 | 25% | 4539024 | 48% | 8714926.08 | 2% | 363121.92 | 0% | 0 | 100% | 98% | 100% | 2% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | viii. | Retrofication for Distribution chamber for Aeration Tank |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
5 | ix. | Retrofication for Aeration Tank |  | 7% | 18156096 | 0% | 0 | 0% | 0 | 75% | 13603693 | 25% | 4552403 | 23% | 4189281.08 | 100% | 98% | 100% | 2% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | x. | Retrofication for Distribution Chamber for final Sedimentation Tank |  | 2% | 5187456 | 0% | 0 | 50% | 2593728 | 40% | 2074982.4 | 10% | 518745.6 | 8% | 414996.48 | 100% | 98% | 100% | 2% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xi. | Retrofication for final Sedimentation Tank |  | 7% | 18156096 | 25% | 4539024 | 25% | 4539024 | 40% | 7262438.4 | 10% | 1815609.6 | 10% | 1815609.6 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | xii. | Retrofication for Blending Tank |  | 2% | 5187456 | 73.72% | 3824192.5632 | 26.28% | 1363263.4368 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xiii. | Retrofication for Gravity Sludge Thickener |  | 7% | 18156096 | 80% | 14524876.8 | 10% | 1815609.6 | 5% | 907804.8 | 5% | 907804.8 | 5% | 907804.8 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 18156096 | 0 | #REF! | 100% | #REF! | 100%
Civil | xiv. | Retrofication for Thickened Sludge Sump |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xv. | Retrofication for Primary Sludge Digestor |  | 7% | 18156096 | 22% | 3994341.12 | 28% | 5083706.88 | 14.2% | 2578165.632 | 35.8% | 6499882.368 | 28% | 5083706.88 | 100% | 92.2% | 90.2% | 7.8% | 1416175.488 | #REF! | #REF! |  | 18156096 | 0 | #REF! | 90.2% | #REF! | 100%
Civil | xvi. | Retrofication for Secondary Digestor |  | 3% | 7781184 | 0% | 0 | 26.56% | 2066458.9033 | 0% | 0 | 73.44% | 5714725.0967 | 63% | 4902145.92 | 100% | 89.56% | 64.56% | 10.44% | 812579.1767 | #REF! | #REF! |  | 7781184 | 0 | #REF! | 59.56% | #REF! | 100%
Civil | xvii. | Retrofication for Digested Sludge Sump |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xviii. | Retrofication for Gas Holder |  | 2% | 5187456 | 0% | 0 | 50% | 2593728 | 25% | 1296864 | 25% | 1296864 | 23% | 1193114.88 | 100% | 98% | 100% | 2% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xix. | Retrofication for Return Sludge Sump |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xx. | Retrofication for Centrate/Supernatant Sump |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxi. | Retrofication for MCC Panel Room |  | 3% | 7781184 | 0% | 0 | 70% | 5446828.8 | 20% | 1556236.8 | 10% | 778118.4 | 8% | 622494.72 | 100% | 98% | 100% | 2% |  | #REF! | #REF! |  | 7781184 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxii. | Retrofication for Gas Engine Room |  | 3% | 7781184 | 0% | 0 | 70% | 5446828.8 | 25% | 1945296 | 5% | 389059.2 | 5% | 389059.2 | 100% | 100% | 95% | 0% |  | #REF! | #REF! |  | 7781184 | 0 | #REF! | 95% | #REF! | 100%
Civil | xxiii. | Retrofication for Return Sludge Pump House |  | 3% | 7781184 | 0% | 0 | 100% | 7781184 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 7781184 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxiv. | Retrofication for Thickened Sludge Pumping Station |  | 3% | 7781184 | 0% | 0 | 100% | 7781184 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 7781184 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxv. | Retrofication for Digested Sludge Pump Station |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxvi. | Retrofication for Centrifuge building/belt filter press bldg |  | 4% | 10374912 | 0% | 0 | 100% | 10374912 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 10374912 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxvii. | Retrofication for Digestor Sludge Pumping Station (Building) |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxviii. | Retrofication for Biogas Compressor Room |  | 2% | 5187456 | 0% | 0 | 100% | 5187456 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5187456 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxix. | Retrofication for Gas Flaring Unit |  | 1% | 2593728 | 0% | 0 | 95% | 2464041.6 | 5% | 129686.4 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 2593728 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxx. | Retrofication for Cooling Tower |  | 0.5% | 1296864 | 0% | 0 | 100% | 1296864 | 0% | 0 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1296864 | 0 | #REF! | 100% | #REF! | 100%
Civil | xxxi. | Retrofication for Scrubber Unit |  | 0.5% | 1296864 | 0% | 0 | 0% | 0 | 95% | 1232020.8 | 5% | 64843.2 | 5% | 64843.2 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1296864 | 0 | #REF! | 100% | #REF! | 100%
| B. | Mechanical Work(Renovation/New Procurement) | 259372800 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI | i. | Mechanical Fine Screen - Supply |  | 3% | 7781184 | 80% | 6224947.2 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 6224947.2 | 1556236.8 | #REF! | 80% | #REF! | 80%
MEI | ii. | Mechanical Fine Screen - Installation |  |  |  | 0% | 0 | 20% | 1556236.8 | 0% | 0 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1556236.8 | -1556236.8 | #REF! | 20% | #REF! | 20%
MEI | iii. | Manual Fine Screen - Supply |  | 2% | 5187456 | 80% | 4149964.8 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | iv. | Manual Fine Screen - Installation |  |  |  | 0% | 0 | 20% | 1037491.2 | 0% | 0 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | v. | Grit Mechanism - Supply |  | 3% | 7781184 | 53.33% | 4149705.4272 | 26.67% | 2075241.7728 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 6224947.2 | 1556236.8 | #REF! | 80% | #REF! | 80%
MEI | vi. | Grit Mechanism - Installation |  |  |  | 0% | 0 | 20% | 1556236.8 | 0% | 0 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1556236.8 | -1556236.8 | #REF! | 20% | #REF! | 20%
MEI | vii. | Primary Clarifier Mechanism - Supply |  | 3% | 7781184 | 0% | 0 | 53.4% | 4155152.256 | 26.6% | 2069794.944 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 6224947.2 | 1556236.8 | #REF! | 80% | #REF! | 80%
MEI | viii. | Primary Clarifier Mechanism - Installation |  |  |  | 0% | 0 | 6% | 466871.04 | 14% | 1089365.76 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1556236.8 | -1556236.8 | #REF! | 20% | #REF! | 20%
MEI | ix. | Surface Aerator - Supply |  | 10% | 25937280 | 25% | 6484320 | 2% | 518745.6 | 53% | 13746758.4 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 20749824 | 5187456 | #REF! | 80% | #REF! | 80%
MEI | x. | Surface Aerator - Installation |  |  |  | 0% |  | 6% | 1556236.8 | 14% | 3631219.2 |  | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 5187456 | -5187456 | #REF! | 20% | #REF! | 20%
MEI | xi. | FST Mechanism - Supply |  | 4% | 10374912 | 0% | 0 | 48.4% | 5021457.408 | 31.6% | 3278472.192 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 80% | #REF! | 80%
MEI | xii. | FST Mechanism - Installation |  |  | 0 | 0% | 0 | 6% | 622494.72 | 14% | 1452487.68 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 20% | #REF! | 20%
MEI | xiii. | Return Sludge Pumps - Supply |  | 4% | 10374912 | 0% | 0 | 80% | 8299929.6 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 80% | #REF! | 80%
MEI | xiv. | Return Sludge Pumps - Installation |  |  | 0 | 0% | 0 | 20% | 2074982.4 | 0% |  | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 20% | #REF! | 20%
MEI | xv. | Gravity Thickener Mechanism - Supply |  | 4% | 10374912 | 0% | 0 | 40% | 4149964.8 | 40% | 4149964.8 | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 80% | #REF! | 80%
MEI | xvi. | Gravity Thickener Mechanism - Installation |  |  |  | 0% | 0 | 10% | 1037491.2 | 9% | 933742.08 | 1% | 103749.12 | 1% | 103749.12 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 20% | #REF! | 20%
MEI | xvii. | Digestor Feed Pumps - Supply |  | 4% | 10374912 | 0% | 0 | 0% | 0 | 80% | 8299929.6 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 80% | #REF! | 80%
MEI | xviii. | Digestor Feed Pumps - Installation |  |  |  | 0% | 0 | 0% | 0 | 10% | 1037491.2 | 10% | 1037491.2 | 10% | 1037491.2 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 20% | #REF! | 20%
MEI | xix. | Sludge Digester Mixer - Primary - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xx. | Sludge Digester Mixer - Primary - Installation |  |  |  | 0% | 0 | 0% | 0 |  | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 15% | 0% | 0 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 8% | #REF! | 20%
MEI | xxi. | Digester Sludge Recirculation Pump - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxii. | Digester Sludge Recirculation Pump - Installation |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 0% | 0% | 0 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 0% | #REF! | 20%
MEI | xxiii. | Digester Sludge Heating System and Ancilliary Equipment-Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 80% | 4149964.8 | 80% | 80% | 0% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 0% | #REF! | 80%
MEI | xxiv. | Digester Sludge Heating System and Ancilliary Equipment-Installation |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 0% | 0% | 0 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 0% | #REF! | 20%
MEI | xxv. | Digested Sludge /Centrifuge Feed Pumps - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxvi. | Digested Sludge /Centrifuge Feed Pumps - Installation |  |  |  | 0% | 0 | 0% |  | 15% | 778118.4 | 5% | 259372.8 | 5% | 259372.8 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxvii. | Centrifuge Machine/ BFP - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 40% | 2074982.4 | 40% | 2074982.4 | 40% | 2074982.4 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxviii. | Centrifuge Machine/BFP - Installation |  |  |  | 0% | 0 | 0% |  | 10% | 518745.6 | 10% | 518745.6 | 10% | 518745.6 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 18% | #REF! | 20%
MEI | xxix. | Supertanant Pumps - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxx. | Supertanant Pumps - Installation |  |  |  | 0% | 0 | 0% | 0 | 5% | 259372.8 | 15% | 778118.4 | 15% | 778118.4 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxi. | Gas Scrubber with ancilliary equipment - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxii. | Gas Scrubber with ancilliary equipment - Installation |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 15% | 0% | 0 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 14% | #REF! | 20%
MEI | xxxiii. | Gas Engine with ancilliary equipment - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxiv. | Gas Engine with ancilliary equipment - Installation |  |  |  | 0% | 0 | 0% | 0 |  | 0 | 20% | 1037491.2 | 15% | 778118.4 | 20% | 15% | 0% | 5% | 259372.8 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 0% | #REF! | 20%
MEI | xxxv. | Gas Flaring System - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxvi. | Gas Flaring System - Installation |  |  |  | 0% | 0 | 0% | 0 | 18% | 933742.08 | 2% | 103749.12 | 2% | 103749.12 | 20% | 20% | 18% | 0% | 0 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 18% | #REF! | 20%
MEI | xxxvii. | Agitator for blending tank - Supply |  | 2% | 5187456 | 0% | 0 | 80% | 4149964.8 | 0% |  | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxviii. | Agitator for blending tank - Installation |  |  |  | 0% | 0 | 20% | 1037491.2 | 0% | 0 | 0% |  |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxix. | Agitator for Digester Feed Sump - Supply |  | 2% | 5187456 | 0% | 0 | 0% |  | 80% | 4149964.8 | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxx. | Agitator for Digester Feed Sump - Installation |  |  |  | 0% | 0 | 0% | 0 | 18% | 933742.08 | 2% | 103749.12 | 2% | 103749.12 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxi. | Agitator for Centrifuge Feed Sump - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxii. | Agitator for Centrifuge Feed Sump - Installation |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxiii. | Agitator for Poly Dosing Tank - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxiv. | Agitator for Poly Dosing Tank - Installation |  |  |  | 0% | 0 | 0% | 0 | 15% | 778118.4 | 5% | 259372.8 | 5% | 259372.8 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxv. | Poly Dosing Pumps - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxvi. | Poly Dosing Pumps - Installation |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxvii. | Valves - Supply |  | 4% | 10374912 | 0% | 0 | 25% | 2593728 | 0% | 0 | 55% | 5706201.6 | 30% | 3112473.6 | 80% | 55% | 80% | 25% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 80% | #REF! | 80%
MEI | xxxxviii. | Valves - Installation |  |  |  | 0% | 0 | 5% | 518745.6 | 5% | 518745.6 | 10% | 1037491.2 | 0% | 0 | 20% | 10% | 15% | 10% | 1037491.2 | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 15% | #REF! | 20%
MEI | xxxxix. | Gates (Open Channel ) - Supply |  | 4% | 10374912 | 60% | 6224947.2 | 0% | 0 | 0% | 0 | 20% | 2074982.4 | 5% | 518745.6 | 80% | 65% | 75% | 15% |  | #REF! | #REF! |  | 8299929.6 | 2074982.4 | #REF! | 60% | #REF! | 80%
MEI | xxxxx. | Gates (Open Channel ) - Installation |  |  |  | 0% | 0 | 12% | 1244989.44 | 0% | 0 | 8% | 829992.96 | 0% | 0 | 20% | 12% | 17% | 8% | 829992.96 | #REF! | #REF! |  | 2074982.4 | -2074982.4 | #REF! | 15% | #REF! | 20%
MEI | xxxxxi. | Existing Duel Fuel Generators |  | 2% | 5187456 | 0% | 0 | 0% |  |  | 0 | 100% | 5187456 | 0% | 0 | 100% | 0% | 40% | 100% | 5187456 | #REF! | #REF! |  | 5187456 | 0 | #REF! | 40% | #REF! | 100%
MEI | xxxxxii. | Gas Holder Dome- Fabrication |  | 2% | 5187456 | 0% | 0 | 0% |  | 80% | 4149964.8 | 20% | 1037491.2 |  | 0 | 100% | 80% | 80% | 20% | 1037491.2 | #REF! | #REF! |  | 5187456 | 0 | #REF! | 80% | #REF! | 100%
MEI | xxxxxiii. | Borewell Pump - Supply |  | 2% | 5187456 | 0% | 0 | 80% | 4149964.8 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxiv. | Borewell Pump - Installation |  |  |  | 10% | 518745.6 |  | 0 |  | 0 | 10% | 518745.6 | 10% | 518745.6 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxxv. | Service Water Pump - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxvi. | Service Water Pump - Installation |  |  |  | 0% | 0 | 0% | 0 |  | 0 | 20% | 1037491.2 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxxvii. | Overhead Tank - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxviii. | Overhead Tank - Erection |  |  |  | 0% | 0 | 0% | 0 |  | 0 | 20% | 1037491.2 | 20% | 1037491.2 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxxix. | Dewatering Pump for Dry well - Supply |  | 2% | 5187456 | 0% | 0 | 30% | 1556236.8 | 50% | 2593728 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxx. | Dewatering Pump for Dry well - Erection |  |  |  | 0% | 0 | 0% | 0 |  | 0 | 20% | 1037491.2 | 15% | 778118.4 | 20% | 15% | 15% | 5% | 259372.8 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 7% | #REF! | 20%
MEI | xxxxxxi. | Monorail for lifting arrangement - Supply |  | 2% | 5187456 | 60% | 3112473.6 | 20% | 1037491.2 | 0% |  | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxxii. | Monorail for lifting arrangement - Installation |  |  |  | 10.3% | 534307.968 | 9.7% | 503183.232 | 0% |  | 0% |  |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 20% | #REF! | 20%
MEI | xxxxxxiii. | DI Pipes & Fittings - Supply |  | 2% | 5187456 | 0% | 0 | 10% | 518745.6 | 70% | 3631219.2 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxxiv. | DI Pipes & Fittings - Installation |  |  |  | 0% | 0 | 1% | 51874.56 |  | 0 | 19% | 985616.64 | 17% | 881867.52 | 20% | 18% | 10% | 2% | 103749.12 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 10% | #REF! | 20%
MEI | xxxxxxv. | MS Pipes & Fittings - Supply |  | 2% | 5187456 | 0% | 0 | 0% | 0 | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxxvi. | MS Pipes & Fittings - Erection |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 1037491.2 | 15% | 778118.4 | 20% | 15% | 10% | 5% | 259372.8 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 10% | #REF! | 20%
MEI | xxxxxxvii. | SS Pipes & Fittings - Supply |  | 2% | 5187456 | 0% | 0 | 10% | 518745.6 | 70% | 3631219.2 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxxviii. | SS Pipes & Fittings - Erection |  |  |  | 0% | 0 | 1% | 51874.56 | 10% | 518745.6 | 9% | 466871.04 | 7% | 363121.92 | 20% | 18% | 18% | 2% | 103749.12 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 14% | #REF! | 20%
MEI | xxxxxxix. | Lab Equipment - Supply |  | 2% | 5187456 | 0% | 0 | 0% |  | 80% | 4149964.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 4149964.8 | 1037491.2 | #REF! | 80% | #REF! | 80%
MEI | xxxxxxx. | Lab equipment- Installation |  |  |  | 0% | 0 | 0% |  | 18% | 933742.08 | 2% | 103749.12 |  | 0 | 20% | 18% | 18% | 2% | 103749.12 | #REF! | #REF! |  | 1037491.2 | -1037491.2 | #REF! | 18% | #REF! | 20%
MEI | xxxxxxxi. | Testing & Commissioning for Mechanical Items |  | 5% | 12968640 | 0% | 0 | 30% | 3890592 | 10% | 1296864 | 60% | 7781184 | 30% | 3890592 | 100% | 70% | 70% | 30% | 4370912 | #REF! | #REF! |  | 12968640 | 0 | #REF! | 50% | #REF! | 100%
| C. | Electrical Work(Renovation/New Procurement) | 96064000 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI | i. | Supply of DP structure |  | 5% | 4803200 | 80% | 3842560 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 80% | #REF! | 80%
MEI | ii. | Installation of DP structure |  |  |  | 5% | 240160 | 5% | 240160 | 10% | 480320 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 960640 | -960640 | #REF! | 20% | #REF! | 20%
MEI | iii. | Supply of TEPH MCC Panel |  | 5% | 4803200 | 0% |  | 0% |  | 0% | 0 | 80% | 3842560 | 80% | 3842560 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 0% | #REF! | 80%
MEI | iv. | Installation TEPH MCC Panel |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 960640 | 20% | 960640 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 960640 | -960640 | #REF! | 0% | #REF! | 20%
MEI | v. | Supply of HT VCB panel |  | 10% | 9606400 | 80% | 7685120 | 0% |  | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 7685120 | 1921280 | #REF! | 80% | #REF! | 80%
MEI | vi. | Installation of HT VCB panel |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 1921280 | 20% | 1921280 | 20% | 20% | 20% | 0% |  | #REF! | #REF! | 20% | 1921280 | -1921280 | #REF! | 0% | #REF! | 20%
MEI | vii. | Supply of Transformer |  | 10% | 9606400 | 80% | 7685120 | 0% |  | 0% |  | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 7685120 | 1921280 | #REF! | 80% | #REF! | 80%
MEI | viii. | Installation of Transformer |  |  |  | 0% |  | 20% | 1921280 | 0% | 0 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 1921280 | -1921280 | #REF! | 20% | #REF! | 20%
MEI | ix. | Supply of Main PCC panel |  | 10% | 9606400 | 0% | 0 | 0% |  | 0% | 0 | 80% | 7685120 | 80% | 7685120 | 80% | 80% | 0% | 0% |  | #REF! | #REF! |  | 7685120 | 1921280 | #REF! | 0% | #REF! | 80%
MEI | x. | Installation of Main PCC panel |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 1921280 | 20% | 1921280 | 20% | 20% | 0% | 0% |  | #REF! | #REF! |  | 1921280 | -1921280 | #REF! | 0% | #REF! | 20%
MEI | xi. | Supply of Other equipments panel (MCC-2 PANEL)/Bar screen, Grit and PST panel/Thickener Panel |  | 10% | 9606400 | 0% |  | 10% | 960640 | 70% | 6724480 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 7685120 | 1921280 | #REF! | 80% | #REF! | 80%
MEI | xii. | Installation of Other equipments panel (MCC-2 PANEL)/Bar screen, Grit and PST panel/Thickener Panel |  |  |  | 0% |  | 1% | 96064 | 12% | 1152768 | 7% | 672448 | 7% | 672448 | 20% | 20% | 20% | 0% |  | #REF! | #REF! | 19% | 1921280 | -1921280 | #REF! | 20% | #REF! | 20%
MEI | xiii. | Supply of Digestor system panel (MCC-3 PANEL) |  | 10% | 9606400 | 0% |  | 0% |  | 71% | 6820544 | 9% | 864576 | 9% | 864576 | 80% | 80% | 80% | 0% |  | #REF! | #REF! | 80% | 7685120 | 1921280 | #REF! | 80% | #REF! | 80%
MEI | xiv. | Installation of Digestor system panel (MCC-3 PANEL) |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 1921280 | 20% | 1921280 | 20% | 20% | 20% | 0% |  | #REF! | #REF! | 20% | 1921280 | -1921280 | #REF! | 20% | #REF! | 20%
MEI | xv. | Supply of APFCR panel with AL reactor |  | 5% | 4803200 | 0% |  | 0% |  | 0% | 0 | 80% | 3842560 | 80% | 3842560 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 0% | #REF! | 80%
MEI | xvi. | Installation of APFCR panel with AL reactor |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 960640 |  | 0 | 20% | 0% | 0% | 20% | 960640 | #REF! | #REF! |  | 960640 | -960640 | #REF! | 0% | #REF! | 20%
MEI | xvii. | Supply of Aerators, FST and RSPS Panel (MCC-1 PANEL) |  | 5% | 4803200 | 0% |  | 0% |  | 0% | 0 | 80% | 3842560 | 80% | 3842560 | 80% | 80% | 80% | 0% |  | #REF! | #REF! | 80% | 3842560 | 960640 | #REF! | 80% | #REF! | 80%
MEI | xviii. | Installation of Aerators, FST and RSPS Panel (MCC-1 PANEL) |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 960640 | 20% | 960640 | 20% | 20% | 20% | 0% |  | #REF! | #REF! | 20% | 960640 | -960640 | #REF! | 20% | #REF! | 20%
MEI | xix. | Supply of LPBS for Motors |  | 5% | 4803200 | 0% |  | 0% | 0 | 0% | 0 | 80% | 3842560 | 40% | 1921280 | 80% | 40% | 0% | 40% | 1921280 | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 0% | #REF! | 80%
MEI | xx. | Installation of LPBS for Motors |  |  |  | 0% |  | 0% | 0 | 0% |  | 20% | 960640 |  | 0 | 20% | 0% | 0% | 20% | 960640 | #REF! | #REF! |  | 960640 | -960640 | #REF! | 0% | #REF! | 20%
MEI | xxi. | Supply of Cable Tray |  | 5% | 4803200 | 0% |  | 80% | 3842560 | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 80% | #REF! | 80%
MEI | xxii. | Installation of Cable Tray |  |  |  | 0% |  | 10% | 480320 | 0% | 0 | 10% | 480320 | 8% | 384256 | 20% | 18% | 15% | 2% | 96064 | #REF! | #REF! | 15% | 960640 | -960640 | #REF! | 14% | #REF! | 20%
MEI | xxiii. | Supply of LT Cable |  | 5% | 4803200 | 80% | 3842560 | 0% |  | 0% | 0 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 80% | #REF! | 80%
MEI | xxiv. | Installation of LT Cable |  |  |  | 0% |  | 8% | 384256 | 0% | 0 | 12% | 576384 | 7% | 336224 | 20% | 15% | 15% | 5% | 240160 | #REF! | #REF! | 15% | 960640 | -960640 | #REF! | 14% | #REF! | 20%
MEI | xxv. | Supply of Street Light Fixture |  | 5% | 4803200 | 0% |  | 72% | 3458304 | 0% | 0 | 8% | 384256 | 8% | 384256 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 72% | #REF! | 80%
MEI | xxvi. | Installation of Street Light Fixture |  |  |  | 0% |  | 18% | 864576 | 0% | 0 | 2% | 96064 | 2% | 96064 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 960640 | -960640 | #REF! | 18% | #REF! | 20%
MEI | xxvii. | Earthing Work |  | 5% | 4803200 | 70% | 3362240 | 10% | 480320 | 0% | 0 | 20% | 960640 | 17% | 816544 | 100% | 97% | 90% | 3% | 144096 | #REF! | #REF! | 90% | 4803200 | 0 | #REF! | 80% | #REF! | 100%
MEI | xxviii. | Testing & Commissioning for Electrical Items |  | 5% | 4803200 | 0% | 0 | 40% | 1921280 | 0% | 0 | 60% | 2881920 | 50% | 2401600 | 100% | 90% | 70% | 10% | 480320 | #REF! | #REF! | 70% | 4803200 | 0 | #REF! | 65% | #REF! | 100%
| D. | SUMP CUM PUMP HOUSE (200 MLD) | 35063360 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| a. | CIVIL WORK | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil | i. | Excavation |  | 5% | 1753168 | 0% | 0 | 0% | 0 | 100% | 1753168 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1753168 | 0 | #REF! | 100% | #REF! | 100%
Civil | ii. | PCC |  | 10% | 3506336 | 0% | 0 | 0% | 0 | 100% | 3506336 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 3506336 | 0 | #REF! | 100% | #REF! | 100%
Civil | iii. | Raft Foundation/Raft |  | 15% | 5259504 | 0% | 0 | 0% | 0 | 100% | 5259504 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5259504 | 0 | #REF! | 100% | #REF! | 100%
Civil | iv. | Wall 50% of total lift work |  | 15% | 5259504 | 0% | 0 | 0% | 0 | 98% | 5154313.92 | 2% | 105190.08 | 2% | 105190.08 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5259504 | 0 | #REF! | 100% | #REF! | 100%
Civil | v. | Walls (balance 50% of Total Lift work) |  | 15% | 5259504 | 0% | 0 | 0% | 0 |  | 0 | 100% | 5259504 | 100% | 5259504 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5259504 | 0 | #REF! | 100% | #REF! | 100%
Civil | vi. | Ground Floor Slab/ Walkway |  | 5% | 1753168 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1753168 | 100% | 1753168 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1753168 | 0 | #REF! | 100% | #REF! | 100%
Civil | vii. | Column & Beam work |  | 15% | 5259504 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 5259504 | 100% | 5259504 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 5259504 | 0 | #REF! | 100% | #REF! | 100%
Civil | viii. | Roof Slab |  | 5% | 1753168 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1753168 | 100% | 1753168 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1753168 | 0 | #REF! | 100% | #REF! | 100%
Civil | ix. | Brickwork & Plaster |  | 10% | 3506336 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 3506336 | 100% | 3506336 | 100% | 100% | 95% | 0% |  | #REF! | #REF! |  | 3506336 | 0 | #REF! | 0% | #REF! | 100%
Civil | x. | Finishing Work |  | 5% | 1753168 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1753168 | 85% | 1490192.8 | 100% | 85% | 40% | 15% | 262975.2 | #REF! | #REF! |  | 1753168 | 0 | #REF! | 0% | #REF! | 100%
| b. | MECHANICAL WORK |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | PUMPING SYSTEM | 28819200 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 23055360 | 0% |  | 36.36% | 8383767.2727 | 63.64% | 14671592.7273 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 23055360 | 0 | #REF! | 100% | #REF! | 100%
MEI |  | (ii) On completion of erection works |  | 15% | 4322880 | 0% |  | 6% | 259372.8 | 0% |  | 94% | 4063507.2 | 89% | 3847363.2 | 100% | 100% | 91% | 0% | 0 | #REF! | #REF! |  | 4322880 | 0 | #REF! | 6% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 1440960 | 0% |  | 0% |  | 0% |  | 100% | 1440960 | 90% | 1296864 | 100% | 90% | 60% | 10% | 144096 | #REF! | #REF! |  | 1440960 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | EOT/HOIST WORKS | 7685120 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 6148096 | 0% |  | 80% | 4918476.8 | 20% | 1229619.2 | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 6148096 | 0 | #REF! | 100% | #REF! | 100%
MEI |  | (ii) On completion of erection works |  | 15% | 1152768 | 0% |  | 0% |  | 0% |  | 100% | 1152768 | 100% | 1152768 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1152768 | 0 | #REF! | 0% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 384256 | 0% |  | 0% |  | 0% |  | 100% | 384256 | 100% | 384256 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 384256 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | ELECRICAL WORK | 6244160 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  |  |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 4995328 | 50% | 2497664 | 0% |  | 0% | 0 | 50% | 2497664 | 50% | 2497664 | 100% | 100% | 90% | 0% |  | #REF! | #REF! | 60% | 4995328 | 0 | #REF! | 50% | #REF!
MEI |  | (ii) On completion of erection works |  | 15% | 936624 | 0% |  | 0% |  | 0% |  | 100% | 936624 | 95% | 889792.8 | 100% | 95% | 90% | 5% | 46831.2 | #REF! | #REF! |  | 936624 | 0 | #REF! | 0% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 312208 | 0% |  | 0% |  | 0% |  | 100% | 312208 | 95% | 296597.6 | 100% | 95% | 80% | 5% | 15610.4 | #REF! | #REF! | 60% | 312208 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| E. | Chlorination Tank Area | 19212800 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil | i. | Excavation |  | 2.5% | 480320 | 0% | 0 | 0% |  | 100% | 480320 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 480320 | 0 | #REF! | 100% | #REF! | 100%
Civil | i. | PCC |  | 5% | 960640 | 0% | 0 | 0% |  | 100% | 960640 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 960640 | 0 | #REF! | 100% | #REF! | 100%
Civil | ii. | RCC Foundation/Raft |  | 7.5% | 1440960 | 0% | 0 | 0% | 0 | 100% | 1440960 | 0% | 0 |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1440960 | 0 | #REF! | 100% | #REF! | 100%
Civil | iii. | Wall 50% of total lift work |  | 10% | 1921280 | 0% | 0 | 0% | 0 | 15% | 288192 | 85% | 1633088 | 85% | 1633088 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1921280 | 0 | #REF! | 100% | #REF! | 100%
Civil | iv. | Walls (balance 50% of Total Lift work) |  | 10% | 1921280 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1921280 | 100% | 1921280 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1921280 | 0 | #REF! | 100% | #REF! | 100%
Civil | v. | Baffle Walls work |  | 5% | 960640 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 960640 | 100% | 960640 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 960640 | 0 | #REF! | 100% | #REF! | 100%
Civil | vi. | Connecting chanel work |  | 7.5% | 1440960 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1440960 | 100% | 1440960 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1440960 | 0 | #REF! | 80% | #REF! | 100%
Civil | ix. | Finishing Work |  | 2.5% | 480320 | 0% | 0 | 0% |  | 0% |  | 100% | 480320 | 100% | 480320 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 480320 | 0 | #REF! | 50% | #REF! | 100%
| F | Chlorination Room Area | 0 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil | i. | Excavation |  | 2.5% | 480320 | 0% | 0 | 0% |  | 0% | 0 | 100% | 480320 | 100% | 480320 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 480320 | 0 | #REF! | 100% | #REF! | 100%
Civil | i. | PCC |  | 5% | 960640 | 0% | 0 | 0% |  | 0% | 0 | 100% | 960640 | 100% | 960640 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 960640 | 0 | #REF! | 100% | #REF! | 100%
Civil | ii. | RCC Foundation/Column Footing |  | 7.5% | 1440960 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1440960 | 100% | 1440960 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1440960 | 0 | #REF! | 100% | #REF! | 100%
Civil | iii. | Column & Beam work |  | 10% | 1921280 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1921280 | 100% | 1921280 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1921280 | 0 | #REF! | 100% | #REF! | 100%
Civil | iv. | Ground Floor Slab |  | 10% | 1921280 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1921280 | 100% | 1921280 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1921280 | 0 | #REF! | 100% | #REF! | 100%
Civil | v. | Roof Slab |  | 5% | 960640 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 960640 | 100% | 960640 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 960640 | 0 | #REF! | 0% | #REF! | 100%
Civil | vi. | Brickwork |  | 5% | 960640 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 960640 | 100% | 960640 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 960640 | 0 | #REF! | 0% | #REF! | 100%
Civil | ix. | Plaster |  | 2.5% | 480320 | 0% | 0 | 0% |  | 0% | 0 | 100% | 480320 | 100% | 480320 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 480320 | 0 | #REF! | 0% | #REF! | 100%
Civil | x. | Finishing Work |  | 2.5% | 480320 | 0% | 0 | 0% |  | 0% |  | 100% | 480320 | 85% | 408272 | 100% | 85% | 40% | 15% | 72048 | #REF! | #REF! |  | 480320 | 0 | #REF! | 0% | #REF! | 100%
| a. | MECHANICAL WORK |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | CHLORINATION SYSTEM | 25937280 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 20749824 | 0% |  | 50% | 10374912 | 40% | 8299929.6 | 10% | 2074982.4 | 10% | 2074982.4 | 100% | 100% | 98% | 0% |  | #REF! | #REF! |  | 20749824 | 0 | #REF! | 90% | #REF! | 100%
MEI |  | (ii) On completion of erection works |  | 15% | 3890592 | 0% |  | 0% |  | 0% |  | 100% | 3890592 | 100% | 3890592 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 3890592 | 0 | #REF! | 0% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 1296864 | 0% |  | 0% |  | 0% |  | 100% | 1296864 | 90% | 1167177.6 | 100% | 90% | 100% | 10% |  | #REF! | #REF! |  | 1296864 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | HOIST WORKS | 4322880 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 3458304 | 0% |  | 80% | 2766643.2 | 0% | 0 | 20% | 691660.8 | 20% | 691660.8 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 3458304 | 0 | #REF! | 80% | #REF! | 100%
MEI |  | (ii) On completion of erection works |  | 15% | 648432 | 0% |  | 0% |  | 0% |  | 100% | 648432 | 100% | 648432 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 648432 | 0 | #REF! | 0% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 216144 | 0% |  | 0% |  | 0% |  | 100% | 216144 | 100% | 216144 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 216144 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | ELECRICAL & INSTRUMENTATION WORK | 7204800 |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | (i) On supply of machinery/equipment at site |  | 80% | 5763840 | 0% |  | 0% |  | 0% | 0 | 100% | 5763840 | 100% | 5763840 | 100% | 100% | 100% | 0% |  | #REF! | #REF! | 80% | 5763840 | 0 | #REF! | 50% | #REF! | 100%
MEI |  | (ii) On completion of erection works |  | 15% | 1080720 | 0% |  | 0% |  | 0% |  | 100% | 1080720 | 100% | 1080720 | 100% | 100% | 100% | 0% |  | #REF! | #REF! | 80% | 1080720 | 0 | #REF! | 0% | #REF! | 100%
MEI |  | (iii) On completion of Testing of equipment |  | 5% | 360240 | 0% |  | 0% |  | 0% |  | 100% | 360240 | 100% | 360240 | 100% | 100% | 100% | 0% |  | #REF! | #REF! | 80% | 360240 | 0 | #REF! | 0% | #REF! | 100%
| III. | RENOVATION WORK for IPS (4 nos) & CSPS (1no) | 67244800 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| a.i. | Civil Works |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Nawabganj IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil |  | a. Retrofication of Inlet Chamber |  | 2% | 1344896 | 85% | 1143161.6 | 15% | 201734.4 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | b. Retrofication of Screen Chamber |  | 2% | 1344896 | 85% | 1143161.6 | 15% | 201734.4 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | c. Retrofication of Wet Well |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | d. Retrofication of Pump House |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
| a. ii. | Mechanical Work(Servicing & Overhauling/New Procurement) | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Nawabganj IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | a. Supply of Centrifugal Pump |  | 2% | 1344896 | 0% |  | 72% | 968325.12 | 8% | 107591.68 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | b. Installation of Centrifugal Pump |  |  |  | 0% |  | 0% |  | 17% | 228632.32 | 3% | 40346.88 | 3% | 40346.88 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 17% | #REF! | 20%
MEI |  | c. SS/MS Structural Work - Supply |  | 1% | 672448 | 0% |  | 40% | 268979.2 | 40% | 268979.2 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | d. SS/MS Structural Work - Fabrication |  |  |  | 0% |  | 10% | 67244.8 | 10% | 67244.8 |  | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 20% | #REF! | 20%
MEI |  | e. Valves and NRV - Supply |  | 2% | 1344896 | 0% |  | 0% |  | 80% | 1075916.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | f. Valves and NRV - Installation |  |  |  | 0% |  | 0% |  | 18% | 242081.28 | 2% | 26897.92 | 2% | 26897.92 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 20% | #REF! | 20%
MEI |  | g. Pipe & Fitting - Supply |  | 1% | 672448 | 0% |  | 0% |  | 80% | 537958.4 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | h. Pipe & Fittings - Erection |  |  |  | 0% |  | 0% |  | 20% | 134489.6 |  | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 20% | #REF! | 20%
MEI |  | i. Monorail for lifting arrangement - Supply |  | 1% | 672448 | 40% | 268979.2 | 30% | 201734.4 |  | 0 | 10% | 67244.8 | 10% | 67244.8 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 70% | #REF! | 80%
MEI |  | j. Monorail for lifting arrangement - Installation |  |  |  | 10% | 67244.8 | 4% | 26897.92 |  | 0 | 6% | 40346.88 | 6% | 40346.88 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 14% | #REF! | 20%
MEI |  | k. Dewatering Pump for dry well - Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 80% | 537958.4 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | l. Dewatering Pump for dry well - Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 | 20% | 134489.6 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 20% | #REF! | 20%
MEI | a. iii. | Electrical Work(Servicing & Overhauling/New Procurement) |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 90% | 1210406.4 | 100% | 90% | 80% | 10% | 134489.6 | #REF! | #REF! | 80% | 1344896 | 0 | #REF! | 40% | #REF! | 100%
testing | a. iv. | Testing & Commissioning |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 85% | 1143161.6 | 100% | 85% | 50% | 15% | 201734.4 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
| b.i. | Civil Works |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Parmat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil |  | a. Retrofication of Inlet Chamber |  | 2% | 1344896 | 0% | 0 | 100% | 1344896 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | b. Retrofication of Screen Chamber |  | 2% | 1344896 | 0% | 0 | 100% | 1344896 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | c. Retrofication of Wet Well |  | 2% | 1344896 | 0% |  | 100% | 1344896 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | d. Retrofication of Pump House |  | 2% | 1344896 | 0% |  | 100% | 1344896 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
| ii. | Mechanical Work(Servicing & Overhauling/New Procurement) | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Parmat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | a. Supply of Centrifugal Pump |  | 2% | 1344896 | 0% |  | 80% | 1075916.8 | 0% |  | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | b. Installation of Centrifugal Pump |  |  |  | 0% |  | 5% | 67244.8 | 0% | 0 | 15% | 201734.4 | 5% | 67244.8 | 20% | 10% | 10% | 10% | 134489.6 | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 5% | #REF! | 20%
MEI |  | c. SS/MS Structural Work - Supply |  | 1% | 672448 | 0% |  | 70% | 470713.6 | 8% | 53795.84 | 2% | 13448.96 |  | 0 | 80% | 78% | 78% | 2% | 13448.96 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 78% | #REF! | 80%
MEI |  | d. SS/MS Structural Work - Fabrication |  |  |  | 0% |  | 14% | 94142.72 | 4% | 26897.92 | 2% | 13448.96 |  | 0 | 20% | 18% | 18% | 2% | 13448.96 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 18% | #REF! | 20%
MEI |  | e. Valves and NRV - Supply |  | 2% | 1344896 | 0% |  | 0% |  | 0% | 0 | 80% | 1075916.8 | 40% | 537958.4 | 80% | 40% | 40% | 40% | 537958.4 | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 0% | #REF! | 80%
MEI |  | f. Valves and NRV - Installation |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 268979.2 | 10% | 134489.6 | 20% | 10% | 10% | 10% | 134489.6 | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | g. Pipe & Fitting - Supply |  | 1% | 672448 | 0% |  | 0% |  | 0% | 0 | 80% | 537958.4 | 40% | 268979.2 | 80% | 40% | 40% | 40% | 268979.2 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 0% | #REF! | 80%
MEI |  | h. Pipe & Fittings - Erection |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 134489.6 | 10% | 67244.8 | 20% | 10% | 10% | 10% | 67244.8 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | i. Monorail for lifting arrangement - Supply |  | 1% | 672448 | 60% | 403468.8 | 10% | 67244.8 |  | 0 | 10% | 67244.8 |  | 0 | 80% | 70% | 70% | 10% | 67244.8 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 70% | #REF! | 80%
MEI |  | j. Monorail for lifting arrangement - Installation |  |  |  | 12% | 80693.76 | 2% | 13448.96 |  | 0 | 6% | 40346.88 |  | 0 | 20% | 14% | 14% | 6% | 40346.88 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 14% | #REF! | 20%
MEI |  | k. Dewatering Pump for dry well - Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 80% | 537958.4 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | l. Dewatering Pump for dry well - Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 | 10% | 67244.8 | 20% | 10% | 10% | 10% | 67244.8 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI | iii. | Electrical Work(Servicing & Overhauling/New Procurement) |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 80% | 1075916.8 | 100% | 80% | 80% | 20% | 268979.2 | #REF! | #REF! | 80% | 1344896 | 0 | #REF! | 40% | #REF! | 100%
testing | iv. | Testing & Commissioning |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 50% | 672448 | 100% | 50% | 50% | 50% | 672448 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
| c.i. | Civil Works |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Baba Ghat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil |  | a. Retrofication of Inlet Chamber |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | b. Retrofication of Screen Chamber |  | 2% | 1344896 | 90% | 1210406.4 | 10% | 134489.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | c. Retrofication of Wet Well |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | d. Retrofication of Pump House |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
| ii. | Mechanical Work(Servicing & Overhauling/New Procurement) | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Baba Ghat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | a. Supply of Submersible Pump alongwith Electric Motor |  | 2% | 1344896 | 0% |  | 80% | 1075916.8 | 0% |  | 0% |  |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | b. Installation of Submersible Pump alongwith Electric Motor |  |  |  | 0% |  | 15% | 201734.4 | 5% | 67244.8 | 0% | 0 |  | 0 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 20% | #REF! | 20%
MEI |  | c. SS/MS Structural Work - Supply |  | 1% | 672448 | 0% |  | 70% | 470713.6 | 0% |  | 10% | 67244.8 | 10% | 67244.8 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | d. SS/MS Structural Work - Fabrication |  |  |  | 0% |  | 14% | 94142.72 | 0% | 0 | 6% | 40346.88 | 6% | 40346.88 | 20% | 20% | 14% | 0% | 0 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 14% | #REF! | 20%
MEI |  | e. Valves and NRV - Supply |  | 2% | 1344896 | 0% |  | 0% |  | 80% | 1075916.8 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | f. Valves and NRV - Installation |  |  |  | 0% |  | 0% |  |  | 0 | 20% | 268979.2 | 20% | 268979.2 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | g. Pipe & Fitting - Supply |  | 1% | 672448 | 0% |  | 70% | 470713.6 |  | 0 | 10% | 67244.8 | 10% | 67244.8 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 70% | #REF! | 80%
MEI |  | h. Pipe & Fittings - Erection |  |  |  | 0% |  | 14% | 94142.72 |  | 0 | 6% | 40346.88 | 6% | 40346.88 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 14% | #REF! | 20%
MEI |  | i. Monorail for lifting arrangement - Supply |  | 1% | 672448 | 40% | 268979.2 | 30% | 201734.4 |  | 0 | 10% | 67244.8 | 10% | 67244.8 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 70% | #REF! | 80%
MEI |  | j. Monorail for lifting arrangement - Installation |  |  |  | 10% | 67244.8 | 4% | 26897.92 |  | 0 | 6% | 40346.88 | 6% | 40346.88 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 14% | #REF! | 20%
MEI |  | k. Dewatering Pump for dry well / wet well- Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 80% | 537958.4 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | l. Dewatering Pump for dry well/ wet well - Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 | 20% | 134489.6 | 20% | 20% | 20% | 0% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI | iii. | Electrical Work(Servicing & Overhauling/New Procurement) |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 90% | 1210406.4 | 100% | 80% | 80% | 20% | 268979.2 | #REF! | #REF! | 80% | 1344896 | 0 | #REF! | 40% | #REF! | 100%
testing | iv. | Testing & Commissioning |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 75% | 1008672 | 100% | 70% | 50% | 30% | 403468.8 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
| d.i. | Civil Works |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Guptar Ghat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil |  | a. Retrofication of Inlet Chamber |  | 2% | 1344896 | 90% | 1210406.4 | 10% | 134489.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | b. Retrofication of Screen Chamber |  | 2% | 1344896 | 90% | 1210406.4 | 10% | 134489.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | c. Retrofication of Wet Well |  | 2% | 1344896 | 90% | 1210406.4 | 10% | 134489.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | d. Retrofication of Pump House |  | 2% | 1344896 | 90% | 1210406.4 | 10% | 134489.6 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
| ii. | Mechanical Work(Servicing & Overhauling/New Procurement) | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) Guptar Ghat IPS |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | a. Supply of Centrifugal Pump |  | 2% | 1344896 | 0% |  | 0% | 0 | 80% | 1075916.8 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | b. Installation of Centrifugal Pump |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 268979.2 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | c. SS/MS Structural Work - Supply |  | 1% | 672448 | 0% |  | 0% | 0 | 80% | 537958.4 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | d. SS/MS Structural Work - Fabrication |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 134489.6 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | e. Valves and NRV - Supply |  | 2% | 1344896 | 0% |  | 0% |  | 80% | 1075916.8 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 80% | #REF! | 80%
MEI |  | f. Valves and NRV - Installation |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 268979.2 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | g. Pipe & Fitting - Supply |  | 1% | 672448 | 0% |  | 0% |  | 80% | 537958.4 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | h. Pipe & Fittings - Erection |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 134489.6 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | i. Monorail for lifting arrangement - Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 80% | 537958.4 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | j. Monorail for lifting arrangement - Installation |  |  |  | 0% |  | 0% | 0 | 0% |  | 20% | 134489.6 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | k. Dewatering Pump for dry well/ wet well - Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 80% | 537958.4 |  | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF! | 80%
MEI |  | l. Dewatering Pump for dry well / wet well- Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 | 0% | 0 | 20% | 0% | 20% | 20% |  | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI | iii. | Electrical Work(Servicing & Overhauling/New Procurement) |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 0% | 0 | 100% | 0% | 70% | 100% | 1344896 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
testing | iv. | Testing & Commissioning |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 0% | 0 | 100% | 0% | 50% | 100% | 1344896 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
| e.i. | Civil Works |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) CSPS - Jajmau |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
Civil |  | a. Retrofication of Inlet Chamber |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | b. Retrofication of Screen Chamber |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | c. Retrofication of Wet Well |  | 2% | 1344896 | 0% | 0 | 100% | 1344896 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
Civil |  | d. Retrofication of Pump House |  | 2% | 1344896 | 80% | 1075916.8 | 20% | 268979.2 | 0% |  | 0% |  |  | 0 | 100% | 100% | 100% | 0% |  | #REF! | #REF! |  | 1344896 | 0 | #REF! | 100% | #REF! | 100%
| ii. | Mechanical Work(Servicing & Overhauling/New Procurement) | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
|  | (i) CSPS - Jajmau |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI |  | a. Supply of Centrifugal Pump |  | 2% | 1344896 | 0% |  | 0% | 0 | 0% | 0 | 80% | 1075916.8 | 80% | 1075916.8 | 80% | 80% | 0% | 0% |  | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 0% | #REF!
MEI |  | b. Installation of Centrifugal Pump |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 268979.2 | 12% | 161387.52 | 20% | 12% | 0% | 8% | 107591.68 | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | c. SS/MS Structural Work - Supply |  | 1% | 672448 | 0% |  | 0% | 0 | 0% | 0 | 80% | 537958.4 | 80% | 537958.4 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 0% | #REF! | 80%
MEI |  | d. SS/MS Structural Work - Fabrication |  |  |  | 0% |  | 0% |  | 0% | 0 | 20% | 134489.6 | 4% | 26897.92 | 20% | 4% | 0% | 16% | 107591.68 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | e. Valves and NRV - Supply |  | 2% | 1344896 | 0% |  | 0% |  | 0% | 0 | 80% | 1075916.8 |  | 0 | 80% | 0% | 0% | 80% | 1075916.8 | #REF! | #REF! |  | 1075916.8 | 268979.2 | #REF! | 0% | #REF! | 80%
MEI |  | f. Valves and NRV - Installation |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 268979.2 |  | 0 | 20% | 0% | 0% | 20% | 268979.2 | #REF! | #REF! |  | 268979.2 | -268979.2 | #REF! | 0% | #REF! | 20%
MEI |  | g. Pipe & Fitting - Supply |  | 1% | 672448 | 0% |  | 0% |  | 0% | 0 | 80% | 537958.4 | 80% | 537958.4 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 0% | #REF! | 80%
MEI |  | h. Pipe & Fittings - Erection |  |  |  | 0% |  | 0% |  | 0% |  | 20% | 134489.6 |  | 0 | 20% | 0% | 0% | 20% | 134489.6 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | i. Monorail for lifting arrangement - Supply |  | 1% | 672448 | 0% | 0 | 0% |  | 0% | 0 | 80% | 537958.4 | 80% | 537958.4 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 0% | #REF! | 80%
MEI |  | j. Monorail for lifting arrangement - Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 | 20% | 134489.6 | 20% | 20% | 0% | 0% | 0 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | k. Dewatering Pump for dry well - Supply |  | 1% | 672448 | 0% | 0 | 0% | 0 | 80% | 537958.4 | 0% | 0 |  | 0 | 80% | 80% | 80% | 0% |  | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 80% | #REF!
MEI |  | l. Dewatering Pump for dry well - Installation |  |  |  | 0% |  | 0% | 0 | 0% | 0 | 20% | 134489.6 |  | 0 | 20% | 0% | 0% | 20% | 134489.6 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI |  | k. Mechanical & Manual Bar Screen - Supply |  | 1% | 672448 | 0% | 0 | 0% | 0 | 0% | 0 | 80% | 537958.4 |  | 0 | 80% | 0% | 0% | 80% | 537958.4 | #REF! | #REF! |  | 537958.4 | 134489.6 | #REF! | 0% | #REF! | 80%
MEI |  | l. Mechanical & Manual Bar Screen - Installation |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 134489.6 |  | 0 | 20% | 0% | 0% | 20% | 134489.6 | #REF! | #REF! |  | 134489.6 | -134489.6 | #REF! | 0% | #REF! | 20%
MEI | iii. | Electrical Work(Servicing & Overhauling/New Procurement) |  | 1% | 672448 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 672448 | 85% | 571580.8 | 100% | 85% | 80% | 15% | 100867.2 | #REF! | #REF! | 80% | 672448 | 0 | #REF! | 70% | #REF! | 100%
testing | iv. | Testing & Commissioning |  | 2% | 1344896 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 1344896 | 40% | 537958.4 | 100% | 40% | 0% | 60% | 806937.6 | #REF! | #REF! |  | 1344896 | 0 | #REF! | 0% | #REF! | 100%
| IV. | RTOLM WORK for STP ,IPS & CSPS Aea | 48032000 | [6 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
| 1 | STP Aea | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI | i. | Supply of Local Field Instruments for STP facility |  | 7% | 3362240 | 0% | 0 | 10% | 336224 | 0% | 0 | 70% | 2353568 | 70% | 2353568 | 80% | 80% | 80% | 0% |  | #REF! | #REF! | 80% | 2689792 | 672448 | #REF! | 30% | #REF! | 80%
MEI | ii. | Installation of Local Field Instruments for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 672448 | 10% | 336224 | 20% | 10% | 5% | 10% | 336224 | #REF! | #REF! |  | 672448 | -672448 | #REF! | 5% | #REF! | 20%
MEI | iii. | Supply of Remote Field Instruments for STP facility |  | 7% | 3362240 | 0% | 0 | 0% |  | 0% | 0 | 80% | 2689792 | 80% | 2689792 | 80% | 80% | 70% | 0% | 0 | #REF! | #REF! | 70% | 2689792 | 672448 | #REF! | 10% | #REF! | 80%
MEI | iv. | Installation of Remote Field Instruments for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 672448 | 10% | 336224 | 20% | 10% | 0% | 10% | 336224 | #REF! | #REF! |  | 672448 | -672448 | #REF! | 0% | #REF! | 20%
MEI | v. | Supply of False Floor at PLC Control Room for STP facility |  | 5% | 2401600 | 0% | 0 | 0% |  | 0% | 0 | 80% | 1921280 | 80% | 1921280 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 1921280 | 480320 | #REF! | 0% | #REF! | 80%
MEI | vi. | Installation of False Floor at PLC Control Room for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 480320 | 10% | 240160 | 20% | 10% | 0% | 10% | 240160 | #REF! | #REF! |  | 480320 | -480320 | #REF! | 0% | #REF! | 20%
MEI | vii. | Supply of AC at PLC Control Room for STP facility |  | 2% | 960640 | 0% | 0 | 0% |  | 0% | 0 | 80% | 768512 |  | 0 | 80% | 0% | 0% | 80% | 768512 | #REF! | #REF! |  | 768512 | 192128 | #REF! | 0% | #REF! | 80%
MEI | viii. | Installation of AC at PLC Control Room for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 192128 |  | 0 | 20% | 0% | 0% | 20% | 192128 | #REF! | #REF! |  | 192128 | -192128 | #REF! | 0% | #REF! | 20%
MEI | ix. | Supply of PLC Panel for STP facility |  | 7% | 3362240 | 0% | 0 | 0% |  | 0% | 0 | 80% | 2689792 | 80% | 2689792 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 2689792 | 672448 | #REF! | 0% | #REF! | 80%
MEI | x. | Installation of PLC Panel for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 672448 | 0% | 0 | 20% | 0% | 0% | 20% | 672448 | #REF! | #REF! |  | 672448 | -672448 | #REF! | 0% | #REF! | 20%
MEI | xi. | Supply of AC at RIO Panel Room for STP facility |  | 2% | 960640 | 0% | 0 | 0% |  | 0% | 0 | 80% | 768512 |  | 0 | 80% | 0% | 0% | 80% | 768512 | #REF! | #REF! |  | 768512 | 192128 | #REF! | 0% | #REF! | 80%
MEI | xii. | Installation of AC at RIO Panel Room for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 192128 |  | 0 | 20% | 0% | 0% | 20% | 192128 | #REF! | #REF! |  | 192128 | -192128 | #REF! | 0% | #REF! | 20%
MEI | xiii. | Supply of RIO Panel for STP facility |  | 5% | 2401600 | 0% | 0 | 0% |  | 0% | 0 | 80% | 1921280 | 80% | 1921280 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 1921280 | 480320 | #REF! | 0% | #REF! | 80%
MEI | xiv. | Installation of RIO Panel for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 480320 | 10% | 240160 | 20% | 10% | 0% | 10% | 240160 | #REF! | #REF! |  | 480320 | -480320 | #REF! | 0% | #REF! | 20%
MEI | xv. | Supply of UPS & UPS ACDB for STP facility |  | 5% | 2401600 | 0% | 0 | 0% |  | 0% | 0 | 80% | 1921280 |  | 0 | 80% | 0% | 0% | 80% | 1921280 | #REF! | #REF! |  | 1921280 | 480320 | #REF! | 0% | #REF! | 80%
MEI | xvi. | Installation of UPS & UPS ACDB for STP facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 480320 |  | 0 | 20% | 0% | 0% | 20% | 480320 | #REF! | #REF! |  | 480320 | -480320 | #REF! | 0% | #REF! | 20%
MEI | xvii. | Supply of Instrument, Control & Bus Cable Work for STP facility |  | 10% | 4803200 | 0% | 0 | 30% | 1440960 | 0% | 0 | 50% | 2401600 | 40% | 1921280 | 80% | 70% | 30% | 10% | 480320 | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 30% | #REF! | 80%
MEI | xviii. | Installation of Instrument, Control & Bus Cable Work for STP facility |  |  |  | 0% | 0 | 5% | 240160 | 0% | 0 | 15% | 720480 | 5% | 240160 | 20% | 10% | 5% | 10% | 480320 | #REF! | #REF! |  | 960640 | -960640 | #REF! | 5% | #REF! | 20%
MEI | xix. | Testing & Commissioning of PLC & RIO for STP facility |  | 5% | 2401600 | 0% | 0 | 0% |  | 0% | 0 | 100% | 2401600 |  | 0 | 100% | 0% | 0% | 100% | 2401600 | #REF! | #REF! |  | 2401600 | 0 | #REF! | 0% | #REF! | 100%
MEI | 2 | IPS & CSPS Aea | [7 empty] | 0 |  | 0 |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  | 0 | 0 | #REF! | 0% | #REF!
MEI | i. | Supply of Local Field Instruments for IPS & CSPS facility |  | 7% | 3362240 | 0% | 0 | 0% |  | 0% | 0 | 80% | 2689792 | 80% | 2689792 | 80% | 80% | 80% | 0% |  | #REF! | #REF! | 80% | 2689792 | 672448 | #REF! | 10% | #REF! | 80%
MEI | ii. | Installation of Local Field Instruments for IPS & CSPS facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 672448 |  | 0 | 20% | 0% | 0% | 20% | 672448 | #REF! | #REF! |  | 672448 | -672448 | #REF! | 0% | #REF! | 20%
MEI | iii. | Supply of Remote Field Instruments for IPS & CSPS facility |  | 7% | 3362240 | 0% | 0 | 0% |  | 0% | 0 | 80% | 2689792 | 80% | 2689792 | 80% | 80% | 70% | 0% |  | #REF! | #REF! | 70% | 2689792 | 672448 | #REF! | 0% | #REF! | 80%
MEI | iv. | Installation of Remote Field Instruments for IPS & CSPS facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 672448 |  | 0 | 20% | 0% | 0% | 20% | 672448 | #REF! | #REF! |  | 672448 | -672448 | #REF! | 0% | #REF! | 20%
MEI | v. | Supply of RTU/RIO Panel for IPS & CSPS facility |  | 6% | 2881920 | 0% | 0 | 0% |  | 0% | 0 | 80% | 2305536 | 80% | 2305536 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 2305536 | 576384 | #REF! | 0% | #REF! | 80%
MEI | vi. | Installation of RTU/RIO Panel for IPS & CSPS facility |  |  |  | 0% | 0 | 0% |  | 0% | 0 | 20% | 576384 |  | 0 | 20% | 0% | 0% | 20% | 576384 | #REF! | #REF! |  | 576384 | -576384 | #REF! | 0% | #REF! | 20%
MEI | vii. | Supply of UPS for IPS & CSPS facility |  | 5% | 2401600 | 0% | 0 | 0% |  | 0% |  | 80% | 1921280 |  | 0 | 80% | 0% | 0% | 80% | 1921280 | #REF! | #REF! |  | 1921280 | 480320 | #REF! | 0% | #REF! | 80%
MEI | viii. | Installation of UPS for IPS & CSPS facility |  |  |  | 0% | 0 | 0% |  | 0% |  | 20% | 480320 |  | 0 | 20% | 0% | 0% | 20% | 480320 | #REF! | #REF! |  | 480320 | -480320 | #REF! | 0% | #REF! | 20%
MEI | ix. | Supply of Instrument, Control & Bus Cable Work for IPS & CSPS facility |  | 10% | 4803200 | 0% | 0 | 0% | 0 | 0% | 0 | 80% | 3842560 | 80% | 3842560 | 80% | 80% | 0% | 0% | 0 | #REF! | #REF! |  | 3842560 | 960640 | #REF! | 0% | #REF! | 80%
MEI | x. | Installation of Instrument, Control & Bus Cable Work for IPS & CSPS facility |  |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 20% | 960640 |  | 0 | 20% | 0% | 0% | 20% | 960640 | #REF! | #REF! |  | 960640 | -960640 | #REF! | 0% | #REF! | 20%
MEI | xi. | Testing & Commissioning of RTU/RIO for IPS & CSPS facility |  | 5% | 2401600 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 2401600 |  | 0 | 100% | 0% | 0% | 100% | 2401600 | #REF! | #REF! |  | 2401600 | 0 | #REF! | 0% | #REF! | 100%
MEI | xii. | Testing & Commissioning of Cloud based RTOLMS facility |  | 5% | 2401600 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 2401600 |  | 0 | 100% | 0% | 0% | 100% | 2401600 | #REF! | #REF! |  | 2401600 | 0 | #REF! | 0% | #REF! | 100%
[6 empty] | 0% | 0 | 0% |  | 0% |  |  |  |  | 0 |  | 0% | 0% | 0% |  | #REF! | #REF! |  |  | 0 | #REF! | 0% | #REF!
| V | TRIAL RUN & COMMISSIONING | [14 empty] | 0% | 0% | 0% |  | #REF! | #REF! |  |  | 0 | #REF! | 0% | #REF!
Testing | 1 | Trial Run & Commissioning | [14 empty] | 0% | 0% | 0% |  | #REF! | #REF! |  |  | 0 | #REF! | 0% | #REF!
|  | Total | 960640000 |  | 960640000 |  | 240160000.4784 |  | 240159999.5216 |  | 240160000.0953 |  | 240159999.9047 |  | 183026106.2 |  | 0% |  |  | 50117379.1447 |  | #REF! |  | 0 | 960640000 | #REF! | 0% | #REF!
[10 empty] | 0 | [6 empty] | 0% | [7 empty] | 0 | #REF! | 0% | #REF!
[25 empty] | 0 | #REF! |  | #REF!
| Sl. No | Milestone Details |  |  | Amount | [22 empty] | 0%
| 1 | 1st Milestone |  |  | 240160000.4784 | [22 empty] | 0%
| 2 | 2nd Milestone |  |  | 240159999.5216 | [22 empty] | 0%
| 3 | 3rd Milestone |  |  | 240160000.0953 | [22 empty] | 0%
| 4 | 4th Milestone |  |  | 183026106.2 | [22 empty] | 0%
|  | Total Amount |  |  | 903506106.2953 | [22 empty] | 0%
|  | Progress Percentage as on 28.02.2025 |  |  | 94.05% | [22 empty] | 0%
| Note: | [23 empty] | 0 |  |  | 0%
| 1) Above listed are itemwise major activities, but all required works/items must be included & completed as per approved drawings & design, as project is turnkey basis; | [23 empty] | 0 |  |  | 0%
| 2) Variation clause applicable | [23 empty] | 0 |  |  | 0%
| 3) Items/Payments shall be as per relevant clauses of Concessionaire Agreement | [23 empty] | 0 |  |  | 0%
| 4) During Billing activity may interchange but as per approved schedule amount to be calculated. | [23 empty] | 0 |  |  | 0%